##### Metropolitan King County Council

Capital Budget Committee

| AGENDA ITEM No.: | 5, 6 |  | DATE: | August 30, 2006 |
| --- | --- | --- | --- | --- |
| PROPOSED NO.: | O 2006-0390 M 2006-0391 |  | PREPARED BY: | Patrick Hamacher Mark Melroy |

STAFF REPORT

SUBJECT:

Proposed Ordinance 2006-0390 would appropriate $375,000 to the building repair and replacement fund for continued design work on the Courthouse South Entry project. Proposed Motion 2006-0391 would identify a number of steps and studies that must be completed prior to approval of final funding of the construction project to reopen the South entrance to the County Courthouse.

BACKGROUND:

Metropolitan King County’s 2006 adopted budget totals approximately $3.46 billion dollar. Of that amount, $796 million represents the capital improvement (CIP) budget. This proposed ordinance would increase the CIP budget by $375,000.

Historically, the primary entrance to the Courthouse was on the South side of the Courthouse in the area that is currently the loading dock. The service entrance to the Courthouse was at the basement level, which was accessed via a vehicular tunnel below City Hall Park. The entrance to this tunnel is located at the South end of City Hall Park between Dilling Way and the Yelser overpass. In 1967, based on increasingly limited vehicular service access in the basement, the tunnel was abandoned as the service entrance for the Courthouse. The historic South entrance was converted to a loading dock and the primary access was relocated to the 3rd Avenue and 4th Avenue entrances on the first and second floors.

Re-Opening of the South Entrance:

Preliminary planning and design work was undertaken on a South entrance to the Courthouse. The impact of the Nisqually earthquake affected projects at the Courthouse. The Courthouse and Seismic Project or CASP project shifted the focus of the Courthouse construction to more urgent needs. Preliminary work and schematic drawings were completed as late as January of 2001 just weeks before the earthquake hit. Details of the project as envisioned at the time are included below:

Scope:

The scope of work for restoration of the Courthouse South Entry included:

- Restoration of the historic south entry,

- Relocation of loading dock services to the south end of City Hall Park,

- City Hall park landscape and hardscape improvements,

- Development of a separate WER entrance,

- Elevator modifications and addition of new stairs and escalators,

- Reconfiguration of 3rd and 4th Avenue Entrances to Exit only, and

- Lobby improvements.

Copies of the South Entry Restoration design and basis of design narrative prepared by the design team (Coughlin, Porter, Lundeen) are available upon request.

Schedule:

The direction to initiate a design to restore the historic South Entry to the Courthouse did not occur until midway through the schematic design phase of the Courthouse Seismic Project which resulted in the south entrance design slightly behind the schedule for the core seismic project.  Additionally, because the South Entry design included an interface with the City Hall Park it was necessary to coordinate with City of Seattle and community stakeholders in an open public process.  The Design Development phase for the core seismic project was concluded on January 19, 2001.

Immediately following the Nisqually Earthquake on February 28, 2001, the Executive recommended to the Council that design work on the South Entry Restoration alternate be stopped in order to allow the design team to focus all of their efforts on completion of the core seismic project.  The BFM Committee members concurred with the Executive’s recommendation and the project was stopped.

Budget:

Because the South Entry was discretionary and not part of the original “Fire and Life Safety” core seismic project it was tracked separately from the core seismic project.   In order to avoid the possibility of potential future budget and/or permitting conflicts the South Entry restoration project was tracked as a separate additive bid alternate.  Following the direction to stop work on the South Entry design in March 2001, a final design development cost estimate for the South Entry Restoration was submitted on April 5, 2001 for $6.7 million.

Courthouse Seismic Project Construction:

During construction of the Courthouse Seismic Project the existing loading dock and Jefferson Street were used as the site for the tower crane and construction service access.

Courthouse Seismic Project – Lobbies Project:

In June 2003, after the Courthouse Seismic Project was underway, the Executive proposed a Courthouse Lobbies Project that incorporated several elements of the previous South Entry Restoration Project.  The $8.0 million Lobbies Project was implemented as an amendment to the Courthouse Seismic Project and included improvements to the 3rd Avenue and 4th Avenue building entrances, reconfiguration of security access equipment to improve traffic flow and equipment upgrades to improve elevator service.  The project combined art projects and historic finishes to improve the historic character of the entrance lobbies.  The project:

- Reconfigured the entrances on 3rd and 4th Avenues and upgraded the security screening equipment and processing layout.

- Upgraded elevator service by activating two additional elevators and provided a state of the art control system to significantly improve the capability of the existing elevators.  The existing elevator cab interiors were refurbished.

- Provide major architectural refurbishment of the 1st and 2nd floor lobbies consistent with the original Courthouse design.

- Art projects.

The Courthouse Lobbies Project was completed in May 2005.  The Courthouse Lobbies project scope of work did not include restoration of the south entry, relocation of the loading dock, separate WER entrance, or City Hall Park improvements.

City Hall Park:

When discussing City Hall Park, to be clear, we’re referring to a City of Seattle public park, which is located at the South end of the King County Courthouse between Jefferson St. on the North, Dilling Way on the South, 4th Avenue on the East and 3rd Avenue on the West. This public park covers area of 1.3 acres and contains walking and sitting areas.

The City of Seattle’s 2005-2006 budget includes $100,000 for planning and initial design work for the park itself. The Mayor also requested $400,000 for final design and construction. This funding has not yet been approved. The City is currently undertaking a project titled “City Hall Park Improvement Project” with the goal of transforming City Hall Park into an attractive gateway to downtown Seattle. The City has further been presenting its redevelopment plan to neighborhood groups and also briefed the Committee of the Whole on June 5, 2006. The current estimates for the redevelopment project in City Hall Park are $3.5 to $4.0 million.

ANALYSIS:

On May 3, 2006, the CBC heard a briefing regarding the close-out of the Courthouse Seismic Project (2006-B0076). At that time members were made aware of the fact that several areas of the project had funds remaining. The Courthouse South Entry project was one of these. After work was stopped in 2001, there was $104,503 left unspent. At that time, the Committee took action to reappropriate those funds to a new project called the Courthouse South Entry project. The funds were to be used to update financial assumptions contained in the 2001 estimates.

Proposed Ordinance 2006-0390

With approval of funds earlier this year (2006-0243), the Facilities Management Division (FMD) was able contract with Seneca Real Estate to update the cost estimates from 2001. Seneca was charged with determining a new cost estimate for the South Entrance project after determining which pieces of the original design have been completed via other Courthouse projects. The initial report to FMD indicated a construction cost of approximately $7.8 million.

That estimate makes a number of assumptions including a 10% annual construction escalation and a 20% construction contingency. These appear to be sufficient to insulate against large increases in cost due to market pressures.

Currently the project has a limited set of project designs (from 2001) and a rough estimate of the total project construction cost. Seneca has estimated that it will cost approximately $375,000 to complete a final set of designs. These designs would be the type used to put the project out to bid. This proposed ordinance would make an appropriation in the amount of $375,000 to accomplish this task.

Proposed Motion 2006-0391

The accompanying motion indicates that that the policy decision on future funding of the construction of a Courthouse South Entry should not be made until a number of other policy studies have been completed. The Executive’s transmittal letter indicates that he will not support any construction funding of a future Courthouse South Entry project until the following tasks are completed:

- An Evaluation of the feasibility of applying the 10% for arts funding from future real estate sales to the art and historic preservation pieces of this project.

- A joint evaluation between the King County Sheriffs Office and FMD/OMB on the feasibility of closing the Third and Fourth Avenue entrances to the Courthouse. The transmittal letter indicates that input shall be taken, document and considered from all branches of county government.

- Pursuit of potential grant funding

- A full evaluation of the impacts to Current Expense Fund CIP debt capacity and potential impacts to other projects.

The motion indicates that the County Executive will prepare a report evaluating these factors. That report will be transmitted to the County Council, who will evaluate the report and adopt a motion containing the findings of the report. When these tasks are completed, construction funding for the project could be approved. The Executive’s transmittal letter indicates that he will not support any future funding for this project until the study has been completed and the County Council has adopted a motion containing its findings.

REASONABLENESS:

Proposed Ordinance 2006-0390 would allow the County to proceed with finalizing design documents for the project. This is the next step in moving forward with the South Entry Project. It should be noted also, that the county typically incurs 20%-30% of the construction costs for planning and design work. With a $7.8 million construction estimate, this amount would be $1.56 million to $2.34 million, so the county is benefiting from much of the design work that was completed in 2001. Adoption of this ordinance would constitute a reasonable business and policy decision.

Proposed Motion 2006-0391, in effect, allows the Council to concur with the County Executive that there are still a number of outstanding issues related to the progression of this project from design to construction.

The Council typically expects the Executive branch to conduct this type of research and study prior to asking the Council for approval of a CIP project. For example, the Council would expect that the Executive would search for grant funding and evaluate the County’s ability to fund the project prior to making a CIP request. This does not represent a problem.

The Executive also indicates that there needs to be study done on the security and access issues related to the closure of the East and West entrances and public access to the building. This has been a concern to Councilmember in prior meetings and therefore warrants discussion prior to final CIP approval.

For these reasons, adoption of Proposed Motion 2006-0391 would represent a reasonable policy decision.

INVITED:

Kathy Brown, Director, DES Facilities Management Division

ATTACHMENTS:

1.  Proposed Ordinance 2006-0390

2.  Proposed Ordinance 2006-0391

3.  Transmittal Letter

4.  Fiscal Note

5.  Seneca Group Memorandum and Estimate