## Target expenditure by phase
Master Project No | Project No | Project Name | LTD Expend through 9/30/11 | Encumbrance through 9/30/11 | EAC on 9/30/11 | Phase on 9/30/11 | Target % Expended (a)* | Target (a) Expenditure + Encumbrance | Actual Expenditure + Encumbrance | Variance from target (a) (negative is overspent) | % Over/underspent vs. (a) Assumed | Target % Expended (b)* | Target (b) Expenditure + Encumbrance | Actual Expenditure + Encumbrance | Variance from target (b) (negative is overspent) | % Over/underspent vs. (b) Assumed
341299 | 99M099 | MRJC Detention Building HVAC Improvements | 78245.87 | 213624 | 220661 | Implementation | 90 | 198594.9 | 291869.87 | -93274.97 | -42.27% | 60 | 132396.6 | 291869.87 | -159473.27 | -72.27%
341299 | 99M105 | RCECC HVAC Study | 50212.41 | 4500 | 50000 | Preliminary Design | 30 | 15000 | 54712.41 | -39712.41 | -79.42% | 15 | 7500 | 54712.41 | -47212.41 | -94.42%
341602 | 341602 | YSC Alder Fire Alarm | 283765.16 | 0 | 450000 | Construction | 90 | 405000 | 283765.16 | 121234.84 | 26.94% | 60 | 270000 | 283765.16 | -13765.16 | -3.059%
342400 | 342400 | Admin Bldg Domestic Water Pipe Replacement Ph 2 | 161837.64 | 80102.8 | 380000 | Planning | 30 | 114000 | 241940.44 | -127940.44 | -33.67% | 15 | 57000 | 241940.44 | -184940.44 | -48.67%
342413 | 342413 | Admin Bldg Floor Finishes | 212039.31 | 0 | 528000 | Construction | 90 | 475200 | 212039.31 | 263160.69 | 49.84% | 60 | 316800 | 212039.31 | 104760.69 | 19.84%
342421 | 342421 | BD Evidence and Lab-Whse Distribution Systems | 21199.89 | 14621.88 | 228000 | Final Design | 30 | 68400 | 35821.77 | 32578.23 | 14.29% | 15 | 34200 | 35821.77 | -1621.77 | -0.7113%
342439 | 342439 | CH Window Repair - Design | 390596.75 | 0 | 404845 | Construction | 90 | 364360.5 | 390596.75 | -26236.25 | -6.481% | 60 | 242907 | 390596.75 | -147689.75 | -36.48%
342440 | 342440 | CH Window Repair, Ph.1 & 2 Construction | 2684400.26 | 0 | 3340366 | Final Design | 30 | 1002109.8 | 2684400.26 | -1682290.46 | -50.36% | 15 | 501054.9 | 2684400.26 | -2183345.36 | -65.36%
342440 | 440M03 | CH Window Repair Phase III Design | 9482.26 | 81040 | 179434 | Final Design | 30 | 53830.2 | 90522.26 | -36692.06 | -20.45% | 15 | 26915.1 | 90522.26 | -63607.16 | -35.45%
342445 | 342445 | CH Domestic Water Distribution (repipe) | 277144.19 | 40889.5 | 147470 | Planning | 30 | 44241 | 318033.69 | -273792.69 | -185.7% | 15 | 22120.5 | 318033.69 | -295913.19 | -200.7%
342446 | 342446 | Courthouse Plumbing Fixtures (Wk Release Showers) | 23811.76 | 35200 | 722601 | Preliminary Design | 30 | 216780.3 | 59011.76 | 157768.54 | 21.83% | 15 | 108390.15 | 59011.76 | 49378.39 | 6.833%
342454 | 342454 | Courthouse Exterior Walls | 183101.72 | 27550.225 | 1427316 | Final Design | 30 | 428194.8 | 210651.945 | 217542.855 | 15.24% | 15 | 214097.4 | 210651.945 | 3445.455 | 0.2414%
342454 | 454M01 | Courthouse South Elevations | 4832.75 | 85474.675 | 390000 | Construction | 90 | 351000 | 90307.425 | 260692.575 | 66.84% | 60 | 234000 | 90307.425 | 143692.575 | 36.84%
342458 | 342458 | Courthouse HVAC Controls | 541174.54 | 0 | 755967 | Construction | 90 | 680370.3 | 541174.54 | 139195.76 | 18.41% | 60 | 453580.2 | 541174.54 | -87594.34 | -11.59%
342459 | 342459 | CH HVAC (Induction Air Repairs) | 1409536.93 | 0 | 9000000 | Implementation | 90 | 8100000 | 1409536.93 | 6690463.07 | 74.34% | 60 | 5400000 | 1409536.93 | 3990463.07 | 44.34%
342459 | 459M01 | CH HVAC Study | 57654.16 | 3616.25 | 84000 | Construction | 90 | 75600 | 61270.41 | 14329.59 | 17.06% | 60 | 50400 | 61270.41 | -10870.41 | -12.94%
342460 | 342460 | CH Floor Finishes | 157574.61 | 0 | 499871 | Construction | 90 | 449883.9 | 157574.61 | 292309.29 | 58.48% | 60 | 299922.6 | 157574.61 | 142347.99 | 28.48%
342483 | 342483 | DC Shoreline Fire Alarm | 187386.08 | 8162.9 | 130000 | Closeout | 100 | 130000 | 195548.98 | -65548.98 | -50.42% | 95 | 123500 | 195548.98 | -72048.98 | -55.42%
342608 | 342608 | RJC-Detention Emergency Generator Phase 2 | 83230.57 | 630 | 104900 | Preliminary Design | 30 | 31470 | 83860.57 | -52390.57 | -49.94% | 15 | 15735 | 83860.57 | -68125.57 | -64.94%
342618 | 342618 | KCCF Water Pipe Replacement | 1057638.81 | 3770842.75 | 5360628 | Implementation | 90 | 4824565.2 | 4828481.56 | -3916.36 | -0.07306% | 60 | 3216376.8 | 4828481.56 | -1612104.76 | -30.07%
342621 | 342621 | KCCF Terminal and Package Units | 75372.36 | 140486.5 | 522663 | Preliminary Design | 30 | 156798.9 | 215858.86 | -59059.96 | -11.3% | 15 | 78399.45 | 215858.86 | -137459.41 | -26.3%
342629 | 342629 | KCCF Floor 2 Court Detail Cooling | 13975.61 | 12426.8 | 115975 | Final Design | 30 | 34792.5 | 26402.41 | 8390.09 | 7.234% | 15 | 17396.25 | 26402.41 | -9006.16 | -7.766%
342634 | 342634 | DC NE Redmond Site Lighting | 12553.28 | 0 | 33897 | Closeout | 100 | 33897 | 12553.28 | 21343.72 | 62.97% | 95 | 32202.15 | 12553.28 | 19648.87 | 57.97%
342647 | 342647 | PH Eastgate Boxes (VAV, Mixing) | 424323.45 | 309866.065 | 938977 | Construction | 90 | 845079.3 | 734189.515 | 110889.785 | 11.81% | 60 | 563386.2 | 734189.515 | -170803.315 | -18.19%
342650 | 342650 | PH Eastgate Controls and Instrumentation | 118220.13 | 55122.83 | 155000 | Construction | 90 | 139500 | 173342.96 | -33842.96 | -21.83% | 60 | 93000 | 173342.96 | -80342.96 | -51.83%
342657 | 342657 | PH Federal Way Boxes (VAV, Mixing) | 460388.98 | 315183.82 | 1050339 | Construction | 90 | 945305.1 | 775572.8 | 169732.3 | 16.16% | 60 | 630203.4 | 775572.8 | -145369.4 | -13.84%
342659 | 342659 | DC NE Redmond Fittings | 3936.93 | 0 | 19540 | Design | 30 | 5862 | 3936.93 | 1925.07 | 9.852% | 15 | 2931 | 3936.93 | -1005.93 | -5.148%
342666 | 342666 | PH NDMSC Electrical Service & Distribution | 19460.14 | 0 | 19460 | Closeout | 100 | 19460 | 19460.14 | -0.14 | -0.0007194% | 95 | 18487 | 19460.14 | -973.14 | -5.001%
342680 | 342680 | PH Renton Testing & Balancing | 6110.81 | 0 | 20000 | Final Design | 30 | 6000 | 6110.81 | -110.81 | -0.5541% | 15 | 3000 | 6110.81 | -3110.81 | -15.55%
342691 | 342691 | PH - White Center Floor finishes | 237421.03 | 0 | 280700 | Implementation | 90 | 252630 | 237421.03 | 15208.97 | 5.418% | 60 | 168420 | 237421.03 | -69001.03 | -24.58%
342692 | 342692 | PH White Center Exterior Wall Finishes | 207638.4 | 59688.245 | 202163 | Closeout | 100 | 202163 | 267326.645 | -65163.645 | -32.23% | 95 | 192054.85 | 267326.645 | -75271.795 | -37.23%
342759 | 342759 | Shoreline DC HVAC Units | 1123505.82 | 94260.46 | 1154900 | Closeout | 100 | 1154900 | 1217766.28 | -62866.28 | -5.443% | 95 | 1097155 | 1217766.28 | -120611.28 | -10.44%
342762 | 342762 | DC SW Burien Parking Lots | 125130.99 | 13871.94 | 130000 | Closeout | 100 | 130000 | 139002.93 | -9002.93 | -6.925% | 95 | 123500 | 139002.93 | -15502.93 | -11.93%
342766 | 342766 | Black River Communications and Security | 121564.08 | 6641 | 139320 | Closeout | 100 | 139320 | 128205.08 | 11114.92 | 7.978% | 95 | 132354 | 128205.08 | 4148.92 | 2.978%
342770 | 342770 | KCCF HVAC Air Grilles Ph 2 | 444057.24 | 4388 | 647219 | Construction | 90 | 582497.1 | 448445.24 | 134051.86 | 20.71% | 60 | 388331.4 | 448445.24 | -60113.84 | -9.288%
343212 | 343212 | RJC-Courts Floor Finishes | 50635.66 | 0 | 434690 | Final Design | 30 | 130407 | 50635.66 | 79771.34 | 18.35% | 15 | 65203.5 | 50635.66 | 14567.84 | 3.351%
343221 | 343221 | MRJC Central Plant Boiler Controls | 206256.17 | 0 | 187065 | Construction | 90 | 168358.5 | 206256.17 | -37897.67 | -20.26% | 60 | 112239 | 206256.17 | -94017.17 | -50.26%
343222 | 343222 | MRJC-Det Communications & Security | 68741.51 | 13051.105 | 2070996 | Preliminary Design | 30 | 621298.8 | 81792.615 | 539506.185 | 26.05% | 15 | 310649.4 | 81792.615 | 228856.785 | 11.05%
343230 | 343230 | Yesler Building Flooring | 439923.48 | 0 | 439921 | Final Design | 30 | 131976.3 | 439923.48 | -307947.18 | -70% | 15 | 65988.15 | 439923.48 | -373935.33 | -85%
343246 | 343246 | Youth-Spruce-Communication & Security | 450380.59 | 193099.575 | 3161337 | Final Design | 30 | 948401.1 | 643480.165 | 304920.935 | 9.645% | 15 | 474200.55 | 643480.165 | -169279.615 | -5.355%
343249 | 343249 | KCCF Window Washing Equip | 69116.19 | 23597 | 260513 | Final Design | 30 | 78153.9 | 92713.19 | -14559.29 | -5.589% | 15 | 39076.95 | 92713.19 | -53636.24 | -20.59%
343250 | 343250 | RJC-Detention Electrical Service and Distribution | 16283.74 | 3950 | 48027 | Final Design | 30 | 14408.1 | 20233.74 | -5825.64 | -12.13% | 15 | 7204.05 | 20233.74 | -13029.69 | -27.13%
343261 | 343261 | Admin Bldg Pedestrian Paving | 65680.82 | 59930.64 | 167501 | Implementation | 90 | 150750.9 | 125611.46 | 25139.44 | 15.01% | 60 | 100500.6 | 125611.46 | -25110.86 | -14.99%
343267 | 343267 | PH Eastgate Fire Alarm Systems | 10296.82 | 10114 | 227400 | Final Design | 30 | 68220 | 20410.82 | 47809.18 | 21.02% | 15 | 34110 | 20410.82 | 13699.18 | 6.024%
343269 | 343269 | PH Federal Way Controls and Instrumentation | 108275.53 | 19097.58 | 156600 | Construction | 90 | 140940 | 127373.11 | 13566.89 | 8.663% | 60 | 93960 | 127373.11 | -33413.11 | -21.34%
343278 | 343278 | PH White Center Distribution Systems | 14177.81 | 0 | 14178 | Preliminary Design | 30 | 4253.4 | 14177.81 | -9924.41 | -70% | 15 | 2126.7 | 14177.81 | -12051.11 | -85%
343285 | 343285 | Precinct 3 - Maple Valley-Elect. Serv. & Distrib. | 96536.16 | 18205.76 | 96536 | Closeout | 100 | 96536 | 114741.92 | -18205.92 | -18.86% | 95 | 91709.2 | 114741.92 | -23032.72 | -23.86%
344500 | 344500 | Precinct 4 Testing & Balancing | 1407.07 | 0 | 71789 | Final Design | 30 | 21536.7 | 1407.07 | 20129.63 | 28.04% | 15 | 10768.35 | 1407.07 | 9361.28 | 13.04%
344505 | 344505 | Records Warehouse Fire Alarm Systems | 13555.18 | 10714 | 155000 | Final Design | 30 | 46500 | 24269.18 | 22230.82 | 14.34% | 15 | 23250 | 24269.18 | -1019.18 | -0.6575%
344513 | 344513 | RJC-Courts Wall Finishes | 2224.69 | 0 | 50000 | Planning | 30 | 15000 | 2224.69 | 12775.31 | 25.55% | 15 | 7500 | 2224.69 | 5275.31 | 10.55%
344515 | 344515 | RJC-Detention BTU Meter | 23474.86 | 0 | 31991 | Closeout | 100 | 31991 | 23474.86 | 8516.14 | 26.62% | 95 | 30391.45 | 23474.86 | 6916.59 | 21.62%
344517 | 344517 | RJC-Detention Floor Finishes | 42791.01 | 0 | 126991 | Closeout | 100 | 126991 | 42791.01 | 84199.99 | 66.3% | 95 | 120641.45 | 42791.01 | 77850.44 | 61.3%
344518 | 344518 | MRJC Phase 3 ESCO | 305176.62 | 63953.78 | 384341 | Construction | 90 | 345906.9 | 369130.4 | -23223.5 | -6.042% | 60 | 230604.6 | 369130.4 | -138525.8 | -36.04%
344528 | 344528 | Youth-Spruce Elect Serv & Distrb | 19050.67 | 0 | 22292 | Implementation | 90 | 20062.8 | 19050.67 | 1012.13 | 4.54% | 60 | 13375.2 | 19050.67 | -5675.47 | -25.46%
344534 | 344534 | Redmond D. C. - New paint, flooring phase 2 | 113323.69 | 0 | 147624 | Construction | 90 | 132861.6 | 113323.69 | 19537.91 | 13.23% | 60 | 88574.4 | 113323.69 | -24749.29 | -16.77%
344544 | 344544 | KCCF Exterior Wall Finishes | 65939.7 | 46131.75 | 574713 | Final Design | 30 | 172413.9 | 112071.45 | 60342.45 | 10.5% | 15 | 86206.95 | 112071.45 | -25864.5 | -4.5%
344545 | 344545 | KCCF Site Lighting | 93998.68 | 0 | 94000 | Construction | 90 | 84600 | 93998.68 | -9398.68 | -9.999% | 60 | 56400 | 93998.68 | -37598.68 | -40%
344578 | 344578 | RJC-Deterntion Other Electrical Systems | 15782.63 | 6000.23 | 200000 | Final Design | 30 | 60000 | 21782.86 | 38217.14 | 19.11% | 15 | 30000 | 21782.86 | 8217.14 | 4.109%
344579 | 344579 | RJC Detent Elec Srv & Distrib - Phase 1 | 22181.27 | 4000 | 72000 | Final Design | 30 | 21600 | 26181.27 | -4581.27 | -6.363% | 15 | 10800 | 26181.27 | -15381.27 | -21.36%
344581 | 344581 | Ravensdale Range Ballistic Improvements | 104288.51 | 25659.89 | 417321 | Final Design | 30 | 125196.3 | 129948.4 | -4752.1 | -1.139% | 15 | 62598.15 | 129948.4 | -67350.25 | -16.14%
344583 | 344583 | Yesler Building Domestic Water Distribution | 94637.2 | 0 | 100000 | Closeout | 100 | 100000 | 94637.2 | 5362.8 | 5.363% | 95 | 95000 | 94637.2 | 362.8 | 0.3628%
344593 | 344593 | Youth - Spruce Distribution Systems | 142906.72 | 119804.825 | 381609 | Construction | 90 | 343448.1 | 262711.545 | 80736.555 | 21.16% | 60 | 228965.4 | 262711.545 | -33746.145 | -8.843%
344596 | 344596 | RJC-Courts other Equip | 22465.47 | 4581.5 | 78210 | final Design | 30 | 23463 | 27046.97 | -3583.97 | -4.582% | 15 | 11731.5 | 27046.97 | -15315.47 | -19.58%
344602 | 344602 | KCCF Interior Doors | 75786.98 | 25680 | 687510 | Construction | 90 | 618759 | 101466.98 | 517292.02 | 75.24% | 60 | 412506 | 101466.98 | 311039.02 | 45.24%
344623 | 344623 | KCCF Electrical Service and Distrib | 4650.3 | 7950 | 78000 | Planning | 30 | 23400 | 12600.3 | 10799.7 | 13.85% | 15 | 11700 | 12600.3 | -900.3 | -1.154%
344624 | 344624 | KCCF Site Development (sidewalks) | 80231.46 | 38371.035 | 154000 | Construction | 90 | 138600 | 118602.495 | 19997.505 | 12.99% | 60 | 92400 | 118602.495 | -26202.495 | -17.01%
344662 | 344662 | MRJC Central Plant Chillers Upgrade | 447616.74 | 0 | 587497 | Construction | 90 | 528747.3 | 447616.74 | 81130.56 | 13.81% | 60 | 352498.2 | 447616.74 | -95118.54 | -16.19%
344682 | 344682 | Youth - Spruce Interior Doors (Detention Hardware) | 11521.98 | 8346.5 | 30000 | Final Design | 30 | 9000 | 19868.48 | -10868.48 | -36.23% | 15 | 4500 | 19868.48 | -15368.48 | -51.23%
344686 | 344686 | Youth - Spruce Fire Alarm Systems | 109119.5 | 16611.62 | 203254 | Construction | 90 | 182928.6 | 125731.12 | 57197.48 | 28.14% | 60 | 121952.4 | 125731.12 | -3778.72 | -1.859%
344696 | 344696 | Orcas Parking lot Overlay | 122311.5 | 3208 | 533589 | Final Design | 30 | 160076.7 | 125519.5 | 34557.2 | 6.476% | 15 | 80038.35 | 125519.5 | -45481.15 | -8.524%
344697 | 344697 | Renton P.H. Site Lights | 34886.79 | 0 | 55000 | Closeout | 100 | 55000 | 34886.79 | 20113.21 | 36.57% | 95 | 52250 | 34886.79 | 17363.21 | 31.57%
344698 | 344698 | White Center P.H. Site Lights | 22815.37 | 0 | 22815 | Closeout | 100 | 22815 | 22815.37 | -0.37 | -0.001622% | 95 | 21674.25 | 22815.37 | -1141.12 | -5.002%
344699 | 344699 | RCECC Distribution System | 46521.81 | 0 | 49828 | Closeout | 100 | 49828 | 46521.81 | 3306.19 | 6.635% | 95 | 47336.6 | 46521.81 | 814.79 | 1.635%
344702 | 344702 | Countywide Building Survey | 342318.62 | 128480.5 | 809415 | Planning | 30 | 242824.5 | 470799.12 | -227974.62 | -28.17% | 15 | 121412.25 | 470799.12 | -349386.87 | -43.17%
344704 | 344704 | Countywide Budget Preparation | 310125.02 | 10640.92 | 300311 | Planning | 30 | 90093.3 | 320765.94 | -230672.64 | -76.81% | 15 | 45046.65 | 320765.94 | -275719.29 | -91.81%
344709 | 344709 | MRJC Phase 2 ESCO | 158223.59 | 92499.395 | 189445 | Construction | 90 | 170500.5 | 250722.985 | -80222.485 | -42.35% | 60 | 113667 | 250722.985 | -137055.985 | -72.35%
344730 | 344730 | DC Issaquah Terminal and Package Units | 342781.65 | 1058692.875 | 1516282 | Construction | 90 | 1364653.8 | 1401474.525 | -36820.725 | -2.428% | 60 | 909769.2 | 1401474.525 | -491705.325 | -32.43%
344734 | 344734 | KCCF Floor Finishes | 46435.86 | 0 | 134756 | Closeout | 100 | 134756 | 46435.86 | 88320.14 | 65.54% | 95 | 128018.2 | 46435.86 | 81582.34 | 60.54%
344737 | 737M01 | PH NDMSC Exterior Structural Repairs Final Phase Design | 29482.27 | 62147 | 100000 | Planning | 30 | 30000 | 91629.27 | -61629.27 | -61.63% | 15 | 15000 | 91629.27 | -76629.27 | -76.63%
344749 | 344749 | MRJC Deten. Bldg. Infirmary Exhaust Upgrade | 61057.09 | 0 | 85817 | Construction | 90 | 77235.3 | 61057.09 | 16178.21 | 18.85% | 60 | 51490.2 | 61057.09 | -9566.89 | -11.15%
344752 | 344752 | Yesler Building Sprinklers | 13511.69 | 0 | 52575 | Preliminary Design | 30 | 15772.5 | 13511.69 | 2260.81 | 4.3% | 15 | 7886.25 | 13511.69 | -5625.44 | -10.7%
344757 | 344757 | MRJC Phase 3 ESCO | 188361.64 | 103464.795 | 163165 | Construction | 90 | 146848.5 | 291826.435 | -144977.935 | -88.85% | 60 | 97899 | 291826.435 | -193927.435 | -118.9%
344758 | 344758 | Black River Backflow Preventer | 11236.98 | 9715 | 59140 | Final Design | 30 | 17742 | 20951.98 | -3209.98 | -5.428% | 15 | 8871 | 20951.98 | -12080.98 | -20.43%
344763 | 344763 | Chinook Floor Finishes (elev. & 1st Fl. Public) | 17760.61 | 0 | 86917 | Closeout | 100 | 86917 | 17760.61 | 69156.39 | 79.57% | 95 | 82571.15 | 17760.61 | 64810.54 | 74.57%
344765 | 344765 | Courthouse Elevator Doors | 10464.59 | 0 | 16760 | Closeout | 100 | 16760 | 10464.59 | 6295.41 | 37.56% | 95 | 15922 | 10464.59 | 5457.41 | 32.56%
344766 | 344766 | Courthouse Communications & Security (APC, Duress) | 11289.7 | 13643.625 | 890000 | Planning | 30 | 267000 | 24933.325 | 242066.675 | 27.2% | 15 | 133500 | 24933.325 | 108566.675 | 12.2%
344778 | 344778 | Kent Animal Shelter Misc Repairs | 13934.52 | 0 | 72335 | Closeout | 100 | 72335 | 13934.52 | 58400.48 | 80.74% | 95 | 68718.25 | 13934.52 | 54783.73 | 75.74%
344781 | 344781 | Orcas Ped Paving (Sidewalk) | 3996.14 | 0 | 79475 | Final Design | 30 | 23842.5 | 3996.14 | 19846.36 | 24.97% | 15 | 11921.25 | 3996.14 | 7925.11 | 9.972%
344801 | 344801 | RJC-Courts Domestic Water Distribution | 17043.42 | 29803.2 | 314515 | Final Design | 30 | 94354.5 | 46846.62 | 47507.88 | 15.11% | 15 | 47177.25 | 46846.62 | 330.63 | 0.1051%
344803 | 344803 | RJC-Courts Other Elect (Gen cooling piping) | 34256.18 | 0 | 80000 | Closeout | 100 | 80000 | 34256.18 | 45743.82 | 57.18% | 95 | 76000 | 34256.18 | 41743.82 | 52.18%
344804 | 344804 | RJC-Detention Light'g (rooftop det'n lighting) | 35465.93 | 20100 | 718265 | Final Design | 30 | 215479.5 | 55565.93 | 159913.57 | 22.26% | 15 | 107739.75 | 55565.93 | 52173.82 | 7.264%
344806 | 344806 | Yesler Building Air Handler replace coil condensate | 22275.95 | 40710.395 | 107068 | Closeout | 100 | 107068 | 62986.345 | 44081.655 | 41.17% | 95 | 101714.6 | 62986.345 | 38728.255 | 36.17%
344807 | 344807 | Youth -Spruce Distrib Systems (AHU 2) | 21980.04 | 0 | 22000 | Closeout | 100 | 22000 | 21980.04 | 19.96 | 0.09073% | 95 | 20900 | 21980.04 | -1080.04 | -4.909%
344808 | 344808 | DC Shoreline Roof coverings (gutter) | 20712.19 | 0 | 69269 | Closeout | 100 | 69269 | 20712.19 | 48556.81 | 70.1% | 95 | 65805.55 | 20712.19 | 45093.36 | 65.1%
344810 | 344810 | Youth-Spruce Ext Wall finishes | 18633.36 | 21294.6 | 306834 | Final Design | 30 | 92050.2 | 39927.96 | 52122.24 | 16.99% | 15 | 46025.1 | 39927.96 | 6097.14 | 1.987%
344814 | 344814 | KCCH Work Release HVAC (ESCO) | 36096.7 | 42577.5 | 1349700 | Preliminary Design | 30 | 404910 | 78674.2 | 326235.8 | 24.17% | 15 | 202455 | 78674.2 | 123780.8 | 9.171%
|  |  | 16670939.54 | 7734019.235 | 49932394 |  |  | 32533647.8 | 24404958.775 | 8128689.025 | 16.28% |  | 21447857.95 | 24404958.775 | -2957100.825 | -5.922%
| * Notes: | Model (a) - target at end of phase:
Planning, Design = 30%
Construction = 90%
Closeout = 100%
Model (b) - target at middle of phase:
Design = 15% (mid-point of design 30%)
Construction = 60% (30% + mid-point of construction 60%)
Closeout =95% (90% plus mid-point of closeout 10%)