## STAFF REPORT

| Agenda Item: | 5 | Name: | Greg Doss |
| --- | --- | --- | --- |
| Proposed No.: | 2015-B0195 | Date: | October 13, 2015 |

SUBJECT

This briefing provides an update on the status of King County Courthouse Revitalization Project.

SUMMARY

The Auditor's August 25, 2015 Management Letter with respect to the King County Courthouse Revitalization project identified a number of issues leading to recommendations to suspend the Facility Management Division's current procurement process and broaden the scope of alternatives being considered (see Attachment 1).

On September 14, 2015, the County Council approved an amendment to the 2015 budget omnibus placing a proviso on the Facilities and Management Division's (FMD's) operating budget.   The proviso restricts expenditure of $720,000 of FMD's operating budget, pending Council approval of a scoping report by March 1, 2016 on the county's future operational and space needs in the downtown Seattle campus as a whole.  The Executive is also directed to update the Real Property Asset Management Plan (RAMP) by March 1, 2016, as mandated by the King County Code.  Executive staff have indicated that FMD will produce the Scoping Report required by the proviso.  They have submitted the following statement in regards to the RAMP:

“With respect to the proviso requesting the update of the RAMP by March 1, 2016, the scope of the update will prioritize updating the aspects of the RAMP that support the development of the downtown civic campus plan, should that effort be approved and funded; status of projects highlighted in the 2014 RAMP; and new developments in terms of near term space needs that have emerged since the last update.  Due to schedule and resources limitations, the 2016 update will not be comprehensive in scope.  As with the civic campus scoping report, we will consult with the County Auditor’s staff regarding what elements of the RAMP they would prioritize.”

Executive staff also recommend that FMD defer work on the proviso that was included in the 2017/2018 Adopted Budget and focus the Department’s initial efforts on the Scoping Report required in the Omnibus Supplemental proviso (described above).  Depending on the outcome of that work, and Council feedback, Executive staff may then redirect their efforts to the other proviso.

BACKGROUND

The Executive's Proposed 2015/2016 Biennial Budget included $1,226,750 for CIP project 1124472 – Courthouse System Revitalization.  The project was intended to address the aging Courthouse infrastructure systems by beginning the process of identifying funding and phasing alternatives, as well as preparing as-built structural documentation.  According to the Executive, this is a critical first step in preparation for developing a proposal for a comprehensive project which includes mechanical, electrical, plumbing and window-related work.  According to the Auditor's Management Letter, FMD's rough order of magnitude cost estimate for project completion translates to a range of $75 to $300 million.

Council Proviso on the Capital Project

The Council included the following proviso on this project in the adopted budget, calling for a report on the Courthouse building systems, prior to deciding how to approach and fund the project:

Of the appropriation for capital project 1124472, courthouse system revitalization, $500,000 shall not be expended or encumbered until the executive transmits a report on the King County Courthouse building systems and a motion that approves the report and the motion is passed by the council.  The motion shall reference the subject matter, the proviso's ordinance, ordinance section and proviso number in both the title and body of the motion.

The report shall include, but not be limited to:

A.  A building alternative analysis;

B.  A list of possible projects, reported by system or task;

C.  The estimated costs for each possible project, reported by system or task;

D.  A risk assessment and any risk mitigation plans for possible projects;

E.  A prioritization for possible projects;

F.  The estimated timelines for possible projects;

G.  The status of locating as-built structural documentation;

H.  A discussion of the historical significance of the building and how the historical designation could affect the project; and

I.  Any work done to investigate or access state, federal or other funding sources in support of the project.

The executive must file the report and motion required by this proviso by April 1, 2016, in the form of a paper original and an electronic copy with the clerk of the council, who shall retain the original and provide an electronic copy to all councilmembers, the council chief of staff, the policy staff director and the lead staff for the budget and fiscal management committee, or its successor.

The King County Council adopted Ordinance 16764 on March 1, 2010 which charged the Joint Advisory Group (JAG), in consultation with the King County Auditor’s capital projects oversight program, with determining which capital projects should be considered ‘high-risk’.  The Courthouse Revitalization Project received the highest capital project risk score in 2015 (twice the average of the other 18 projects considered), and Council requested that the project be added to the Auditor's work program.

King County Auditor's Management Letter

The Auditor published a Management Letter on August 25, 1015, evaluating actions taken on the project to date and providing recommendations about broader space planning issues for King County facilities.

The report from the Auditor's Office summarizes the issues as follows:

- The County faces a critical decision about whether to spend over $100 million either to replace old and failing systems or to pursue an alternative that might better meet its needs. The Courthouse Revitalization Project could commit the county to one option without first thoroughly analyzing possible alternatives.

- FMD's planned alternatives analysis (required by the County Council's proviso) would not take into account the future operational needs of the county or the needs of the downtown campus as a whole, both of which the auditor deems necessary for a thorough alternatives analysis.

- The County needs a plan to manage risks while it is selecting and implementing an alternative, since courthouse systems failures could impact the ability of the county to conduct business.

The Auditor's Office has made the following recommendations:

Recommendation 1:  Facilities Management Division should suspend its procurement process to obtain a project manager and seek assistance as needed to manage funded project activities.

Recommendation 2:  The County Executive should determine the future space needs of the downtown campus and update the Real Property Asset Management Plan as mandated by King County Code 20.12.100.

Recommendation 3:  The County Executive should conduct and report on a thorough alternatives analysis that compares the status quo of maintaining the current courthouse to other viable alternatives based on the future needs of the downtown campus, the updated Real Property Asset Management Plan, and input from stakeholders.

Recommendation 4:  Facilities Management Division should conduct and document risk management planning to maintain county services in the courthouse for the number of years it will take to thoroughly explore alternatives and complete the systems revitalization or other alternative project.

Recommendation 5:  Facilities Management Division should work with courthouse tenants and other stakeholders to understand, develop, and document action plans to mitigate potential impacts to operations in the event of failure of building systems.

Proviso on FMD's Operating Budget

On September 14, 2015 the County Council approved an amendment to the 2015 budget omnibus, sponsored by Councilmembers von Reichbauer and Dembowski, placing the following proviso on the Facilities and Management Division's operating budget.   The proviso restricts expenditure of $720,000 of FMD's operating budget, pending Council approval of the Executive's transmittal of a scoping report by March 1, 2016 on the county's future operational and space needs in the downtown Seattle campus as a whole.  The Executive is also directed to update the Real Property Asset Management Plan (RAMP) by March 1, 2016, as mandated by the King County Code.

Of this appropriation, $720,000 shall not be expended or encumbered until the executive transmits a scoping report on the county's future operational and space needs in the downtown Seattle campus as a whole and updates the Real Property Asset Management Plan as mandated by K.C.C. 20.12.100 and a motion that approves the report and the motion is passed by the council.  The motion shall reference the subject matter, the ordinance number, the ordinance section number and the proviso number in both the title and body of the motion.

The scoping report shall include, but not be limited to:

A.  A plan for identification of the tenants' future operational and

space needs within King County's downtown Seattle civic campus through 2025, including, but not limited to, total useable square feet, a list of current King County operations, staffing and space utilized at each location, current unoccupied, useable square feet at each location, and potential funding alternatives, including public/private partnerships.  The civic campus shall include, but is not limited to, the following properties and the tenants thereof:

1. The King County Courthouse;

2.  The Chinook building;

3.  The King County Administration building;

4.  Vacant land adjacent to the Goat Hill parking garage;

5.  The Yesler building; and

6.  420 Fourth Avenue;

The executive must file the motion required by this proviso by March 1, 2016, in the form of a paper original and an electronic copy with the clerk of the council, who shall retain the original and provide an electronic copy to all councilmembers, the council chief of staff, the policy staff director and the lead staff for the government accountability and oversight committee, or its successor.

Executive's Next Steps

Executive staff testified at the September 14, 2015 meeting that they intend to use funds from the courthouse revitalization capital project to produce the requested scoping report and RAMP update. They noted that the scoping report would include a "high level" alternatives analysis for the county's downtown Seattle properties and operations.  They also committed to postpone action on the request for proposal (RFP) associated with the courthouse project, while they produced the scoping report.

They have submitted the following statement in regards to the RAMP:

“With respect to the proviso requesting the update of the RAMP by March 1, 2016, the scope of the update will prioritize updating the aspects of the RAMP that support the development of the downtown civic campus plan, should that effort be approved and funded; status of projects highlighted in the 2014 RAMP; and new developments in terms of near term space needs that have emerged since the last update.  Due to schedule and resources limitations, the 2016 update will not be comprehensive in scope.  As with the civic campus scoping report, we will consult with the County Auditor’s staff regarding what elements of the RAMP they would prioritize.”

Executive staff have recommend that FMD should focus its initial efforts on the proviso that was included in the recent Omnibus Supplemental Ordinance (discussed above).  This proviso calls for a Scoping Report on the County’s future space needs in the downtown Seattle campus and for an update to the RAMP.  Executive staff have indicated that FMD is developing an approach to this work and will review it with Council staff and the County Auditor.  The Department expects to complete this work by the due date of March 1, 2016.

Executive staff also recommend that FMD defer work on the proviso that was included in the 2017/2018 Adopted Budget.  This proviso calls for a report on building alternatives, risk assessment, as-built documentation for the Courthouse, and a variety of other topics.  They indicate that some of this work will be covered in the new proviso.  Other portions are exclusive to the Courthouse revitalization project and Executive staff believe that it would be inappropriate for PSB or FMD to undertake work on the original proviso until after the March 1 report is submitted and the Council provides additional direction.  Executive staff added that it will not be possible to complete this work by April 1 (the due date in the original proviso) if efforts are focused on the new proviso.

ATTACHMENTS

- King County Auditor's Office Management Letter, dated August 25, 2015

INVITED

- Anthony Wright, FMD Director

- Elissa Benson, FMD Deputy Director