2022 Annual King County Comprehensive Plan Update, Skyway-West Hill Subarea Plan, North Highline Subarea Plan

King County Council committee review and adoption schedule

As of June 30, 2022 – subject to change

| Date | Event |
| --- | --- |
| March 22 9:30am | Local Services and Land Use Committee Briefing |
| March 31 | Executive’s Transmittal of 2022 King County Comprehensive Plan Update |
| July 11 | Substantive direction needed on Striking Amendment |
| July 15 | Striking Amendment released |
| July 18 | Line amendment direction due |
| July 22 | Public Line Amendments released |
| July 26 9:30am | Local Services and Land Use Committee Review and consideration of striking and line amendments Vote on Committee recommendation Opportunity for Public Comment |
| August 16 | Councilmember Deadline for amendment concepts for public hearing notice |
| July 26 to November 21 | SEPA Process by Executive/Council staff Public Hearing Notice by Council staff Budget Standdown September 19 to ~Thanksgiving |
| October 7 | Substantive direction needed on Striking Amendment |
| November 1 | Striking Amendment distributed to Councilmembers |
| November 4 | Line amendment direction due |
| November 15 | Public Amendments released |
| November 22 1:00pm | Public Hearing at full Council Opportunity for Public Testimony |
| December 6 1:00pm | Possible vote at full Council Consideration of amendments Vote on final adoption of proposed 2022 King County Comprehensive Plan Update |
| December 13 1:00pm | Back up vote if 1-week courtesy delay |