##### Metropolitan King County Council

Capital Budget Committee

| AGENDA ITEM No.: | 6, 7 |  | DATE: | September 5, 2007 |
| --- | --- | --- | --- | --- |
| Ordinance No.: | 2007- 0443 2007-0444 |  | PREPARED BY: | Jennifer Giambattista Patrick Hamacher Mark Melroy |

STAFF REPORT

SUMMARY:

The County’s centralized data center is currently located in leased space in the Seattle Municipal Tower.  The County is currently exercising a one year, month-to-month, extension option on a lease in the Municipal Tower. The lease expired in March of 2007.  As of March of 2008 the County no longer has space secured for its centralized data center, which supports several critical county functions.

The Executive has recently transmitted legislation that would move the data center to “Building Five” of the Sabey Center, which is located at 3355 South 120th Place, Seattle Washington.

Proposed Ordinance 2007-0443 would designate Building Five as the county’s enterprise data center location and would authorize the Executive to enter into a thirty-year lease for 11,474 square feet in Building Five.  Terms of the lease are generally described by a “letter of intent”, which is Attachment A to the proposed ordinance.

Proposed Ordinance 2007-0444 is a supplemental appropriation request that would authorize the Executive to spend up to $17.1 million in 2007 to pursue relocation of the data center from the Seattle Municipal Tower into Building Five of the Sabey Center.  This request would fund capital investment activities including data center infrastructure improvements, relocation planning, and a project contingency reserve.

These proposed ordinances are being heard by the committee for the first time today.    This legislation was recently transmitted along with several other major capital budget legislative items.  Although executive staff have provided preliminary information in response to issues raised in today’s report, this information was not provided in time to be included in the staff report.  Today’s report and presentation are intended to provide committee members an overview of the issues and to generate questions.  Staff intend to provide more detailed analysis and responses to questions from the committee at the September 19th meeting.

BACKGROUND:

The County’s centralized data center is currently housed in leased space in the Seattle Municipal Tower.  This lease, originally executed in March of 2004 was scheduled to run through March of 2009 and contained an “early out” clause that would allow the County to end the lease in 2007 or 2008 and pay associated penalties.  The “early out” option was exercised according to the lease terms 24 months prior to the revised expiration date of March, 2007.  Revisions to the original lease also included terms to allow the County to extend the lease on a month-to-month basis for up to one year at a rate of 150% of the rate charged prior to March 2007.  The County is currently paying the increased rate and does not have replacement space secured beyond the March 2008 final lease expiration date.

Replacement space for the County’s data center has been the subject of significant discussions by the Council and the Executive in recent years.  As discussed in the transmittal letter for the current legislation, the first major proposal for new data center space came when the Executive recommended acquisition of a building located at 1130 Rainier Avenue in Seattle in June of 2005.  This 3-story 60,000 square foot building was envisioned to serve the needs of a consolidated elections facility as well as offering 16,000 square feet of space and infrastructure to serve as a data center.  The 1130 Rainier building, as then presented, was not large enough to house consolidated elections operations including warehousing facilities without significant additional construction and investment.  The Council considered and rejected the 1130 Rainier proposal based on the facility’s inability to meet the goals of elections consolidation as outlined in by the Citizen’s Elections Oversight Committee (CEOC).

The transmittal letter made cost comparisons between the Sabey proposal and the 1130 Rainier proposal that were later featured in a local news article.  The comparisons between the two options were not based on similar factors.  Most notably, the Sabey proposal included relocation costs of $3.7 million and contingency costs of $2.8 million whereas estimates for the 1130 Rainier proposal, included only $500K in total contingency and no of the relocation expenses.  This factor alone accounts for a six million dollar imbalance in a comparison of the two options.

The most recent legislative proposal would allow the County to move ahead with the Sabey center as the selected site for the data center space.  Also included in the proposal is cost information from another potential lease site at Fisher Plaza in downtown Seattle.  Executive staff had been negotiating with representatives from both of these facilities however, when cost information was finalized, the Sabey proposal was determined to be more advantageous to the County.  Council staff have analyzed the cost information and preliminarily concur with this conclusion.  As such, this staff report will focus on an analysis of the Sabey center proposal.

ANALYSIS:

SCOPE

The proposed relocation of the existing data center at the Seattle Municipal Tower to Building Five of the Sabey Center involves a large scope of work. The scope of the project includes making extensive improvements to the leased space in order to create an infrastructure that meets the technical requirements for housing the county’s data center and purchasing new equipment. The proposed lease comprises a total of 11,474 square feet of space in Building Five of the Sabey Center.  7745 square feet of this space would be dedicated to data center operations and the remaining 3,729 square feet would be used for office and administrative purposes.  The estimates for capital contributions to this space are approximately $7 million, or $900 per square foot.

The project scope also includes installing two long, high capacity fiber optic runs (almost 20 miles) to the leased space and connecting the new space with various points all the way from the airport to selected sites downtown. The second run serves as a back-up run. While the cost estimates for the county assume installing its own fiber optic network (KCWAN) rather than using a commercial vendor, OMB notes that a final analysis on whether to install KCWAN versus a commercial vendor has not been completed. OMB reports that such an analysis will be completed during the scope of this project.

The project will also involve hiring a relocation consultant and the actual physical move. The move will involve transferring the existing equipment housed in the Seattle Municipal Tower (SMT) to the Sabey Center space. The servers and associated equipment for Public Health will also be moved to the Sabey space. (Public Health has been temporarily renting space since its move to the new county office building.) The project scope does not include moving other executive branch departments or separately elected agencies. Under this proposal, the county will have the first right of refusal on an additional 3,729 feet of space.  However, an analysis has not been done to determine whether the additional space is sufficient to meet the county’s overall needs for data center space. OMB notes that such an analysis on server consolidation is a separate task, not part of the current relocation proposal and can not be done until after 2008.

In order to ensure minimal disruption to IT services, the project proposes to run dual equipment during the relocation process and temporarily lease fiber lines while the permanent fiber network is established.

Committee staff have identified several issues for further analysis related to the scope of this project.  Those issues are highlighted here by topic:

Tenant Improvements

- What is included in tenant improvements and infrastructure work that is proposed for the leased space?

Fiber Optic Network

  - The project involves installing an extensive amount of high capacity fiber in order to connect the data center with county buildings downtown and the airport. Staff will review the executive's analysis completed thus far on whether it is more cost effective for the county to build (using contractors) its own fiber lines  or rely on leasing fiber lines from a commercial vendor already servicing the Sabey building. What criteria will be used to make a final decision? Should a final decision be approved by Council?

Equipment

- What is the purpose of the new equipment to be installed in the data center related to the fiber option network?

Relocation Consultant

- What is the scope of work for the relocation consultant?

Impact on IT Reorganization and Server Consolidation

- The proposed plan’s affect on the existing IT Reorganization plans related to consolidating and/or co-locating the county’s servers will need further analysis.

OIRM Staffing

- Historically, it has been difficult to fill technology positions at the county. Staff will be analyzing whether the staffing plan will allow for OIRM to maintain existing operations and support this project.

SCHEDULE

The following schedule milestones have been projected by executive staff.

- Sept 2007: Hire a consultant with expertise in relocation planning and relocation     physical move

- Sept 2007-June 2008: Relocation planning and move prep

- June 2008- November 2008: Physical Move(s)

It is worth noting that even under the most optimistic projections, the move from the Seattle Municipal Tower facility will not fully occur until well after the existing lease extension expires in March of 2008.

BUDGET

Proposed Ordinance 2007-0444 would appropriate $17,070,572 to the Building Repair and Replacement Fund (Fund #3951). The 2007 adopted budget for the Building Repair and Replacement Fund is $5,344,953. The impact on the appropriation from this ordinance is summarized in Table 1.

Table 1: BR&R Fund Expenditures

| Building Repair & Replacement Fund |
| --- |
| 2007 Appropriation | PO 2007-0444 | Spring 2008 Estimate | Total |
| $ 5,344,953 | $ 17,070,572 | $ 2,964,586 | $25,380,111 |
| Total for Data Center | $20,035,158 |

Council staff has made an initial inquiry as to the elements and backup information that were used in developing the request of $17,070,572. We have received initial information on a category basis, but have not yet had time to analyze the detail associated with the appropriation request. An initial breakdown of both the funding request as well as the proposed spring 2008 supplemental is included as Table 2.

Table 2: Funding Request Breakdown

| Type of Expense | 2007-0444 | 2008 Est. |
| --- | --- | --- |
| Tenant Improvements (Per Lease) | $7,000,000 |  |
| Core Infrastructure | 774,000 |  |
| Network Equipment | 2,352,477 |  |
| Telephone Systems | 206,019 |  |
| Wireless Connectivity | 6,210 |  |
| Data Center Operations | 31,309 |  |
| I-Net Equipment | 117,811 |  |
| Fiber Costs | 3,119,293 |  |
| Systems Engineering |  | 647,955 |
| Relocation Consultant | 1,000,000 | 500,000 |
| Physical Move Costs |  | 1,108,824 |
| FMD Staffing Costs | 348,000 |  |
| Auxiliary Servers - Fortress | 331,098 |  |
| OIRM Staffing Costs | 309,355 | 707,807 |
| Project Contingency | 1,400,000 |  |
| Sazan Consultant Costs | 75,000 |  |
| Total | $17,070,572 | $2,964,586 |

- Project Contingency Funds

Within the different projects listed in Table 2 contingency funds are embedded in the project budget. Additionally, there is $1.4 million in project scope contingency included in the appropriation request. This brings total contingency contained within the project to $2,835,388 or 20% of the total project cost. Council staff will continue to evaluate how the project contingency was developed – i.e. whether this was a simple budget percentage calculation or if it was based upon project risk.  As the tenant improvement costs (construction costs) are covered by the lease and provided by the landlord, this project appears to have little construction risk, an area where the County has experience issues with cost escalation in the recent years. The planned work also involves a build-out of empty space, rather than remodeling an existing facility.  Considering a lower risk of construction escalation, Councilmembers may want to consider reductions in the project contingency.

- Relocation Costs

The current appropriation request includes over $1.5 million for planning, project management and move costs. Factoring in current estimates for the spring 2008 supplemental, total move, planning and project management costs exceed $3.7 million.

Considering that the total project cost is currently estimated at $20 million, relocation costs ($3.7 million) and contingency costs ($2.8 million) exceed 30% of the total project costs. Council staff will further analyze the methodology for estimating these moves costs, consulting costs and staffing costs in preparation for the next committee meeting.

In addition council staff will evaluate how the proposed $1.5 million of expenditures for the “Relocation Consultant” was calculated or determined. Essentially this proposal includes $1.5 million to develop a plan for moving the IT services to the new data center. However, our initial reviews of the costs included with this estimate indicate that move costs are also included. Council staff are interested in being able to provide Councilmembers with additional information as to what these funds will be used for.

- Fisher Plaza Costs

In beginning to review the detailed budget estimates for the project, it appears that approximately $138,000 was spent on examining the Fisher Plaza opportunity. It is unclear whether this request belongs in this appropriation. Council staff will continue to examine this request.

- Phase I Capital Costs Versus Future Expansion

As noted previously, the Council is being asked to consider leasing a total of 11,474 square feet of space in Building Five of the Sabey Center.  7,745 square feet of this space would be dedicated to data center operations and the remaining 3,729 square feet would be used for office and administrative purposes. The capital costs to prepare the 11,474 SF of space for occupancy (tenant improvements) are currently estimated to be $7 million, or approximately $900 per square foot.  The estimated capital costs associated with the potential expansion space of 3,114 square feet are $4 million, or approximately $1285 per square foot.  Executive staff have indicated that a significant amount of the difference between these numbers is due to the fact that the expansion space would consist entirely of data center space, which is significantly more expensive to build out.  Council staff will further analyze this issue for the September 19th report.

Additional Inquiries

Council staff have made inquiries to Executive staff regarding several other issues. Responses to the questions posed below were recently received but were not available in time to be included in the staff report.  Further analysis involving issues noted below will continue in preparation for the September 19th committee meeting.

Expenditures

- Why is the full amount of the project is not being requested at this time? Currently the Executive is predicting an additional legislative package for 2008 which would request an additional approximately $3 million for the project.

- The Transmittal Letter indicates several alternative proposals considered. Staff has inquired as to what assumptions or changes exist between the various proposals.

Financing

- The rationale for debt-financing infrastructure costs over only 10 years when the lease can run as long as 30 years.

- What impact will this shorter-term debt have on the central rates?

- What is the basis for including relocation costs in the financing?

- What will the impact on central rates be if we delay rate increases until the first debt payments are due (likely in 2009)?

Revenue

- Has any thought been given to ramping up internal rates for 2008 as opposed to waiting for 2009 when it is possible that agencies will also begin to pay debt service for the Accountable Business Transformation (ABT) project?

- Is it going to be possible to recover any of the fiber infrastructure costs from any of the other agencies we provide service to via I-net?

LEGAL REVIEW

The legal documents related to the Sabey center are still being reviewed by the Council’s legal advisor.

NEXT STEPS:

Council staff will continue working with executive staff to ready both pieces of legislation in preparation for possible committee action on September 19th.

INVITED:

Kurt Triplett, Chief of Staff to the King County Executive

Kathy Brown, Division Director, Facilities Management Division

Bob Cowan, Director, King County Office of Management and Budget

Jim Napolitano, DES Capital Projects Manager, Facilities Management Division

De’Sean Quinn, Council Relations Director, Office of the King County Executive

Dana Spencer, Manager, Office of Information Resource Management

CherylAnn Boudreau, Project Manager, Office of Information Resource Management

Bob Thompson, Program Manager, Facilities Management Division

ATTACHMENTS:

1.	Proposed Ordinance 2007-0443

2.	Proposed Ordinance 2007-0444

3.	Transmittal Letter, dated August 20, 2007

4.	Fiscal Note

# Footnotes

This is just an estimate for 2008 costs associated with the Data Center. The 2008 proposed budget is likely to include additional projects for the Building Repair & Replacement Fund. The Executive has indicated that a spring 2008 legislative package will be transmitted for additional Data Center costs.