March 5, 2012

Honorable Larry Gossett

Chair, King County Council

Room 120

COURTHOUSE

Dear Councilmember Gossett:

With this letter I am forwarding the Department of Elections report in response to the 2012 Adopted Budget, Ordinance 17232, Section 34, Proviso 1. The proviso states:

“Of this appropriation, $250,000 shall not be expended or encumbered until the director of elections transmits a plan for updating the voters’ pamphlets between the primary and general elections.  The plan shall include, but not be limited to ….”

The report provides the information as requested in the proviso and outlines a plan for updating the voters’ pamphlets between the primary and general elections.

Sincerely,

Sherril Huff, Director

cc:	King County Council Members

Cindy Domingo, Acting Chief of Staff

Anne Noris, Clerk of the Council

King County Department of Elections

March 2012

Updating the Voters’ Pamphlet

A Report Responding to a Proviso in King County Ordinance 17232

The following information is in response to the five items outlined in Section 34, Proviso 1.

- The cost of preparing, printing and distributing voters’ pamphlets for 2008, 2009 and 2010 as well as the percentage of costs that King County has recovered from other jurisdictions for the preparation, printing and distribution of voters’ pamphlets for 2008, 2009 and 2010.

The following table (Table 1) provides information on preparing, printing and distributing the voters’ pamphlet for 2008 through 2010.  This table displays costs billed for the Primary and General elections.  The Spring Special elections are not included due to their inconsistency and resulting unreliability when comparing annual expenses.

Table 1.  Voters’ Pamphlet Cost and Recovery

| Year |  | Cost |  | County Share |  | Other Jurisdictions |  | % Recovered |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2008 | $306,538 |  | $259,736 |  | $ 46,802 |  | 15.3% |  |  |
| 2009 | $458,119 |  | $179,772 |  | $278,347 |  | 60.8% |  |  |
| 2010 | $432,762 |  | $393,796 |  | $ 38,966 |  | 9.0% |  |  |

- The analysis used to make the decision to bring the layout of the voters’ pamphlets in-house as opposed to contracting for this service with a vendor.

King County Elections has never used a contractor for layout and design of the voters’ pamphlet. In the past, short-term temporary employees were employed off-site, with the production, coordination and translation being provided by employees in our office. In an effort to improve the process and provide efficiency to candidates and staff, Elections made the decision to shift these tasks and responsibilities to existing full-time staff.

- Key tasks or milestones and dates that need to be met for updating the voters’ pamphlets between the primary and general elections.

We have provided a list of tasks and dates that will allow for two separate submission dates for voters’ pamphlets, one for the primary election pamphlet and one for the general election pamphlet. The submission deadlines are:

Statement in the primary - May 30, 2012

Statement in the general - August  24, 2012

Please refer to the following table (Table 2) for more details.

| Pri E - | Gen E- | Date | KCE/SOS | Action |
| --- | --- | --- | --- | --- |
|  | 243 | Thursday, March 08, 2012 | SOS | Receive full text of RefBill/Amendment/Initiative to Leg for translation |
|  | 200 | Friday, April 20, 2012 | SOS | Receive arguments for RefBill/Amendment/Initiative to Leg for translation |
| 99 | 190 | Monday, April 30, 2012 | KCE | First day to accept candidate VP material by mail |
| 98 | 189 | Tuesday, May 01, 2012 |  |  |
| 97 | 188 | Wednesday, May 02, 2012 |  |  |
| 96 | 187 | Thursday, May 03, 2012 |  |  |
| 95 | 186 | Friday, May 04, 2012 |  |  |
| 94 | 185 | Saturday, May 05, 2012 |  |  |
| 93 | 184 | Sunday, May 06, 2012 |  |  |
| 92 | 183 | Monday, May 07, 2012 |  |  |
| 91 | 182 | Tuesday, May 08, 2012 |  |  |
| 90 | 181 | Wednesday, May 09, 2012 |  |  |
| 89 | 180 | Thursday, May 10, 2012 |  |  |
| 88 | 179 | Friday, May 11, 2012 | SOS KCE | Receive SOS cover, ed and ad pages for translation Deadline to file a resolution for Primary ballot measures |
| 87 | 178 | Saturday, May 12, 2012 |  |  |
| 86 | 177 | Sunday, May 13, 2012 |  |  |
| 85 | 176 | Monday, May 14, 2012 |  |  |
| 84 | 175 | Tuesday, May 15, 2012 | KCE | Explanatory statements and committee appointments due |
| 83 | 174 | Wednesday, May 16, 2012 |  |  |
| 82 | 173 | Thursday, May 17, 2012 |  |  |
| 81 | 172 | Friday, May 18, 2012 |  |  |
| 80 | 171 | Saturday, May 19, 2012 |  |  |
| 79 | 170 | Sunday, May 20, 2012 |  |  |
| 78 | 169 | Monday, May 21, 2012 | KCE | Pro/Con statements due |
| 77 | 168 | Tuesday, May 22, 2012 |  |  |
| 76 | 167 | Wednesday, May 23, 2012 | KCE | Pro/Con rebuttals due |
| 75 | 166 | Thursday, May 24, 2012 |  |  |
| 74 | 165 | Friday, May 25, 2012 |  |  |
| 73 | 164 | Saturday, May 26, 2012 |  |  |
| 72 | 163 | Sunday, May 27, 2012 |  |  |
| 71 | 162 | Monday, May 28, 2012 |  |  |
| 70 | 161 | Tuesday, May 29, 2012 | SOS | All candidate material will be available for translation |
| 69 | 160 | Wednesday, May 30, 2012 | KCE | Deadline to submit candidate VP material |
| 68 | 159 | Thursday, May 31, 2012 |  |  |
| 67 | 158 | Friday, June 01, 2012 | KCE | Ad/Ed pages final language in MS Word due from Communications |
| 66 | 157 | Saturday, June 02, 2012 |  |  |
| 65 | 156 | Sunday, June 03, 2012 |  |  |
| 64 | 155 | Monday, June 04, 2012 |  |  |
| 63 | 154 | Tuesday, June 05, 2012 |  |  |
| 62 | 153 | Wednesday, June 06, 2012 |  |  |
| 61 | 152 | Thursday, June 07, 2012 |  |  |
| 60 | 151 | Friday, June 08, 2012 | KCE | Layout of Ad/Ed pages to communications for review English data entry and proofing completed (Primary candidates only) |
| 59 | 150 | Saturday, June 09, 2012 |  |  |
| 58 | 149 | Sunday, June 10, 2012 |  |  |
| 57 | 148 | Monday, June 11, 2012 |  |  |
| 56 | 147 | Tuesday, June 12, 2012 | KCE | Final approval of layout and ad/ed pages Bulk inquiry sent to SPL and KCLS |
| 55 | 146 | Wednesday, June 13, 2012 | KCE | Initial meeting regarding placement of ad/ed pages (priority of messaging) |
| 54 | 145 | Thursday, June 14, 2012 |  |  |
| 53 | 144 | Friday, June 15, 2012 | SOS KCE | Receive full text RefMeasure/ Initiative for translation Proof layout emailed to candidates and pro/con committees |
| 52 | 143 | Saturday, June 16, 2012 |  |  |
| 51 | 142 | Sunday, June 17, 2012 |  |  |
| 50 | 141 | Monday, June 18, 2012 | KCE | Deadline for candidate and committee response to proof email |
| 49 | 140 | Tuesday, June 19, 2012 |  |  |
| 48 | 139 | Wednesday, June 20, 2012 |  |  |
| 47 | 138 | Thursday, June 21, 2012 | SOS | Candidate statements entered into WEI (Chinese and Vietnamese) |
| 46 | 137 | Friday, June 22, 2012 | KCE | VP information live on the web (all languages) Editions, page numbers and bulk delivery information to vendor |
| 45 | 136 | Saturday, June 23, 2012 |  |  |
| 44 | 135 | Sunday, June 24, 2012 |  |  |
| 43 | 134 | Monday, June 25, 2012 |  |  |
| 42 | 133 | Tuesday, June 26, 2012 |  |  |
| 41 | 132 | Wednesday, June 27, 2012 |  |  |
| 40 | 131 | Thursday, June 28, 2012 |  |  |
| 39 | 130 | Friday, June 29, 2012 | KCE | Editions finalized and approved |
| 38 | 129 | Saturday, June 30, 2012 |  |  |
| 37 | 128 | Sunday, July 01, 2012 |  |  |
| 36 | 127 | Monday, July 02, 2012 |  |  |
| 35 | 126 | Tuesday, July 03, 2012 | KCE | PDFs of VP to printer |
| 34 | 125 | Wednesday, July 04, 2012 |  |  |
| 33 | 124 | Thursday, July 05, 2012 |  |  |
| 32 | 123 | Friday, July 06, 2012 | KCE | Signoff on vendor proofs |
| 31 | 122 | Saturday, July 07, 2012 |  |  |
| 30 | 121 | Sunday, July 08, 2012 |  |  |
| 29 | 120 | Monday, July 09, 2012 |  |  |
| 28 | 119 | Tuesday, July 10, 2012 |  |  |
| 27 | 118 | Wednesday, July 11, 2012 | SOS | Receive arguments for RefMeasure for translation |
| 26 | 117 | Thursday, July 12, 2012 |  |  |
| 25 | 116 | Friday, July 13, 2012 |  |  |
| 24 | 115 | Saturday, July 14, 2012 |  |  |
| 23 | 114 | Sunday, July 15, 2012 |  |  |
| 22 | 113 | Monday, July 16, 2012 |  |  |
| 21 | 112 | Tuesday, July 17, 2012 | KCE | VP mailed |
| 20 | 111 | Wednesday, July 18, 2012 |  |  |
| 19 | 110 | Thursday, July 19, 2012 | KCE | VP in homes |
| 18 | 109 | Friday, July 20, 2012 |  |  |
| 17 | 108 | Saturday, July 21, 2012 |  |  |
| 16 | 107 | Sunday, July 22, 2012 |  |  |
| 15 | 106 | Monday, July 23, 2012 |  |  |
| 14 | 105 | Tuesday, July 24, 2012 |  |  |
| 13 | 104 | Wednesday, July 25, 2012 |  |  |
| 12 | 103 | Thursday, July 26, 2012 |  |  |
| 11 | 102 | Friday, July 27, 2012 |  |  |
| 10 | 101 | Saturday, July 28, 2012 |  |  |
| 9 | 100 | Sunday, July 29, 2012 |  |  |
| 8 | 99 | Monday, July 30, 2012 |  |  |
| 7 | 98 | Tuesday, July 31, 2012 |  |  |
| 6 | 97 | Wednesday, August 01, 2012 | KCE | First day to accept candidate material resubmissions |
| 5 | 96 | Thursday, August 02, 2012 |  |  |
| 4 | 95 | Friday, August 03, 2012 |  |  |
| 3 | 94 | Saturday, August 04, 2012 |  |  |
| 2 | 93 | Sunday, August 05, 2012 |  |  |
| 1 | 92 | Monday, August 06, 2012 |  |  |
| 0 | 91 | Tuesday, August 07, 2012 | KCE | Deadline to file a resolution for General ballot measures |
|  | 90 | Wednesday, August 08, 2012 |  |  |
|  | 89 | Thursday, August 09, 2012 | SOS | Receive arguments for Initiative Measures for translation |
|  | 88 | Friday, August 10, 2012 | KCE | Explanatory statements and committee appointments due |
|  | 87 | Saturday, August 11, 2012 |  |  |
|  | 86 | Sunday, August 12, 2012 |  |  |
|  | 85 | Monday, August 13, 2012 | SOS | Receive explanatory and fiscal statements for translation |
|  | 84 | Tuesday, August 14, 2012 |  |  |
|  | 83 | Wednesday, August 15, 2012 | KCE | Pro/Con statements due |
|  | 82 | Thursday, August 16, 2012 |  |  |
|  | 81 | Friday, August 17, 2012 | KCE | Pro/Con rebuttals due |
|  | 80 | Saturday, August 18, 2012 |  |  |
|  | 79 | Sunday, August 19, 2012 |  |  |
|  | 78 | Monday, August 20, 2012 |  |  |
|  | 77 | Tuesday, August 21, 2012 |  |  |
|  | 76 | Wednesday, August 22, 2012 |  |  |
|  | 75 | Thursday, August 23, 2012 |  |  |
|  | 74 | Friday, August 24, 2012 | KCE | Deadline to resubmit candidate VP material (not starting General Translation until this point) |
|  | 73 | Saturday, August 25, 2012 |  |  |
|  | 72 | Sunday, August 26, 2012 |  |  |
|  | 71 | Monday, August 27, 2012 |  |  |
|  | 70 | Tuesday, August 28, 2012 |  |  |
|  | 69 | Wednesday, August 29, 2012 |  |  |
|  | 68 | Thursday, August 30, 2012 |  |  |
|  | 67 | Friday, August 31, 2012 | KCE | Ad/Ed pages final language in MS Word due from Communications English data entry and proofing completed |
|  | 66 | Saturday, September 01, 2012 |  |  |
|  | 65 | Sunday, September 02, 2012 |  |  |
|  | 64 | Monday, September 03, 2012 |  |  |
|  | 63 | Tuesday, September 04, 2012 |  |  |
|  | 62 | Wednesday, September 05, 2012 |  |  |
|  | 61 | Thursday, September 06, 2012 |  |  |
|  | 60 | Friday, September 07, 2012 | KCE | Layout of Ad/Ed pages to Communications for review |
|  | 59 | Saturday, September 08, 2012 |  |  |
|  | 58 | Sunday, September 09, 2012 |  |  |
|  | 57 | Monday, September 10, 2012 |  |  |
|  | 56 | Tuesday, September 11, 2012 | KCE | Final approval of layout and ad/ed pages |
|  | 55 | Wednesday, September 12, 2012 | KCE | Initial meeting regarding placement of ad/ed pages (priority of messaging) |
|  | 54 | Thursday, September 13, 2012 |  |  |
|  | 53 | Friday, September 14, 2012 | KCE | Proof layout emailed to candidates and pro/con committees |
|  | 52 | Saturday, September 15, 2012 |  |  |
|  | 51 | Sunday, September 16, 2012 |  |  |
|  | 50 | Monday, September 17, 2012 | KCE | Deadline for candidate and committee response to proof email |
|  | 49 | Tuesday, September 18, 2012 |  |  |
|  | 48 | Wednesday, September 19, 2012 | SOS | Final Chinese/Vietnamese PDFs due to SOS |
|  | 47 | Thursday, September 20, 2012 | SOS | All measure info entered into WEI (Chinese and Vietnamese) |
|  | 46 | Friday, September 21, 2012 | KCE | VP information live on the web (all languages) Editions, page numbers and bulk delivery information to vendor |
|  | 45 | Saturday, September 22, 2012 |  |  |
|  | 44 | Sunday, September 23, 2012 |  |  |
|  | 43 | Monday, September 24, 2012 |  |  |
|  | 42 | Tuesday, September 25, 2012 |  |  |
|  | 41 | Wednesday, September 26, 2012 |  |  |
|  | 40 | Thursday, September 27, 2012 |  |  |
|  | 39 | Friday, September 28, 2012 | KCE | Editions finalized and approved |
|  | 38 | Saturday, September 29, 2012 |  |  |
|  | 37 | Sunday, September 30, 2012 |  |  |
|  | 36 | Monday, October 01, 2012 |  |  |
|  | 35 | Tuesday, October 02, 2012 | KCE | PDFs to vendor |
|  | 34 | Wednesday, October 03, 2012 |  |  |
|  | 33 | Thursday, October 04, 2012 |  |  |
|  | 32 | Friday, October 05, 2012 | KCE | Signoff on vendor proofs |
|  | 31 | Saturday, October 06, 2012 |  |  |
|  | 30 | Sunday, October 07, 2012 |  |  |
|  | 29 | Monday, October 08, 2012 |  |  |
|  | 28 | Tuesday, October 09, 2012 |  |  |
|  | 27 | Wednesday, October 10, 2012 |  |  |
|  | 26 | Thursday, October 11, 2012 |  |  |
|  | 25 | Friday, October 12, 2012 |  |  |
|  | 24 | Saturday, October 13, 2012 |  |  |
|  | 23 | Sunday, October 14, 2012 |  |  |
|  | 22 | Monday, October 15, 2012 |  |  |
|  | 21 | Tuesday, October 16, 2012 | KCE | VP mailed |
|  | 20 | Wednesday, October 17, 2012 |  |  |
|  | 19 | Thursday, October 18, 2012 |  |  |
|  | 18 | Friday, October 19, 2012 |  |  |
|  | 17 | Saturday, October 20, 2012 |  |  |
|  | 16 | Sunday, October 21, 2012 |  |  |
|  | 15 | Monday, October 22, 2012 |  |  |
|  | 14 | Tuesday, October 23, 2012 |  |  |
|  | 13 | Wednesday, October 24, 2012 |  |  |
|  | 12 | Thursday, October 25, 2012 |  |  |
|  | 11 | Friday, October 26, 2012 |  |  |
|  | 10 | Saturday, October 27, 2012 |  |  |
|  | 9 | Sunday, October 28, 2012 |  |  |
|  | 8 | Monday, October 29, 2012 |  |  |
|  | 7 | Tuesday, October 30, 2012 |  |  |
|  | 6 | Wednesday, October 31, 2012 |  |  |
|  | 5 | Thursday, November 01, 2012 |  |  |
|  | 4 | Friday, November 02, 2012 |  |  |
|  | 3 | Saturday, November 03, 2012 |  |  |
|  | 2 | Sunday, November 04, 2012 |  |  |
|  | 1 | Monday, November 05, 2012 |  |  |
|  | 0 | Tuesday, November 06, 2012 |  |  |

- The cost of updating the voters’ pamphlets between the primary and general elections, including an analysis of producing the voters’ pamphlets in-house or through a vendor.  In addition to identifying the cost of updating the pamphlets, the analysis should identify any operational or logistical considerations for updating the pamphlet.

King County Elections does not use vendors for producing election materials. Vendors are contracted only for printing and mailing of elections materials.

- The pros and cons, including costs and schedule impacts, of producing a voters’ pamphlet jointly with the state of Washington, particularly in even-numbered years.  The plan shall also identify the pros and cons of not producing voters’ pamphlets in even numbered years and having the state voters’ pamphlet include local issues.

King County Elections produces a primary voters’ pamphlet according to K.C.C. 1.10.010. The State of Washington does not produce and distribute a primary voters’ pamphlet. Voters receive a primary pamphlet from King County, but receive a State-produced pamphlet in the general, which has created confusion for voters as to where the King County-specific information was placed.

The submission date for candidates appearing in the general election State voters’ pamphlet is May 25. The State requests that we know the number of pages we would need as early as mid-June. We do not know which districts with propositions will appear in the general election until August 7.  The early submission dates make it difficult for targeting which messages voters in King County need to properly cast and return their ballots. It does not allow our office to provide information that is timely to the election.

In past years, King County-specific information did not start to appear until 50 plus pages into the pamphlet. We have heard from voters that when we produce and distribute a voters’ pamphlet that closely follows a voter’s ballot, this creates less confusion.

King County Elections is required to produce pamphlets in two languages, Chinese and Vietnamese. The State-produced pamphlet does not allow separate editions to be mailed to specific voters. The languages are added to the English, therefore creating an extremely large pamphlet.