## OEOCE Business Plan 2025
Department: |  |  | Project & Program Objectives, Strategies, Goals | [9 empty] | Key Performance Measures |  |  |  |  | Activities to Implement Strategies
Dept | Division Name | Priority Initiative / Project | Primary Executive Priority Linkage, if any | Project / Program Objective | Strategy | Goals | Who is Responsible | ERSJ Alignment | Anticipated Tier 5 Monitoring | Indicator (Not started -G-R-Done) | Current Status (comments) | Date Updated | Key Performance Measures | Why is the measure important to monitor? | Numerical goal for measure | Most recent data point | Countywide internal project? (Y/N) | Milestone 1 Date | Milestone 1 | Milestone 2 date | Milestone 2 | Milestone 3 date | Milestone 3 | Milestone 4 date | Milestone 4 | Milestone 5 date | Milestone 5 | Milestone 6 date | Milestone 6
EXEC | OEOCE | OEOCE - Operationalize the Office - Standard Work and Data | Best-Run Government | Create and implement standard work for OEOCE. Build a system for OEOCE to collect, analyze, and report program/project data on a rolling basis. Train/support OEOCE staff in implementing the system and updating their data. | See Column E | OEOCE makes data-driven program and project decisions, rapidly course-corrects, and provides on-demand evidence of program and project efficacy and impact. | Sponsor: Kate Becker & Ashton Allison Lead/PM: Susano Surface | Enhancing King County’s capacity to implement pro-equity/anti-racism work | Annual Plan Monitoring | On Track | Work breakdown structure is drafted; have compiled research on several "dashboard" platforms | 2024-11-05 | OEOCE develops and implements a comprehensive reporting system for OEOCE activities, ensuring that 100% of key performance measures are tracked and reported monthly by the end of Q3 2025. Equity: KPMs align with OERSJ strategic plan metrics when available in 2025 Climate: KPMs align with ECO's SCAP metrics when available in June 2025. | Ensure OEOCE's alignment with BRG Executive Priority, measured by improved BRGR self-assessment scores due to making data-driven decisions (which will require having usable, accessible data.) | See column L | NA - project not started | No | 2025-02-28 | Data collection platform is identified (and purchased if necessary) | 2025-03-31 | First round of platform build-out; draft training contents | 2025-04-30 | Revised platform build-out; existing OEOCE data is input for user testing; staff training begins | 2025-07-30 | User testing complete, staff training refinement, Finalization process begins | 2025-09-30 | System is ready to go and OEOCE begins to track data; staff are trained | 2025-12-31 | OEOCE has input and reported 6 months of data; troubleshooting has taken place.
EXEC | OEOCE | OEOCE- Develop Communications Strategy | Best-Run Government | Expand and amplify communications and external relations, increasing engagement with OEOCE's social media, newsletters, websites, publicity, and earned media by 30% in 2025. | Investments in Website and Social Media platforms; increase staff capacity with dedicated comunications support | OEOCE's activities are transparent and appealing to residents, workers, vistors, and all who enjoy King County's Cultural sector. | Kate Becker | Enhancing King County’s capacity to implement pro-equity/anti-racism work | Annual Plan Monitoring | On Track | Creative Economy e-newsletter is shared regularly. KingCounty.gov website has been refreshed. FAQ is ready to post. Social Media and kingcountycreative.com focus. | 2024-11-05 | Open/click rate for e-newsletter, number of likes/comments/reposts on social media, qualitative feedback via email or other direct engagement, number of page views and clicks on websites, reduction of individual email inquiries and staff response times after FAQ is published, reduction of staff time in responding individually to repeated inquiries, number of earned media articles pertaining to OEOCE, and more. Equity: 100% ADA/WCAG/W3C compliance of new content on web and social. Communication materials (social media posts, newsletters, website content) are available in multiple languages and accessible formats (e.g., screen reader-friendly, subtitles). Equity: Number of content pieces (articles, posts, newsletters) specifically addressing equity-related topics and issues relevant to frontline communities. Climate: Percentage of communications content (social media posts, newsletters, website articles) that includes climate-related topics. Climate: Adoption of sustainable practices in content production and distribution (e.g., reducing digital carbon footprint, using eco-friendly materials for print). | Understand how community members and relevant industries are learning about OEOCE's programs/projects. Optimize information. | Maintain e-news open rate. For others, 30% increase from 2024 numbers in Column O | Reporting Period: 01/01/2024-11/05/2024 Creative Economy E-newsletter - 57% open rate. @kingcountycreative instagram - 1,346 followers @harborislandstudios Instagram - 345 followers King County Creative Facebook Group: 3,100 Members kingcountycreative.com - 14,584 views OEOCE kingcounty.gov - 1,575 views # of earned media articles pertaining to OEOCE - 12 | No | 2024-11-30 | Publish FAQ to OEOCE kingcounty.gov page by Q3 2024. Set up Autoresponse with FAQ link for creativeeconomy@kingcounty.gov | 2025-03-31 | Launch Economic Opportunity newsletter by Q1 2025. | 2025-03-31 | Hire communications & social media support and create content plan. Create plans and collateral for marketing, social media, publicity, and branding by Q1 2025 Refresh kingcountycreative.com by Q1 2025
EXEC | OEOCE | Creative Economy - Film - Harbor Island Studios - Business Development | Anti-Racism / Pro-Equity | Generate new film-industry business & jobs at Harbor Island Studios. 2025-2026 will be pilot years as OEOCE manages and monitors HIS workflow, capital improvements, and staffing/facility capacity. OEOCE will explore alternative business models for Harbor Island Studios (public/private, etc.) | Operate and promote Harbor Island Studios | OEOCE builds the Film industry in King County, creates living wage, climate-conscious, working-class film industry jobs; earns income sufficient to pay operating costs of Harbor Island Studios; ensures Harbor Island Studios is accessible to under-resourced filmmakers. | Kate Becker | Enhancing King County’s capacity to implement pro-equity/anti-racism work | Annual Plan Monitoring | On Track | Films, episodics, commercials, and other productions have commenced and continue to take place in HIS. In 2025, mill/roof construction will impact the number of productions. | 2024-11-05 | Number of inquiries received per year Number of tours conducted per year Number of completed productions per year Budget, per production and per year Earned income (total, and also in relation to cost of operating and staffing HIS), per production and per year Production spend with King County (small) businesses, per production and per year Number of production learning opportunities, per production and per year Space Utilization: Use days per sound stage/space in Harbor Island Studios Union & Prevailing Wage Jobs Created: Number of jobs created and the percentage of total jobs that are Union/Prevailing Wage, per production and per year Efficiency of Studio: The average time required to prepare the studio for a new production from the end of the previous production. Customer Satisfaction: Achieve a satisfaction rating of 80% or higher from customers regarding their experience at Harbor Island Studios. Equity: Diversity of cast and crew members based on disaggregated demographic data, per production and per year Equity: Percentage of productions representing different economic situations (budget, corporate vs. independent, etc.) Equity: Number and percentage of living wage jobs created that are filled by individuals from institutionally marginalized communities, per production and per year Climate: Number of productions categorized as climate-friendly, based on criteria such as use of sustainable practices, reduced carbon footprint, or green certifications. | Baseline the productivity of HIS, so its operations can be understood and optimized | See Column L | Pilot project history and inquiry database | No | 2025-06-30 | Systems developed to capture data in 2024-2025 | 2025-09-30 | Analyze first quarter of studio data capture and system efficacy. | 2025-12-31 | Four month data collection complete - tracking productions, crew info, calendar references | 2026-09-30 | One year data complete
EXEC | OEOCE | Creative Economy - Film - Harbor Island Studios - Capital Improvements | Environment | Complete Harbor Island Studios capital improvements (mill complete by January 2025; roof replacement is still TBD per SW) | County investments in mill construction, and roof replacement that includes soundproofing, solar generation, and lighting grid | OEOCE elevates Harbor Island Studios facility to be competitive with the industry-standard offerings of other major soundstages, thus contributing to increased numbers of local productions and living wage jobs; climate action in building improvements. | Nate Brend (FMD) | Other - KC values-based pricing scheme incentivizes hiring of casts and crews that have historically & institutionally been underresourced. | Annual Plan Monitoring | On Track | Mill construction is scheduled to be completed by January 2025. Roof Construction to take place in 2025, date TBD. Ongoing exploration of lighting grid/solar power generation on roof may impact timeline. | 2024-11-05 | 1. Completion of mill construction - the mill will exist where there previously was none. 2. Exploring additions of lighting grid and solar generators on HIS roof. 3. Completion of roof replacement - roof will no longer leak and will be more soundproof. 4. All construction completed on time and on budget. 5. Equity: Percentage of WMBE capital improvement contracts. 6. Equity: Number of design or construction adjustments made to ensure the new facilities are accessible to individuals with disabilities and inclusive of diverse needs. Upon completion of construction: Track the assumed increase in monthly/quarterly/yearly rentals for the desirabiltiy/usefulness of the venue following the improvements. Climate: Receive a Bronze (38% or above of total applicable points) on the Sustainable Infrastructure Scorecard. Climate: Compare utility costs (in dollars) year-over-year to measure savings. Climate: Track the financial savings (in dollars) from solar installations and other renewable energy sources. | Ensure the usefulness of capital improvements, which impacts community's ability to access and benefit from HIS. Ensure the construction and design process and outcome align with the Executive Priorities on Equity and Climate. | Construciton completion, construction budget (FMD), noise reduction difference in decibels. | NA | No | 2025-01-31 | Mill constructed. Date shifted due to FMD and SW orders. | 2025-02-01 | Harbor Island Studios reopens betwen Mill and Roof construction. Date shifted due to FMD and SW orders. | 2025-06-30 | Roof Replaced. Date shifted due to FMD and SW orders. | 2025-07-01 | Harbor Island Studios reopens after Roof construction. Date shifted due to FMD and SW orders. | 2025-09-30 | Harbor Island Studios is activated at capacity, with minimal un-used time between productions. Date shifted due to FMD orders. | 2025-12-31 | Major feature film landed and work completed. Date shifted due to FMD orders.
EXEC | OEOCE | Creative Economy - Film - Executive’s Film Advisory Board (EFAB), Permitting, Ecosystem Study, and Film Ordinance | Anti-Racism / Pro-Equity | Continue supporting Executive Film Advisory Board (EFAB) in its advisory role for HIS. Film Permitting process to be streamlined and published to website by Q3 2025. Film Ecosystem Study, in partnership with City of Seattle, to be completed in Q1 2025. Film Ordinance to be drafted by Q2 2025, with intent to pass council thereafter. | EFAB membership is diverse (across film industry experience type, as well as individual demographics) and active/participatory; create working groups | OEOCE manages governance of HIS by a working film industry experts, ensuring the facility is desirable to industry and becomes self-sustaining. | Kate Becker | Working with community | Annual Plan Monitoring | On Track | Film Ecosystem Study was on hiatus due to COVID-19 emergency and City of Seattle staffing changes; deadline extended at request of City of Seattle. Additional dates shifted due to internal factors. | 2024-11-05 | Film Ordinance draft passed. Interdepartmental film liaison collaobration process will be operationalized. Work w/ FMD and SW will be complete and film permitting process will be decided and posted publicly. Film Ecosystem Study will be published. Upcoming for 2025: Film Permitting Website is updated with directions for applicants to inquire about filming in King County owned properties, and the information to contact other local jurisdictions or private property owners if the interest is a non-KC owned property. Permit and Filmmaking Inquiries: The number of filming inquiries received, regardless of outcome. Permit Issuance Quantity: The number of film production permits issued per month/quarter/year. Permit Type: The number of permits by type (e.g., feature films, shorts, documentaries, music videos, commercials). Permit Distribution by Geographic Area: The number of permits issued in different geographic regions within the county Permit Holder Demographics: The number of permits by type of filmmaker (corporate, independent) and film budget strata Permit Processing Time: The average time taken from permit application to permit issuance. Permit Income: The average permit fee collected per vendor. Specific fees paid per production for "King County Values" discounts. Equity: Permit Holder Demographics: The number of permits issued per demographic category (e.g., race/ethnicity, gender, disability status, production companies, independent filmmakers). Equity: Number of equity-related provisions included in the streamlined film permitting process published on the website (e.g., support for marginalized filmmakers, inclusive fee structures). Climate: Number & impact of climate and sustainability provisions included in the draft Film Ordinance. Film Ordinance Equity: Number of equity-focused provisions included in the draft Film Ordinance (e.g., requirements for equitable hiring practices, incentives for inclusive projects). Film Ecosystem Study Equity: Number of recommendations in the Film Ecosystem Study that focus on increasing equity and access for underrepresented groups in the film industry. Climate: Number of recommendations in the Film Ecosystem Study that address climate impact and sustainability in film production. | Ordinance & permit process updates will make filming in KC more attractive and accessible to industry. Study will provide clarity about state of the field and how issues can be addressed. | See Column L | EFAB meets monthly, Excel sheet tracks film industry inquiries, multiple KC departments issue and track film permits | No |  |  | 2024-12-31 | External Film Ecosystem Study sessions and interviews complete. | 2025-03-31 | Film Ecosystem Study complete and published. | 2025-06-30 | Film Ordinance drafted following consultation w internal (EFAB, FMD, RES, DNRP, DLS, & Metro) and external (film industry) collaborators. | 09/31/2025 | Film Permitting Process ready to launch and promote.
EXEC | OEOCE | Creative Economy - Music Industry Development – Innovation Cluster, Cascadia Music Corridor, and WA Music Census | Anti-Racism / Pro-Equity | Understand the scale of King County's music economy by: obtaining WA statewide data pertaining to the Cascadia Music Corridor by December 2024 nd producing Washington Music Census results by March 2025, With this information OEOCE will be able to strategize how best to support King County's music industry. | Create the Washington Music Census, the first major study of the WA state music industry, current since the COVID pandemic | OEOCE understands King County's music economy and its role within the State and Regional music industries, in order to make data-driven decisions about how to best support the industry. | Amie Danielewicz + Kate Becker | Working with community | Annual Plan Monitoring | On Track | The scale of King County's music economy is unknown. In a 2019 Seattle Creative Economy Study, musicians were the lowest paid workers in our creative economy. Data and research are needed to understand the scale of our music ecosystem to inform policy decisions. UW Evans School music ecosystem research Jan-April 2024 complete. Have secured funding from WA Dept. of Commerce and City of Seattle to produce the WA Music Census. | 2024-11-05 | UW Evans School contract secured and student research completed. Washington Music Ecosystem Study completed. Innovation Cluster work with WA Dept of Commerce will have music ecosystem cohort established and working together. Cascadia Music Corridor will compile and share Cascadia Music Summit learnings. Washington Music Census Equity: Washington Music Census includes specific analysis on the participation, challenges, and opportunities for underrepresented and marginalized groups in the music industry. Climate: Percentage of the Washington Music Census that includes analysis of the climate impact and sustainability practices within the music industry. Cascadia Music Corridor Equity: Percentage of music industry leaders from OR, ID, and AK involved in the Cascadia Music Corridor who represent underrepresented and marginalized groups (e.g., racial/ethnic minorities, women, LGBTQ+). Cascadia Music Summit Equity: Percentage of strategies and recommendations developed through the Cascadia Music Summit that include specific provisions for increasing equity and access for marginalized groups in the music industry. Climate: Number of climate-related insights and recommendations included in the analysis of WA statewide data for the Cascadia Music Summit. | Statewide collaboration (relationship-building as well as results for music sector) and ensuring a meaningful educational opoprtunity for student consultants | Publication of Music study, formation of Innovation Cluster cohort, publication of Cascadia Music Summit findings. | $150k from WA Dept. of Commerce and $100k from City of Seattle OED - funding secured to complete Music Census. Must be expended by 12/31/2025. | No | 2024-12-31 | Cascadia Music Corridor work continues in partnership with OR, ID & AK music industry leaders | 2024-12-31 | Washington Music Census data is complete and analyzed | 2025-03-31 | Washington Music Census report is complete and socialized with regional and state leaders | 2025-04-27 | National Convening of Music Ecosystem Leaders, public reveal of WA Music Census data and analysis
EXEC | OEOCE | Creative Economy - Festivals/Events/Nightlife Partnerships | Anti-Racism / Pro-Equity | Collaborate with WFEA, WANMA, Cultural Leaders Roundtable, NITECAP, etc. to provide technical assistance and strategic support; Partner to produce the Cascadia Music Summit (April 25-27, 2025). | Produce major industry event, where new, significant Washington Music Census will be shared and discussed | OEOCE creates cohesion across regional Music industry, with King County/WA State as leaders in gathering data/evidence on the current status and recommendations for how to move forward. | Kate Becker/Amie Danielewicz | Working with community | Annual Plan Monitoring | On Track | OEOCE continues to participate in WFEA and WANMA. 2025 regional film and music event schedule and participation plan confirmed. | 2024-11-05 | Execution of 2025 Cascadia Music Summit in King County. Customer Satisfaction: Successfully host the Cascadia Music Summit with at least 80% of surveyed attendees rating the events as valuable and well-organized. Equity: Number of summit sessions, panels, or workshops that specifically address equity and inclusion issues in the film and music industries. Equity: Number of accessibility features provided at the Cascadia Music Summit (e.g., sign language interpreters, captioning, wheelchair access, accessible materials, ADA-compliant venues). Climate: Number of climate-friendly initiatives implemented during the Cascadia Music Summit (e.g., waste reduction strategies, energy-efficient technologies). Climate: Number of sessions or panels at the Cascadia Music Summit that address climate issues in the creative and music industries. | Ongoing support of and influence in key creative industries | See Column L | NA | No | 2024-11-16 | 4 state partners planning session for April 2025 | 2025-04-27 | Cascadia Music Summit hosted in King County
EXEC | OEOCE | Creative Economy - Hospitality/Tourism - Cloudbreak Music Festival | Anti-Racism / Pro-Equity | Ongoing engagement with Hospitality and Tourism partners, locally, nationally, and internationally, including the annual Cloudbreak Music Festival | Produce Cloudbreak Music Festival; increase promotions, marketing, and communication of festival | OEOCE promotes economic security and visibility of local musicians and music venues, provides opportunities for tourists to experinece Seattle musicians and venues, deveops and highlights the links between tourism and cultural sector. | Kate Becker/Amie Danielewicz | Working with community | Annual Plan Monitoring | On Track | Continued engagement with tourism (City of Seattle, Visit Seattle, Southside Regional Tourism Agency, SnoValley Chamber, etc), WA Restaurant Association, national colleagues, and internal departments. | 2024-11-05 | Hospitality/Toursim Number of site visits to tourism locations and events Number of presentations to hospitality and tourism groups Number of attendees and venues. Cloudbreak Attendance: Total number of Hotel stays/guests that attended Cloudbreak Total number of non-hotel related Cloudbreak attendees Advance Reservations: Total number of ticket sales made in advance. Walk-Ups: Total number of walk-up attendees. No-Shows: Total number of reserved attendees who did not show up. Overall Attendance: Total number of attendees. Funding: Track how amount of funding for Cloudbreak each year (total, per venue, per artist) affects the impact and nature of festival. Compare the number of shows presented before and after the change in funding guidelines. Measure the amount of funding allocated per show before and after changes in funding guidelines. Estimate range of total revenue generated from tourist spending (in dollars) Total revenue generated in addition to typical Equity: All venues self-report as ADA compliant. Venues have opportunity to report additional access measures (sign language, international language interpretation, etc.) Equity: Percentage of performing artists coming from underrepresented or marginalized communities, including racial/ethnic minorities, women, LGBTQ+ individuals, and artists with disabilities. Climate: Number of partner venues that include a focus on climate-friendly practices (e.g., energy-efficient facilities, waste reduction). Climate: Number of sustainability initiatives implemented in the planning and execution of Cloudbreak Music Festival, including waste management, energy use, and transportation. | Hospitality and tourism are key economic drivers for our region | # of presentations, # of partnerships, # of trainings, # of convenings and collaborations | NA | No | 2025-01-15 | Analysis of Cloudbreak Music Festival 2024. Determined via partner meetings that there is budget and appettite to continue in 2025. DONE | 2025-03-15 | Launch of planning process for Cloudbreak 2025 | 2025-04-10 | Decision finalized to produce Cloudbreak 2025. Funding secured. | 2025-06-30 | Partnership with Freakout Festival, new structure for funding to venues and artists, venues secured, public announcement of event dates. | 2025-09-09 | Public announcement of artist lineup, venues, calendar | 11/31/2025 | Cloudbreak Festival takes place
EXEC | OEOCE | Creative Economy - Countywide Creative Districts | Anti-Racism / Pro-Equity | Support Councilmember Perry and ArtsWA in the development of creative districts throughout King County District 3 | Build relatinoships with KC Cities that do not currently participate in the creative districts program | OEOCE ensures that Creative Economy is supported and visible throughout King County, leading to increased opportunities and income for creative workers and businesses. | Kate Becker | Working with community | Annual Plan Monitoring | On Track | Monthly group meetings + individual meetings w/ District 3 city leaders | 2024-11-05 | Work with District 3 city leads to strategize their respective creative district initiatives. Equity: Number of equity-focused features included in the creative district design, such as affordable artist spaces, cultural programming, and accessibility features. Climate: Number and percentage of sustainable design features implemented in the creative districts' plans, including energy efficiency, water conservation, and green building materials. Climate: Reduction in the carbon footprint associated with the development and operation of the creative districts, including transportation, energy use, and waste management. | Each District 3 city will have a different creative district plan based on thier strengths | Minimum of 3 (out of 13) District 3 cities that initiate creative district strategies in 2025 | 1 year of participation in monthly group meetings + numerous individual city consultations | No | 2025-03-31 | Development continues with Carnation and North Bend. | 2025-12-31 | 2nd and 3rd creative districts launched with branding and public campaign
EXEC | OEOCE | Economic Opportunity - Business Retention & Expansion - Community Business Connector program | Anti-Racism / Pro-Equity | Increase countywide small business assistance capacity at least by one ADO Community Business Connector organization in 2025, with a focus on UKC, South King County, and neighborhoods where the self-sufficiency standards are lowest. | Outreach and relationship-building with organiztions that are not yet participants | OEOCE creates increased business connections in under-resourced areas of King County. | Amie Danielewicz | Working with community | Annual Plan Monitoring | Complete | Currently fund nine ADO Business Connector organizations representing six geographic hubs across the county, with plans to add one more. CLFR funding is expended; Port of Seattle & City of Seattle are providing follow-on funding to sustain the program. | 2024-11-05 | Port of Seattle's equity metrics TBD. Small Business Assistance: Increase the number of small businesses receiving assistance in UKC and South King County by 15% by the end of 2025, tracked through assistance programs and feedback surveys. Equity: The percentage of small business assistance distributed across targeted areas, including UKC, South King County, and neighborhoods with the lowest self-sufficiency standards. Align with ERSJ update. Climate: The percentage of total assistance resources allocated to businesses focused on green or climate-friendly initiatives. Align with SCAP update. Climate: The percentage of businesses receiving assistance located in areas most affected by climate change and environmental justice issues. Align with SCAP update. Climate: The percentage of assisted businesses that adopt climate resilience measures, such as energy efficiency or flood protection. Align with SCAP update. | Alignment with racial equity & BRG values; documenting amount of assistance provided and who is receiving it | One new business connector organization is contracted with the ADO | NA | No | 2025-12-31 | One new business connector org is contracted with ADO
EXEC | OEOCE | Economic Opportunity - Business Retention & Expansion - King County Aerospace Alliance | Environment | Expand Aerospace Alliance beyond King County boundaries to be a multi-county initiative. Host one additional study briefings by Q2 2025, with the goals of educating private industry about the importance of the aerospace industry and retaining the legacy aerospace manufacturing footprint, while fostering growth in the new space sector. TBD: Community Business Connector outreach to supply-chain vendors large and small | See Column E | OEOCE nurtures the regional Aerospace industries, and creates positive business environment to support local proeduction and living wage job creation. OEOCE Influences the Aerospace industry to embed equity and environmental factors in its operations and products. | Ashton Allison | Working with community | Annual Plan Monitoring | On Track | Expansion to multi-county initiative in progress. One additional briefing is being planned with GSP for Private Industry. | 2024-11-05 | Private Industry briefing will have taken place in 2024. Measurements may include - number of engagements/questions by attendees, inquiries from interested elected officials. Customer Satisfaction and Engagement Document the impact of briefings through a participant feedback survey showing at least 80% satisfaction. Track and record the total number of documented engagements, including questions, comments, or feedback, received from attendees during briefings. Document the total number of formal inquiries received from elected officials concerning specific projects, initiatives, or organizational updates Equity: The percentage of speakers and panelists at the briefings who represent diverse backgrounds and perspectives. Equity: The number of community organizations or groups representing diverse or underserved populations contacted for outreach about the briefings. Climate: Number of climate impact and sustainability topics addressed in the briefing agendas, including emissions reduction strategies and sustainable aerospace technologies. Climate: Number of climate and sustainability experts included among the speakers and panelists at the briefings. | Awareness of current status, stakeholder engagement & future opportunity in the sector | See Column L | NA | No | 2025-06-30 | Host briefing event #3: Private Industry | 2025-12-31 | Formallize and socialize new Aerospace Alliance
EXEC | OEOCE | Economic Opportunity - Business Retention & Expansion - New and Existing Employers | Environment | New and Existing Employers: Conduct an analysis of current County assets, especially real property, that could potentially be utilzied /repurposed for business attraction and/or expansions. Special focus will be paid to clean technology development and/or green economy businesses. | Analyze current County assets and provide recommendations for how to utilize them | OEOCE maximizes climate-conscious stewardship of County resources; identifies instances of underutilization or opportunities for maximization; and increases the utility of County resources to the County itself, as well as the public and/or local businesses. | Ashton Allison + Amie Danielewicz | NA | Annual Plan Monitoring | On Track | OEOCE has made efforts to build an inventory of properties in conjunction with DLS staff. Researched what data is availble and how to find it. Waiting for DLS capacity to open up in Q1 2025 to move collaboration forward. Need to connect with FMD for properties outside UKC. | 2024-11-05 | The inventory register will exist, and include all relevant data columns. Equity: The percentage of analyzed County real property assets identified for potential repurposing that are located in institutionally underserved or economically disadvantaged communities. Equity: The percentage of County assets repurposed that are allocated to businesses owned by or employing individuals from institutionally underrepresented communities. Equity: The number of community forums or consultation sessions held with representatives from institutionally underserved communities to gather input on the use of County assets Climate: Clean Technology Opportunities Measure: Produce a report on clean technology opportunities in identified properties by Q3 2025. Climate: The percentage of County assets identified for potential repurposing that are specifically designated for clean technology development or green economy businesses. Climate: The number of new or existing businesses in the clean technology or green economy sectors attracted or expanded, or partnerships formed, as a result of the asset analysis. | Understanding available facilities for relevant purposes | Existence of inventory register when previously there was none. At least 3 properties identified for further analysis. | NA | No | 2025-01-31 | Re-convene team members to discuss roles & responsibilities in gathering data | 2025-08-31 | Finalized site inventory complete; socialized with ECO leadership
EXEC | OEOCE | Economic Opportunity - Business Retention & Expansion - Cascadia Ultra High-Speed Ground Transportation | Environment | Advance Cascadia High Speed Rail by developing funding allocation for remainder of High-Speed Rail funds. In partnership with UW Mobility Innovation Lab, develop Transportation 2050 Dashboard and predictive model. Sponsor Cascadia Local Elected Officials Summit and develop follow-up action plan to solicit local exploration of high speed rail. By Q1 2025, we will know if the summit is taking place, and will then determine whether to use funds if it happens, or reallocate if it is cancelled. | See Column E | OEOCE advances Cascadia High Speed Rail; uses the dashboard to make data-driven transportation decisions, and provides on-demand evidence of efficacy and impact | Ashton Allison | Working with community | Annual Plan Monitoring | On Track | OEOCE has committed to sponsor Cascadia Summit, if funds are secured. | 2024-11-05 | King County municipal government local matching amount that can be applied toward WSDOT high-speed rail funding from federal government. Follow-Up Action Plan Measure: Develop and implement a follow-up action plan for high-speed rail exploration, with at least two actionable steps identified and initiated by the end of Q4 2025. Equity: The percentage of summit participants representing institutionally underserved communities. Equity: The number of follow-up action plan recommendations specifically addressing equity and accessibility issues related to high-speed rail implementation. Equity: The percentage of local exploration activities (e.g., community meetings, surveys) included in the action plan that involve input from institutionally underrepresented communities. Climate: The number of summit participants or speakers who are experts in climate science or sustainability and contribute to discussions on high-speed rail's climate benefits. Climate: The percentage of action plan goals or metrics related to reducing carbon emissions and enhancing energy efficiency in the high-speed rail project. Climate: The percentage of summit sessions and discussions that specifically address climate impact and sustainability aspects related to high-speed rail implementation. | Match commitment is indicative of local support | TBD based on WSDOT communication | NA | No | 2025-03-31 | Notification of federal funding award, up to $200M | 2025-08-31 | Transportation Dashboard and Predictive Model | 2025-12-31 | KC Exec to moderate governors panel at Cascadia Summit, if funding is secured
EXEC | OEOCE | Economic Opportunity - Regional Business Attraction & Marketing - Key Industry Expansion | Environment | In 2025, in partnership with WA State Department of Commerce and Greater Seattle Partners, attract at least one new high-growth key industry business attraction/expansion project. The project will align with KC's equity, climate, and workforce values. (Top industry focus: Clean Technology/Green Economy and Film/Music Production; Key industries will also include: Advanced Manufacturing - Aerospace, Agriculture, Financial Services, Healthcare, Hospitality/Tourism, IT, Life Sciences, Maritime). Tribal Film Initiative TBD Statewide Video Game Developers Initiative TBD | TBD | OEOCE demonstrates that King County is attractive to businesses that align with County values, proving that values alignment is a viable and sustainable business practice. | Ashton Allison + Amie Danielewicz | Other - mitigate climate impact to frontline communities | Annual Plan Monitoring | Complete | Proposal about new initiatives from Greater Seattle Partners TBD. | 2024-11-05 | Alignment with business size constraint, and KC values. Number/percentage of new jobs created and existing jobs retained that pay median wage or above Equity: Percentage of attracted/expanded businesses that demonstrate a clear plan for equitable hiring and promotion practices. Equity: The distribution of business locations across the county, and the change in income levels for communities surrounding the new business locations. Equity: Investment in workforce training programs aimed at increasing skills for underserved populations. Climate: Number of new jobs created by the projects that are in climate-focused or green sectors. Climate: Percentage of attracted/expanded businesses that present a documented climate action and sustainability plan. Climate: Investment in workforce training programs focusing on green skills and climate-related competencies. | Ensure that business and equity goals are met | 1 aligned businesses attracted. Tribal Film Initiative and Statewide Video Game Initiative TBD. | NA | No | 2025-12-31 | Letter of Intent signed and projects moving forward. Name of business(es) TBD. | 2025-12-31 | Tribal Film Initiative, Statewide Video Game Initiative milestones TBD.
EXEC | OEOCE | Economic Opportunity - - Regional Business Attraction & Marketing -Executive’s Small Business Awards | Anti-Racism / Pro-Equity | Present the Executive's Small Business of the Year Awards | Streamline and professionalize the ESBYA experience by transitioning to organization by OEOCE's in-house live event planning experts | OEOCE provides meaningful recognition experience to standout small businesses, creates opportunity for business owners to network, generates media spotlights on King County's economic contributions, and drives business engagement between nominees and the public. | Ashton Allison | Prioritizing where needs are the greatest | Annual Plan Monitoring | Not Started | OEOCE is now the lead on this event, and has transitioned the project from Department of Executive Services. | 2024-11-05 | Businesseses/community members engaged, applications received, sponsors confirmed. Equity: Percentage of small businesses recognized or awarded that represent institutionally marginalized communities or have demonstrated strong equity practices. Equity: Implementation of accessibility features for the application and nomination processes, such as language support, accessible formats, and accommodations for disabilities. Equity: Percentage of marketing and outreach efforts aimed at reaching businesses from institutionally marginalized communities. Climate: Percentage of small businesses recognized or awarded that have demonstrated climate-friendly practices, such as energy efficiency, green job creation, or waste reduction. (Including but not limited to the Green/Sustainable category) | Measures overall engagement and participation | Goal: At least 250 attendees | 2024 event | No | 2025-02-07 | Schedule meeting with DES to debrief lessons learned and assure smooth transition | 2025-03-21 | Select event date (October 2025 TBD) and confirm venue | 2025-10-17 | Award luncheon and ceremony event takes place
EXEC | OEOCE | Economic Opportunity - Regional Business Attraction & Marketing -FIFA World Cup 2026 Activation | Anti-Racism / Pro-Equity, Climate | Through the Community Business Connector program, support business owners to leverage the opportunity for FIFA World Cup tourism in 2026. | TBD | OEOCE ensures that King County businesses, nonprofits, workers, and residents benefit from the unique, rare investment and publicity opportunity presented by FIFA World Cup 2026. | Ashton Allison, Kate Becker | Working with community | Annual Plan Monitoring | Not Started | Initial discussions have begun, awaiting funding notice | 2024-11-05 | TBD | TBD | TBD | NA | No | 2026-08-31 | TBD
EXEC | OEOCE | Economic Opportunity - Workforce Development - Flexible Funding Development | Anti-Racism / Pro-Equity | Increase flexible funding by $15 million (e.g. state, federal, private, and philanthropic funding) to support the Workforce Devevelopment Council's backbone organization function. | Identify and apply for funding opportunities, with increased emphasis on philanthropic and foundation funding, and funding for equity initiatives | OEOCE increases equitable workforce opportunities | Ashton Allison | Prioritizing where needs are the greatest | Annual Plan Monitoring | On Track | OEOCE supported the WDC's applications to Employment Security and Dept. of Commerce. As of 11/05/24, this has resulted in receiving approximately $10.75M, with an additional $700k in pending applications, primarily from State/Federal sources. OEOCE to identify additional flexible funding sources in 2025, with emphasis on philanthropic funders. | 2024-11-05 | New non-WIOA funding generated. Equity: Percentage of identified funding sources that prioritize or include specific provisions for equity and inclusion in their criteria. Equity: Comprehensive documentation of all identified equity-focused funding opportunities and their alignment with organizational goals. Equity: Percentage of funders evaluated for their equity criteria and inclusiveness in their funding guidelines. Climate: Percentage of identified funding sources that prioritize climate action or sustainability in their criteria. Climate: Comprehensive documentation of all identified climate-focused funding opportunities and their alignment with organizational goals. Climate: Percentage of funders evaluated for their climate action criteria and sustainability focus in their funding guidelines. | Non-WIOA (Workforce Innovation and Opportunity Act) funding offers more flexibility to fund innovative and equitable workforce training/placement initiatives. | $15m or more external funding raised | NA | No | 2025-03-31 | Schedule working meeting with WDC leadership to whiteboard flexible funding sources and receive update on applications | 2025-06-30 | Follow up on tracking additional flexible funding sources. | 2025-12-31 | $15M of flexible funding confirmed
EXEC | OEOCE | Economic Opportunity - Workforce Development - King County Economic Opportunity Coalition | Anti-Racism / Pro-Equity | Economic Opportunity Coalition to develop stronger linkages with economic/workforce development programs/functions across the Executive Branch. Host monthly large group update meetings and bi-monthly working group meetings to develop closer working relationships with program leads. | All-Member gatherings and working groups | OEOCE develops stronger linkages with economic/workforce development programs/functions across the Executive Branch. | Ashton Allison | Prioritizing where needs are the greatest | Annual Plan Monitoring | On Track | EOC meetings are enthusiastically attended, increasing from quarterly to monthly all group meetings. | 2024-11-05 | Task force and working group meetings. Value Provided to Partner Organizations Document the satisfaction of partner organizations through a participant feedback survey showing at least 80% satisfaction. Percentage increase in the capacity (e.g. new programs launched) or geographic reach of partner organizations attributable to the support provided. Percentage of partner organizations that meet or exceed their predefined goals or outcomes. Equity: Percentage of coalition initiatives or recommendations that explicitly address equity or evaluate their effects on underserved populations. Equity: Number of reports on the equity outcomes of coalition initiatives and linkages with economic/workforce development programs. Climate: Percentage of working group members or organizations that focus on or have a track record in climate action and sustainability. Climate: Percentage of coalition objectives that explicitly address climate action and sustainability in economic and workforce development programs. Climate: Number of reports on the climate outcomes of coalition initiatives and linkages with economic/workforce development programs. | Measures touch points to exchange info and share progress against strategies | 10+ meetings | NA | No | 2024-06-30 | Host 1:1s with all program leads | 2024-12-31 | Quarterly extended sessions include external guest speakers from industry and community | 2024-12-31 | Host all monthly EOC meetings
EXEC | OEOCE | Economic Opportunity - Workforce Development - Partnerships | Anti-Racism / Pro-Equity | Convene Unincorporated King County and South King County municipal partners to discuss common workforce opportunities/challenges at least three times per year. Meet onsite in East King County and North King County. | All-Member gatherings | OEOCE identifies and addresses common workforce opportunities and challenges; creates alignment betwen municipalities and UKC. | Ashton Allison | Prioritizing where needs are the greatest | Annual Plan Monitoring | Complete | All South KC municipal economic development partners have been engaged. All 1:1 meetings have taken place. | 2024-11-05 | Number of meetings with municipal partners and meeting outcomes Business Licenses in Unincorporated King County Total number of new business licenses issued in unincorporated areas. Percentage increase in the number of licensed businesses in unincorporated areas over a specific period. Value Provided to Partner Organizations Percentage increase in the capacity (e.g. new programs launched) or geographic reach of partner organizations attributable to the support provided Equity: Percentage of meeting agenda items (e.g. discussions or presentations) specifically addressing equity and inclusion issues related to workforce opportunities and challenges. Equity: Provision of accessibility features and inclusive practices for meetings, such as translation services and accommodations for disabilities. Climate: Percentage of meeting agenda items (e.g. discussions or presentations) specifically addressing climate-related workforce opportunities and challenges. Climate: Percentage of meeting participants who are experts or representatives from organizations specializing in climate action or sustainability. | Municipal partner engagement is a performance metric in the County/City joint letter to WDC | 3 convenings take place in 2025 | NA | No | 2025-04-30 | Host first convening | 2025-08-31 | Host second convening | 2025-12-31 | Host third convening
Note on N12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: From KCDataReport4Q2023.Withchart.xlsx: 707 businesses reported 557 (79%) WMBE owned 85 (12%) none of the above 65 (9%) declined to respond

## OEOCE Annual Plan 2023 Q4
Department: |  | OEOCE | [13 empty] | Milestones
Dept | Division Name | Priority Initiative/ Project | Primary Executive Priority Linkage, if any | Project Objective | Who is Responsible | ERSJ Alignment | Anticipated Tier 5 Monitoring | Indicator (Not started -G-R-Done) | Current Status (comments) | Date Updated | Key performance measure | Why is the measure important to monitor? | Numerical goal for measure | Most recent data point | Countywide internal project? (Y/N) | M1 Date | M1 | M2 date |  | M3 date | M3 | M4 date | M4 | M5 date | M5 | M6 date | M6
EXEC | OEOCE | Establish (Operationailze) OEOCE | Best-Run Government | While early in its organizational maturity, operationalize OEOCE: implement formalized processes, consistent communication, collaboration, control/monitoring, documentation, and reporting. This should ensure the strategic goals, mission, and vision drive action. Operations optimization and continuous improvement will be ongoing, permanent work for the Office, but the "Operationalize" project will be considered complete in 2024 if OEOCE achieves LMM level 2 across the scoring model. NOTE: Across this entire Annual Plan, identifying and establishing performance measures, metrics, and reporting for OEOCE as a whole, and for individual priorities/initiatives, is a large part of the 2024 Operationalize workload. It is of utmost importance to develop these with ERSJ centered and BRG values embedded, which requires a time investment to incorporate thoughtful community and stakeholder feedback. Hence, this information is not yet fully specified in this document as of 12/15/2023. | Susano Surface | Enhancing King County’s capacity to implement pro-equity/anti-racism work | Annual Plan Monitoring | Complete | In Progress | 2023-12-15 | OEOCE will score at LMM Level 2 in at least 3 focus areas. KPMs will be confirmed after the first assessment is done. ERSJ KPMs are embedded within LMM scoring. | Ensure OEOCE's alignment with BRG Executive Priority | LMM Level 2 | NA - LMM Scoring to start in 2024. Department orientation to LMM in October 2023. | No | 2023-10-30 | LMM Orientation | 2024-01-16 | LMM Scoring & Analysis Q1: Initial Baseline | 2024-04-12 | LMM Scoring & Analysis Q2: Pre-Annual Planning | 2024-07-12 | LMM Scoring & Analysis Q3: Pre-Annual Planning | 2024-08-11 | LMM Scoring & Analysis Q4: Reflection of 2024 Status and Progress | 2024-10-18 | First Draft of 2024 Annual Plan due ✅
EXEC | OEOCE | Establish (Operationailze) OEOCE- Communications | Best-Run Government | Expand and amplify communications and external relations, increasing engagement with OEOCE's social media, newsletters, websites, publicity, and earned media by 30% in 2024. | Kate Becker | Enhancing King County’s capacity to implement pro-equity/anti-racism work | Annual Plan Monitoring | On Track | Creative Economy e-newsletter is shared regularly. KingCounty.gov website has been refreshed. FAQ in process of compliation. Social Media and kingcountycreative.com focus in 2024. | 2023-12-15 | Open/click rate for e-newsletter, number of likes/comments/reposts on social media, qualitative feedback via email or other direct engagement, number of page views and clicks on websites, reduction of individual email inquiries and staff response times after FAQ is published, reduction of staff time in responding individually to repeated inquiries, number of earned media articles pertaining to OEOCE, and more. ERSJ KPMs to be identified and implemented in 2024. | Understand how community members and relevant industries are learning about OEOCE's programs/projects. Optimize information. WCAG/W3C compliance on web and social. | Maintain e-news open rate. For others, 30% increase from 2023 numbers in Column O | As of 12/15/2023, in the past 12 months: Creative Economy E-newsletter - 60% open rate. kingcountycreative.com - 14,750 page views. OEOCE kingcounty.gov - 593 views (as of 10/20/2023) @kingcountycreative instagram - 1,162 followers. To begin monintoring in 2024: # of earned media articles pertaining to OEOCE. | No | 2024-03-31 | Designate communications & social media lead and create content plan by Q1 2024. Publish FAQ/Autoresponses by Q1 2024. | 414367 | Create plans and collateral for marketing, social media, publicity, and branding by Q2 2024. Refresh kingcountycreative.com by Q2 2024. | 2024-09-30 | Launch Economic Opportunity newsletter by Q3 2024.
EXEC | OEOCE | Creative Economy - Film - Harbor Island Studios - Capital Improvements | Environment | Complete 2024 Harbor Island Studios capital improvements (set build mill; roof replacement) between April-July 2024. | Nate Brend (FMD) | Other - KC values-based pricing scheme incentivizes hiring of casts and crews that have historically & institutionally been underresourced. | Annual Plan Monitoring | On Track | Construction is scheduled to begin no earlier than April 2024. FMD and SWD coordinating to have simultaneous mill construction and roof replacement to minimize impact on filming. | 2023-12-15 | 1. Completion of mill construction - the mill will exist where there previously was none. 2. Completion of roof replacement - roof will no longer leak and will be more soundproof. 3. All construction completed on time and on budget. | Ensure the usefulness of capital improvements, which impacts community's ability to access and benefit from HIS. | Dates of completion (6/15/2024), construction budget (FMD), noise reduction difference in decibels. | NA | No | 2023-09-15 | FMD Harbor Island Studios Facility Manager hired | 2023-10-15 | Sound insulation installed in Stage 2 | 2024-03-01 | Major feature film landed and work completed | 2024-05-30 | Mill constructed and roof replaced | 2024-06-15 | Harbor Island Studios Reopens | 2024-07-01 | Harbor Island Studios is activated at capacity, with minimal un-used time between productions
EXEC | OEOCE | Creative Economy - Film - Harbor Island Studios - Business Development | Anti-Racism / Pro-Equity | Generate new film-industry business & jobs at Harbor Island Studios in 2024. 2024-2025 will be pilot years as OEOCE manages and monitors HIS workflow, capital improvements, and staffing/facility capacity. OEOCE will explore alternative business models for Harbor Island Studios (public/private, etc.) | Kate Becker | Enhancing King County’s capacity to implement pro-equity/anti-racism work | Annual Plan Monitoring | On Track | Films, episodics, commercials, and other productions have commenced and continue to take place in HIS. In 2024, mill/roof construction will impact the number of productions. | 2023-12-15 | Documenting number of inquiries received, number of tours conducted, number of completed productions, budget earned income (total, and also in relation to cost of operating and staffing HIS), production spend with King County small businesses, number of living wage jobs created per production and total per year, how many production learning opportunities are offered, data tracking the percentage of jobs created for self-identified demographic categories per production and total per year, and other categories as relevant. ERSJ KPMs to be identified and implemented in 2024. | Baseline the productivity of HIS, so its operations can be understood and optimized | To be determined in 2024, following the collection of data in categories listed in Column L | Pilot project history and inquiry database | No | 2023-11-15 | Pilot project history summary complete | 2023-12-15 | Systems developed to capture data in 2024-2025 (possibly FilmApp) | 2024-01-31 | Analyze first month of data capture and system efficacy | 2024-03-31 | Update Harbor Island Studios business plan including future model research | 2024-06-30 | Six month data collection complete | 2024-12-31 | One year data complete
EXEC | OEOCE | Creative Economy - Film | Anti-Racism / Pro-Equity | Film Permitting process to be streamlined and published to website by January 2024. Film Ordinance to be drafted in February 2024, with intent to pass council in April 2024. Film Ecosystem Study, in partnership with City of Seattle, to be completed in June 2024. Continue supporting Executive Film Advisory Board (EFAB) as it transitions to ongoing advisory role now that HIS has opened. | Kate Becker | Working with community | Annual Plan Monitoring | On Track | Film Ecosystem Study was on hiatus due to COVID-19 emergency and City of Seattle staffing changes; our collaborator is now ready to finalize. Dates and timeline for Ordinance and Permitting TBD as part of program work in 2024. | 2023-12-15 | Film Ordinance draft will exist, and ideally be passed. Interdepartmental film liaison collaobration process will be operationalized. Work w/ FMD will be complete and film permitting process will be decided and posted publicly. Film Ecosystem Study will be published. ERSJ KPMs to be identified and implemented in 2024. | Ordinance & permit process updates will make filming in KC more attractive and accessible to industry. Study will provide clarity about state of the field and how issues can be addressed. | See Column L | EFAB meets monthly, Excel sheet tracks film industry inquiries, multiple KC departments issue and track film permits | No | 2023-11-30 | Interdepartmental film liaison process for collaboration and data tracking developed (w/ FMD, RES, DNRP, DLS & Metro); film permitting process work underway | 2023-12-31 | Film Ecosystem Study data collection strategy ready to launch | 2023-12-31 | Film permitting process ready to launch and promote on 1/2/2024 | 2024-01-31 | Film ordinance drafted following consultation w internal (EFAB, FMD, RES, DNRP, DLS, & Metro) and external (film industry) collaborators | 2024-04-30 | External film ecosystem study sessions and interviews complete | 2024-06-30 | Film Ecosystem Study complete and published
EXEC | OEOCE | Creative Economy - Music | Anti-Racism / Pro-Equity | Understand the scale of King County's music economy by: producing a Music Ecosystem Study to be completed by June 2024, forming an Innovation Cluster task cohort by January 2024, and analyzing/interpreting WA statewide data pertaining to the Cascadia Music Corridor by July 2024. With this information OEOCE will be able to strategize how best to support King County's music industry. | Amie Danielewicz + Kate Becker | Working with community | Annual Plan Monitoring | On Track | The scale of King County's music economy is unknown. In a 2019 Seattle Creative Economy Study, musicians were the lowest paid workers in our creative economy. Data and research are needed to understand the scale of our music ecosystem to inform policy decisions. Proposal currently with UW Evans School to have grad students conduct music ecosystem research Jan-April 2024. Innovation Cluster work and Cascadia Music Corridor work continues. | 2023-12-15 | UW Evans School contract secured and student research completed. Washington Music Ecosystem Study completed. Innovation Cluster work with WA Dept of Commerce will have music ecosystem cohort established and working together. Cascadia Music Corridor will compile and share Cascadia Music Summit learnings. ERSJ KPMs to be identified and implemented in 2024. | Statewide collaboration (relationship-building as well as results for music sector) and ensuring a meaningful educational opoprtunity for student consultants | Publication of Music study, formation of Innovation Cluster cohort, publication of Cascadia Music Summit findings. | 11/7/23 acceptance of proposal to engage UW Evans School for grad student research assistance submitted 8/31/23 in partnership with WA Dept of Commerce Creative Economy Lead. | No | 2023-11-12 | Acceptance by UW Evans School on 11/7/23; Music Ecosystem chosen by WA Dept of Commerce for one year engagement in ICAP (Innovation Cluster Accelerator Program) | 2024-01-15 | Statewide music ecosystem data collection and research begins | 2024-06-30 | Washington Music Ecosystem Study complete | 2024-09-30 | WA Dept of Commerce ICAP (Innovation Cluster Accelerator Program) related music ecosystem stakeholder group meeting regularly and working together | 2024-12-31 | Cascadia Music Corridor work continues in partnership with OR, ID & AK music industry leaders ✅
EXEC | OEOCE | Creative Economy - Festivals/Events/Nightlife | Anti-Racism / Pro-Equity | Collaborate with WFEA, WANMA, Cultural Leaders Roundtable, NITECAP, etc to provide technical assistance and strategic support; Partner to produce the Cascadia Music Summit and The Summit | Kate Becker/Amie Danielewicz | Working with community | Annual Plan Monitoring | Complete | OEOCE continues to participate in WFEA and WANMA. 2024 regional film and music event schedule and participation plan TBD. | 2023-12-15 | Participation in the 12/7 & 12/8/23 Cascadia Music Summit in Boise, ID. Execution of 2024 Cascadia Music Summit in King County. ERSJ KPMs to be identified and implemented in 2024. | Ongoing support of and influence in key creative industries | See Column L | NA | No | 2023-12-08 | Announcement of Cascadia Music Summit in King County in 2024; commitment to Creative Economy Career Day on 2/9/24 | 2024-01-02 | Monthly meeting schedule with all groups is defined and calendared | 2024-02-09 | Execution of Creative Economy Career Day at Seattle Center on 2/9/2024 | 2024-06-01 | Cascadia Music Summit team identified and planning underway ✅
EXEC | OEOCE | Creative Economy - Hospitality/Tourism | Anti-Racism / Pro-Equity | Ongoing engagement with Hospitality and Tourism partners, locally, nationally, and internationally including the annual Cloudbreak Music Festival | Kate Becker/Amie Danielewicz | Working with community | Annual Plan Monitoring | Complete | Continued engagement with tourism (Visit Seattle, Southside Regional Tourism Agency, SnoValley Chamber, etc), WA Restaurant Association, national colleagues, and internal departments | 2023-12-15 | Number of site visits to tourism locations and events, number of presentations to hospitality and tourism groups, number of collaborations. ERSJ KPMs to be identified and implemented in 2024. | Hospitality and tourism are key economic drivers for our region | # of presentations, # of partnerships, # of trainings, # of convenings and collaborations | NA | No | 2023-11-21 | Successfully complete Cloudbreak 2023; partner with Visit Seattle, City of Seattle, 71 downtown hotels, 33 independent music venues and >150 musicians and bands | 2024-01-15 | Analysis of Cloudbreak Music Festival 2023; should we do it again? | 2024-02-15 | Decision is made regarding Cloudbreak 2024 and funding is secured (lodging tax) | 2024-03-01 | Launch of planning process for Cloudbreak 2024 ✅
EXEC | OEOCE | Creative Economy - Eastside Creative Districts | Anti-Racism / Pro-Equity | Support Councilmember Perry and ArtsWA in the development of creative districts throughout King County District 3 | Kate Becker | Working with community | Annual Plan Monitoring | On Track | Monthly group meetings + individual meetings w/ District 3 city leaders | 2023-12-15 | Work with District 3 city leads to strategize their respective creative district initiatives. ERSJ KPMs to be identified and implemented in 2024. | Each District 3 city will have a different creative district plan based on thier strengths | Minimum of 3 (out of 13) District 3 cities that initiative creative district strategies in 2024 | Six months of participation in monthly group meetings + numerous individual city consultations | No | 2024-06-30 | 1st of three creative districts is launched with branding and public campaign (likely Carnation, possibly North Bend) | 2024-09-30 | 2nd of three creative districts is launched with branding and public campaign | 2024-12-31 | 3rd of three creative districts is launched with branding and public campaign
EXEC | OEOCE | Economic Opportunity - Business Retention & Expansion - ADO | Anti-Racism / Pro-Equity | Increase countywide small business assistance capacity at least by two ADO Community Business Connector organizations in 2024, with a focus on UKC, South King County, and neighborhoods where the self-sufficiency standard are lowest. | Amie Danielewicz | Working with community | Annual Plan Monitoring | Complete | Currently fund seven ADO Business Connector organizations representing six geographic hubs across the county, with plans to add three more. Current CLFR funding will be expended by the end of 2023. Port of Seattle & City of Seattle are providing follow-on funding to sustain the program. | 2023-12-15 | 70% (175 out of 250) of all small businesses receiving assistance will be historically underrepresented and under-resourced. (As measured by the King County SERI index). | Alignment with racial equity & BRG values; documenting amount of assistance provided and who is receiving it | Two business connector organizations are contracted with the ADO | NA | No | 2024-03-31 | RFP Sent out by ADO | 2024-07-31 | Two business connector orgs are contracted with ADO ✅
EXEC | OEOCE | Economic Opportunity - Business Retention & Expansion - Aerospace | Environment | Expand Aerospace Alliance beyond King County boundaries to be a multi-county initiative. Transition primary convening partner to Greater Seattle Partners. Host two additional study briefings by Q1 2024, with the goals of educating legislators, educators, and private industry about the importance of the aerospace industry and retaining the legacy aerospace manufacturing footprint, while fostering growth in the new space sector. | Ashton Allison | Working with community | Annual Plan Monitoring | Complete | Two briefings have been conducted: one for for legislators & one for STEM/Education. | 2023-12-15 | Two briefings will have taken place in 2024. Measurements may include - number of engagements/questions by attendees, inquiries from interested elected officials. ERSJ KPMs to be identified and implemented in 2024. | Awareness of current status,, stakeholder engagement & future opportunity in the sector | See Column L | NA | No | 2024-03-31 | Host two briefing events: STEM/Educator and private industry | 2024-06-30 | Determine the desired future state of the Aerospace Alliance | 2024-09-03 | Identify lead organization to convene Aerospace Alliance | 2024-12-31 | Formallize and socialize new Aerospace Alliance ✅
EXEC | OEOCE | Economic Opportunity - Business Retention & Expansion - New and Existing Employers | Environment | New and Existing Employers: Conduct an analysis of current County assets, especially real property, that could potentially be utilzied /repurposed for business attraction and/or expansions. Special focus will be paid to clean technology development and/or green economy businesses. | Ashton Allison + Amie Danielewicz | NA | Annual Plan Monitoring | On Track | OEOCE has made efforts to build an inventory of properties in conjunction with DLS staff. The deliverable is pending and will be re-visited when vacant DLS Economic Manager staffing/workload is resolved. Currently working with Anjilee Dodge & Michael Morales. Need to connect with FMD for properties outside UKC. | 2023-12-15 | The inventory register will exist, and include all relevant data columns. ERSJ KPMs to be identified and implemented in 2024. | Understanding available facilities for relevant purposes | Existence of inventory register when previously there was none. At least 3 properties identified for further analysis. | NA | No | 2024-01-31 | Convene team members to discuss roles & responsibilities in gathering data | 2024-03-31 | First draft of site inventory complete | 2024-04-30 | Finalized site inventory complete; socialized with ECO leadership
EXEC | OEOCE | Economic Opportunity - Business Retention & Expansion - Cascadia Summit | Environment | Sponsor Cascadia Local Elected Officials Summit and develop follow-up action plan to solicit local exploration high speed rail implementation by Q4 2024. | Ashton Allison | Working with community | Annual Plan Monitoring | Complete | OEOCE has committed to sponsor Cascadia Summit. | 2023-12-15 | King County municipal government local matching amount that can be applied toward WSDOT high-speed rail funding from federal government. ERSJ KPMs to be identified and implemented in 2024. | Match commitment is indicative of local support | TBD based on WSDOT communication | NA | No | 2023-11-15 | KC Exec to moderate governors panel at Cascadia Summit | 2023-12-31 | Hear back about WSDOT funding award | 2024-03-01 | Finalize local match needed from KC local governments ✅
EXEC | OEOCE | Economic Opportunity - Regional Business Attraction & Marketing - Key Industry Expansion | Environment | In 2024, in partnership with WA State Department of Commerce and Greater Seattle Partners, attract two new high-growth key industry business attraction/expansion projects. These two projects will align with KC's equity, climate, and workforce values. (Top industry focus: Clean Technology/Green Economy and Film/Music Production; Key industries will also include: Advanced Manufacturing - Aerospace, Agriculture, Financial Services, Healthcare, Hospitality/Tourism, IT, Life Sciences, Maritime). | Ashton Allison + Amie Danielewicz | Other - mitigate climate impact to frontline communities | Annual Plan Monitoring | Complete | Constant circulation of leads generated between WA State Dept of Commerce and Greater Seattle Partners, which are in various states of confidential vetting/decision-making. | 2023-12-15 | Alignment with business size constraint, and KC values. ERSJ KPMs to be identified and implemented in 2024. | Will demonstrate that KC is attractive not only for business in general, but businesses that align with County values, proving that values alignment is a viable and sustainable business practice. | 2 aligned businesses attracted | NA | No | 2024-12-31 | 2 Letters of Intent signed ✅
EXEC | OEOCE | Economic Opportunity - Workforce Development - Flexible Funding | Anti-Racism / Pro-Equity | Increase flexible funding by $15 million (e.g. state, federal, private, and philanthropic funding) to support the Workforce Devevelopment Council's backbone organization function. | Ashton Allison | Prioritizing where needs are the greatest | Annual Plan Monitoring | Complete | OEOCE supported the WDC's applications to Employment Security and Dept. of Commerce. This has resulted in approximately $10.3M in awards confirmed as of 12/15/23, primarily from State/Federal sources. Awaiting notification about additional $9.3M in applications. OEOCE to identify additional flexible funding sources in 2024, with emphasis on philanthropic funders. | 2023-12-15 | New non-WIOA funding generated. ERSJ KPMs to be identified and implemented in 2024. | Non-WIOA (Workforce Innovation and Opportunity Act) funding offers more flexibility to fund innovative and equitable workforce training/placement initiatives. | $15m or more external funding raised | NA | No | 2024-12-31 | Notifications of grant applications acceptance or rejection | 2024-03-31 | Schedule working meeting with WDC leadership to white board flexible funding sources and receive update on applications ✅
EXEC | OEOCE | Economic Opportunity - Workforce Development - Economic Opportunity Task Force | Anti-Racism / Pro-Equity | Launch Economic Opportunity Task Force to develop stronger linkages with economic/workforce development programs/functions across the Executive Branch. Host quarterly large group update meetings and bi-monthly working group meetings to develop closer working relationships with program leads. | Ashton Allison | Prioritizing where needs are the greatest | Annual Plan Monitoring | Complete | Launched EOTF in September 2023. | 2023-12-15 | Task force and working group meetings. ERSJ KPMs to be identified and implemented in 2024. | Measures touch points to exchange info and share progress against strategies | 8 meetings | NA | No | 2024-03-31 | Host one OETF meeting and one work group | 2024-06-30 | Host 1:1s with all program leads that correspond with Exec priorities | 2024-11-15 | Host two additional OETF meetings and two working groups ✅
EXEC | OEOCE | Economic Opportunity - Workforce Development - Municipal Partners | Anti-Racism / Pro-Equity | Convene Unincorporated King County and South King County municipal partners to discuss common workforce opportunities/challenges at least twice per year. | Ashton Allison | Prioritizing where needs are the greatest | Annual Plan Monitoring | Complete | All South KC municipal economic development partners have been engaged & 1:1 meetings are being scheduled. | 2023-12-15 | Number of meetings with municipal partners and meeting outcomes ERSJ KPMs to be identified and implemented in 2024. | Municipal partner engagement is a performance metric in the County/City joint letter to WDC | 2 convenings take place in 2024 | NA | No | 2024-02-28 | Host first convening | 2024-06-30 | Host second convening ✅
EXEC | OEOCE | Economic Opportunity - Small Business Awards | Anti-Racism / Pro-Equity | Rethink and relaunch the Executive's Small Business of the Year Awards in partnership with the Dept of Executive Services. Consider partnering with WDC to recognize employers for innovative workforce practices. Brainstorm additional competitions/grant opportunities for priority sector promotion/recognition. | Ashton Allison | Prioritizing where needs are the greatest | Annual Plan Monitoring | Complete | Initiatied request with Tom K. in DES/FBOD, who indicated the event could be planned for Fall 2024 | 2023-12-15 | Businesseses/community members engaged, applications received, sponsors confirmed ERSJ KPMs to be identified and implemented in 2024. | Measures overall engagement and participation | Will establish with DES in Q1 2024 | 2019 event | No | 2024-02-01 | Schedule meeting with DES to plan next steps ✅

## Div1 (hidden)
Department: |  | #REF! | [13 empty] | Milestones
| Division Name | Priority Initiative/ Project | Primary Executive Priority Linkage, if any | Project Objective | Who is Responsible | ESJ Alignment | Anticipated Tier 5 Monitoring | Indicator (Not started -G-R-Done) | Current Status (comments) | Date Updated | Key performance measure | Why is the measure important to monitor? | Numerical goal for measure | Most recent data point | Countywide internal project? (Y/N) | M1 Date | M1 | M2 date | M2 | M3 date | M3 | M4 date | M4 | M5 date | M5 | M6 date | M6
#REF! | Div 1
#REF! | Div 1
#REF! | Div 1
#REF! | Div 1
#REF! | Div 1
#REF! | Div 1
#REF! | Div 1
#REF! | Div 1
#REF! | Div 1

## Div2 (hidden)
Department: |  | #REF! | [13 empty] | Milestones
Dept | Division Name | Priority Initiative/ Project | Primary Executive Priority Linkage, if any | Project Objective | Who is Responsible | ESJ Alignment | Anticipated Tier 5 Monitoring | Indicator (Not started -G-R-Done) | Current Status (comments) | Date Updated | Key performance measure | Why is the measure important to monitor? | Numerical goal for measure | Most recent data point | Countywide internal project? (Y/N) | M1 Date | M1 | M2 date | M2 | M3 date | M3 | M4 date | M4 | M5 date | M5 | M6 date | M6
#REF! | Div 2
#REF! | Div 2
#REF! | Div 2
#REF! | Div 2
#REF! | Div 2
#REF! | Div 2
#REF! | Div 2
#REF! | Div 2
#REF! | Div 2

## Div3 (hidden)
Department: |  | #REF! | [13 empty] | Milestones
Dept | Division Name | Priority Initiative/ Project | Primary Executive Priority Linkage, if any | Project Objective | Who is Responsible | ESJ Alignment | Anticipated Tier 5 Monitoring | Indicator (Not started -G-R-Done) | Current Status (comments) | Date Updated | Key performance measure | Why is the measure important to monitor? | Numerical goal for measure | Most recent data point | Countywide internal project? (Y/N) | M1 Date | M1 | M2 date | M2 | M3 date | M3 | M4 date | M4 | M5 date | M5 | M6 date | M6
#REF! | Div 3
#REF! | Div 3
#REF! | Div 3
#REF! | Div 3
#REF! | Div 3
#REF! | Div 3
#REF! | Div 3
#REF! | Div 3
#REF! | Div 3

## Div4 (hidden)
Department: |  | #REF! | [13 empty] | Milestones
Dept | Division Name | Priority Initiative/ Project | Primary Executive Priority Linkage, if any | Project Objective | Who is Responsible | ESJ Alignment | Anticipated Tier 5 Monitoring | Indicator (Not started -G-R-Done) | Current Status (comments) | Date Updated | Key performance measure | Why is the measure important to monitor? | Numerical goal for measure | Most recent data point | Countywide internal project? (Y/N) | M1 Date | M1 | M2 date | M2 | M3 date | M3 | M4 date | M4 | M5 date | M5 | M6 date | M6
#REF! | Div 4
#REF! | Div 4
#REF! | Div 4
#REF! | Div 4
#REF! | Div 4
#REF! | Div 4
#REF! | Div 4
#REF! | Div 4
#REF! | Div 4

## ListRef
ESJ Alignment | Tier 5 Monitoring | Executive Priorities | Status + Detail | Status | Status + Detail (Formatted | Countywide Project | Column1
Prioritizing where needs are the greatest | Operational Review | Best-Run Government | 0 | Not Started | Not Started | Yes | Not Started On Track | Rating
Working with community | Annual Plan Monitoring | Anti-Racism / Pro-Equity | 1 | On-Track | On Track | No | On Track On Track | Not Started | Not Started
Transforming the legal system | Financial Monitoring | Environment | 2 | At Risk | At Risk |  | At Risk On Track | On-Track | On-Track
Enhancing King County’s capacity to implement pro-equity/anti-racism work | Investment Monitoring | Affordable Housing & Homelessness | 3 | Complete | Complete |  | Complete On Track | At Risk | At Risk
Other (Please explain in comments) | Executive Priority Scorecard Update | Legal System reform |  |  |  |  | On Track | Complete | Complete
NA | Other (Please explain in comments) | Investing In You |  |  |  |  | On Track
| IIY/People Strategy Monitoring with Whitney Abrams | NA
NA