## STAFF REPORT

| Agenda Item: | 9 | Name: | Mike Reed |
| --- | --- | --- | --- |
| Proposed No.: | 2017-B0213 | Date: | November 1, 2017 |

SUBJECT

Briefing on King County Combined Sewer Overflow (“CSO”) project status and the Joint Ship Canal Water Quality Project

SUMMARY

Pursuant to Ordinance 18313, King County and the City of Seattle are participating in a partnership to design, construct and operate the Joint Ship Canal Water Quality Project.  This project responds to respective consent decrees signed by each of the parties with state and federal officials, requiring control of Combined Sewer Overflows that discharge untreated wastewater and stormwater flows into regional waters.  This project will control CSO discharges into the Lake Washington Ship Canal from CSO outfalls owned by each of the parties.  The semiannual report required by Ordinance 18313 has been received; that report, as well as budget documents submitted by Seattle Public Utilities to the Seattle City Council, indicate projected costs that are higher than originally anticipated.  Today’s briefing will address the status of the Joint Ship Canal project as part of the broader combined sewer overflow control process.

BACKGROUND

The City of Seattle and King County are undertaking the development and funding of the Joint Ship Canal Water Quality Project, intended to control untreated wastewater/stormwater overflows to the Lake Washington Ship Canal.  The project was authorized through a Joint Project Agreement (“JPA”) approved by the King County Council in June 2106 (Ordinance 18313); Seattle City Council approved the JPA in December 2015.

This Joint Ship Canal Water Quality Project is part of the county’s larger undertaking to control overflows from the combined stormwater/wastewater collection system that serves parts of Seattle, as an element of the larger regional wastewater system.  In 2013, King County signed a Consent Decree with the federal Environmental Protection Agency and Department of Justice and the state Department of Ecology, committing to controlling 14 remaining uncontrolled county-owned overflow discharge sites.  The City of Seattle has also signed a Consent Decree for the control of discharge sites owned by the City.  The goal of the Consent Decree is to ensure that overflows that occur at the County’s CSO outfalls are limited to no more than once per year based on a rolling 20-year average, and that the effluent discharged from CSO control treatment facilities meets defined standards.

The Joint Project Agreement for the Ship Canal Water Quality Project defines the roles of the County and the City in the execution and management of the project, and specifies the funding for planning, design, construction, maintenance, operation, repair, replacement alteration and improvement of the facility.  The JPA provides that:

- Seattle Public Utilities will design, construct, own and manage the project

- The project will address combined sewer discharges from six overflow locations, including four Seattle locations and two King County locations

Seattle Outfalls

- Fremont (Outfall 174): 1.06 MG

- Wallingford (Outfall 147): 2.15 MG

- Ballard (Outfall 152): 5.38 MG

- Ballard (Outfall 150/151): 0.62 MG

King County Outfalls

- 3rd Avenue West (DSN008): 4.18 MG

- 11th Avenue Northwest (DSN004): 1.85 MG

- The project will include a storage tunnel with a minimum 14-foot interior diameter, approximately 2.7 miles long, generally routed in the street right-of-way along the north side of the Ship Canal.

- The project capital costs will be shared between the parties.  SPU will pay for portions of the project that solely relate to its delivery of influent to the storage facility. Otherwise, most costs of the facility will be split, with Seattle paying 65 percent and King County 35 percent of the costs.  Estimates for total project costs included in the Joint Project Agreement were $423 million at the time of approval of the JPA.  King County’s share of the costs—noting that some costs are exclusive to Seattle—were estimated at $134 million at the time of JPA approval.

- Operations and maintenance costs are based on the same proportional responsibility, with Seattle paying 65% of operations/maintenance costs, and King County paying 35%.

- Project changes would be the responsibility of a Project Review and Change Management Committee (“PRCMC”), composed of senior management from each agency.

Semiannual Report—Ship Canal Water Quality Project

King County Ordinance 18313, which authorized the execution of the Joint Project Agreement, required the submittal of semiannual project status reports, summarizing

- budget status and cash flow;

- key upcoming activities;

- major project milestones and project status; and

- potential uses of contingency and management reserve.

In July, 2017, the Executive transmitted the second semiannual report.  That report included both a summary of changes that have been approved by the Project Review and Change Management Committee, and changes that have been proposed.  Of particular note are potential changes to the size of the storage tunnel.  As described earlier, the Joint Project Agreement approved in 2016 assumed a storage tunnel with a minimum inside diameter of fourteen feet.  The Semiannual Update references the potential for a significantly enlarged storage tunnel:

“SPU is moving forward with final design of an eighteen foot ten inch diameter tunnel.  Based on modeling data, King County is only participating in its cost share of a fifteen foot diameter tunnel.  Both parties are awaiting final modeling results for the integrated system incorporating a tunnel, which are expected by November.  By that time, King County will have had the opportunity to re-evaluate final tunnel size capacity decisions and cost share.”

Recent communications with the city have indicated that modeling efforts, intended to define needed storage capacity for the pipeline, continue.  Also continuing are discussions regarding the appropriate participation level by the County in cost increases associated with the enhanced storage size of the project; King County is separately undertaking a review of modeling efforts regarding its storage needs, in light of updated inputs regarding anticipated flow volumes.

In budget documents submitted to the City, SPU has further discussed cost escalation drivers.  According to the SPU 2018 Proposed Budget Narrative submitted to the Seattle City Council, the following factors are impacting projected costs:

- Increases in regional construction market cost assumptions reflecting updated projections on growing costs of construction;

- Increases due to larger tunnel storage volume based on modeling of more recent rainfall data and changing rainfall patterns;

- Increases based on design changes like increased pipe an shaft diameters, and changes in construction methodology, and

- Increases based on new sales tax growth.

SPU has included in its budget narrative, a note that “SPU estimates the total project cost of the Ship Canal Water Quality Project at $540 million into 2025”.  As noted, this compares with projected costs at the time of signature of the Joint Project Agreement of $423 million.  As described above, there has been no final determination whether, or to what extent, this cost escalation will impact the County’s cost share.

ANALYSIS:

The Joint Ship Canal Water Quality Project appears to be moving forward according to the timeline anticipated at the time of approval of the agreement, with several elements on track to be completed prior to the target date.  The project appears, however, to be impacted by significant cost escalation.  While some cost drivers—the increasing cost of land, the heated regional construction market—appear to be common to major construction projects throughout the region, close analytical review of project changes and the extent to which such changes are specific to county project requirements, as well as other cost drivers, is needed.

The County does retain some level of influence over cost increases that it will bear associated with project changes.  The Joint Project Agreement includes specific language defining the project scope, including the following components:

- A minimum 15.24-mg offline storage tunnel with a nominal 14-foot inside diameter and approximately 14,000 feet long or as defined during the design phase of the project;

- Seven diversion structures

- Four drop structures

- A pump station at the West portal

- Gravity sewer lines conveying flows from the Fremont, 3rd Avenue, and 11th Ave. NW diversion structures;

- A force main conveying flows from the tunnel pump station to the existing Ballard Siphon location

The JPA includes a reference to process requirements for modifications to the project as defined above:

“Any changes to this project scope need to be negotiated and agreed to by both SPU and DNRP through the Change Management process, attached to the Joint Project Agreement as Exhibit B.”

As noted, the Change Management process, included in Exhibit B, creates a Project Review and Change Management Committee (“PRCMC”)

“to provide senior level management oversight, support and direction to the project; the PRCMC will focus on project issues that can affect project scope, schedule and/or budget…”

Exhibit B also describes impacts of project changes on cost shares.

“…if the Parties agree to change the project scope beyond the Project Description, then the joint project cost shares and the costs to which those shares apply will be revised.  The cost shares will be recalculated in accordance with Technical Memorandum No. 4 to include additional avoided independent project, if applicable.”

Technical Memorandum No. 4 describes the process for calculating the respective cost shares of the parties.  In sum, it provides that the parties are to estimate the cost of the projects that they would independently undertake to satisfy their respective consent decrees.  The cost of those independent projects, as a proportion of the total combined costs of all of the projects that the city and county would undertake, is used to define their proportional responsibility for the project.  Presumably, then, the two projects that the County would be required to do were it to proceed independently—the 3rd Avenue West and the 11th Ave. NW projects—represent 35% of the cost of all the projects if done independently.

The JPA also includes an Exhibit C which addresses decisionmaking guidelines.  The document generally emphasizes consensus in decisionmaking, and openness and efficiency in the process of coming to decision.  It does also note, however, that

“if general agreement among members is not possible, then the Lead is responsible for making a final decision (including any compromise aspect).  This action will be the direction of the Team, subject to #13 (item #13 in Exhibit C, SPU/DNRP Ship Canal Water Quality Project:  One Team Decision Making Guidelines)”.

Item #13 of Exhibit C provides a process to address disagreements with project decisions. Where a member disagrees with a decision, an escalating appeals ladder is provided, ultimately ending with leadership of the respective participating organizations:

“if no decision is made (in the previous appeal steps), then the issue must be promptly elevated to the SPU DWW LOB Deputy Director, and the WTD Director; their decision is final.”

There is additionally an “Exhibit D”, List of Potential Causes for Capital Cost Increases”, that delineates financial responsibility for cost increases, as either Lead Agency responsibility, Shared, or Partner Agency responsibility.  Of note relative to the current cost escalation issue are the following:

- Project cost increases due to higher than estimated site acquisition costs—Shared

- Changed market conditions for labor, materials and equipment and other factors of construction such as fuel costs—Shared

- Changed bidding climate—Shared

- Unanticipated Sales Tax Increases—Shared

- Overrun due to changes that resulted from reliance on data provided by either jurisdiction proved to be inaccurate—To be jointly determined by both Agencies based on who’s Agency provided the information found to be in error.

Escalating project costs appear to be driven by a mix of factors.  The specifics of these cost drivers will be the center of discussions between the parties relative to appropriate cost share for the increased costs.  While project lead responsibility for the Joint Ship Canal Water Quality Project is assigned to the City of Seattle, the Joint Project Agreement does contain elements, referenced above, providing some level of definition for financial responsibility for cost increases, as well as for the ability of the County to influence final decisions, including project change-driven cost share decisions.

ATTACHMENTS:

- Ship Canal Water Quality Project Semiannual Report—July 2017

- City of Seattle and King County Ship Canal Water Quality Project Joint Project Agreement

INVITED:

- Keith Ward, Project Executive, Ship Canal Water Quality Project, Seattle Public Utilities

- Mark Isaacson, Director, Wastewater Treatment Division, King County Department of Natural Resources and Parks