## STAFF REPORT

| Agenda Item: | 9 | Name: | Mary Bourguignon |
| --- | --- | --- | --- |
| Proposed No.: | 2022-0160 | Date: | June 21, 2022 |

SUBJECT

Proposed Motion 2022-0160 would acknowledge receipt of the RapidRide Restart Report, which covers efforts to restart work on the K and R RapidRide lines.

SUMMARY

Metro currently operates six RapidRide lines (A-F) and is working to develop four more lines (G-J) for planned openings through 2026. Metro had begun planning for two additional lines (K Kirkland and R Rainier) but paused that work in 2020. The Council included a proviso in the 2021-2022 budget to guide efforts to restart work on the K and R lines, with a report required by March 30, 2022. Proposed Motion 2022-0160 would acknowledge receipt of the RapidRide Restart Report, which states:

K Line

- Work was paused at one percent design, reached two to five percent in 2021.

- Metro invested $600,000 in 2021 and $400,000 in 2022 to identify key improvements, advance preliminary design, analyze implementation challenges, and develop revised cost estimates of $80-$103 million (2021 dollars).

- Additional $3 to $5 million needed to reach 10 percent design and prepare for NEPA submittal, Metro recommends waiting until the line is fully funded.

- If the K Line is funded in the 2023-2024 budget, a 16-month community engagement process would begin in May 2023 leading to NEPA submittal.

- The K Line is currently less competitive for a federal Small Starts grant unless ridership recovers, as many people in the corridor have been telecommuting.

R Line

- Work was paused at approximately 10 percent design.

- Capital cost estimates developed pre-pandemic: $90-$100 million (2020 dollars).

- If the R Line is funded in the 2023-2024 budget, a 10-month community engagement process would begin in May 2023 leading to NEPA submittal.

- The R Line remains competitive for a federal Small Starts grant due to the continued high ridership on the existing Route 7 (which the R Line would replace).

BACKGROUND

RapidRide Implementation. Metro’s first RapidRide lines were proposed as part of the 2006 King County Transit Now ballot measure, which added 0.1 percent to Metro’s dedicated sales tax. RapidRide lines were proposed to be a form of bus rapid transit with high frequency operation; faster, more reliable trip times using exclusive lanes and/or transit signal priority at intersections; improved shelter waiting areas with off-board payment and real-time information at major stops; low-emission hybrid diesel-electric buses; and branded buses and facilities with a unique ride and feel.

The 2006 Transit Now measure included a commitment to implement the first five RapidRide lines (A-E). A sixth line (F) was added at the Council’s direction. The alignments for these RapidRide lines were established by ordinance and each line’s service start date and frequency were set by a service change ordinance.

Metro’s long-range plan, Metro Connects, which was first adopted in 2017, proposed an expansion of the RapidRide network. Work is currently underway on four of these next-generation lines (G-J). The Council has adopted an alignment for each of these lines, and opening dates are planned through 2026. Metro also began planning for two more lines (K, R), though work was paused during the pandemic.

Table 1 summarizes the status of the existing and planned RapidRide lines.

Table 1. Rapid Ride Lines (Operating and Planned)

| Line | Pathway | Alignment Ordinance | Service Change Ordinance | Start Date |
| --- | --- | --- | --- | --- |
| A | Federal Way to Tukwila | 16725 | 16844 | Oct 2010 |
| B | Bellevue to Redmond | 16725 | 17100 | Oct 2011 |
| C | Westwood Village to South Lake Union | 16725 | 17320 | Sept 2012 |
| D | Crown Hill to Downtown Seattle | 16725 | 17320 | Sept 2012 |
| E | Aurora Village to Downtown Seattle | 17391 | 17584 | Feb 2014 |
| F | Burien to Renton | 17391 | 17584 | June 2014 |
| G | Madison Valley to Downtown Seattle | 19012 | -- | 2024 |
| H | Burien to Downtown Seattle | 18894 | 19422 | 2023 |
| I | Renton to Auburn | 19098 | -- | 2025 |
| J | Downtown Seattle to U District | 19312 | -- | 2026 |
| K | Kirkland to Bellevue | -- | -- | ? |
| R | Rainier Beach to Downtown Seattle | -- | -- | ? |

Pause on K and R progress. The proposed 2021-2022 biennial budget was transmitted to the Council in September 2020, during the first year of the COVID-19 pandemic. Metro was experiencing financial and operational impacts from the pandemic, including significant declines in revenue,, ridership, and fare recovery. As a result, Metro’s proposed 2021-2022 budget included a reduction in both operating and capital expenditures. Specifically, the transmitted budget proposed a reconsideration of the status and schedule for the RapidRide lines that were being developed.

- G Line, H Line. For the G and H lines, Metro proposed that work was far enough along, with funding commitments in place and construction work started, that the lines should be completed as planned. The proposed budget appropriated $2 million for trolley wire reconfiguration along Madison Street in preparation for the construction of the G Line, in addition to $11 million previously appropriated, as well as $5 million for H Line capital improvements, in addition to $57 million previously appropriated.

- J Line. For the J line, Metro proposed that the County would no longer plan to provide capital funding, thus pausing work and deferring completion of the line. The City of Seattle later agreed to fund capital improvements for a truncated alignment that would end at the U District Link light rail station rather than the Roosevelt station, but which would allow work on the line to continue for a planned opening in 2026.

- I Line. For the I Line, Metro proposed that work should continue since Metro had already applied for federal funding, the I Line would operate in an area with high equity scores, and it would replace Route 160, a route that operated with lower frequency than Route 7, which had been proposed to become the R line. The proposed 2021-2022 budget appropriated $107 million to proceed with capital improvements for the I Line.

- K Line. The K Line had received an initial appropriation of $3 million in the 2019-2020 budget for preliminary design work, with additional appropriations identified in Metro’s capital improvement plan (CIP) of $4.5 million that had been intended to be proposed for the 2021-2022 biennium and $57.9 million intended to be proposed for the 2023-2024 biennium, in anticipation of construction beginning in 2024. However, as part of the transmitted 2021-2022 budget, Metro proposed that, because preliminary design work had only been partially completed prior to the onset of the pandemic (work on the K Line had reached one percent design) and because of the uncertainty around future capital funding, work on the line should be paused and no further capital appropriations should be made until a new implementation timeline could be developed.

- R Line. The R Line had completed planning through 10 percent design, although Metro had not yet sought federal NEPA environmental clearance. The line had received an appropriation of $59 million in the 2019-2020 budget, but, based on a proposal from Metro that further work on this line be paused, the 2021-2022 budget disappropriated $54 million of that amount. As noted above, Metro staff stated at the time that part of the reasoning to pause work on the R Line and instead proceed with work on the I Line was that, while both lines would serve areas with high equity scores, the R Line would replace Route 7, a route that already provided frequent all-day service.

In response to the proposal to pause work on several of the planned RapidRide lines, the Council added a proviso requirement to the budget ordinance that asked Metro to transmit a RapidRide Restart Report by September 30, 2021.

By mid-2021, when the mid-biennial supplemental budget ordinance was transmitted, Metro’s financial situation had improved due to an uptick in sales tax revenues and additional federal funding.

In response to the improvement in Metro’s financial situation, the Council added an expenditure restriction to encumber $400,000 to be used for staff to continue design, planning, and community engagement, and to develop detailed capital program proposals for the K and R lines. In addition, the Council amended the proviso requirement to extend the due date for the RapidRide Restart Report until March 30, 2022, and to add more specificity about the work to be completed.

In late 2021, the Regional Transit Committee and Council adopted an update to Metro Connects. The updated Metro Connects states that 10 RapidRide lines (A-J) are expected to be in operation by 2026; 13 to 15 lines are expected to be in operation by the time of the Interim Network (approximately 2035); and 19 to 23 lines are expected to be in operation by the time of the 2050 Network. Metro Connects states that the K and R lines have been prioritized as the next RapidRide lines to be implemented and that, because they have been prioritized for investment, they are not considered to be “candidate lines,” but rather are committed as the next two RapidRide lines to be developed.

Budget proviso requirement. The expenditure restriction and proviso requirement, as amended by the mid-biennial supplemental ordinance, state:

ER6 EXPENDITURE RESTRICTION:

Of this appropriation, $400,000 shall be expended or encumbered solely to:

A.  Hire staff, continue design, planning or project delivery work, prepare for community and partner engagement or otherwise prepare and present detailed capital program proposals and timelines for both the K and R RapidRide lines as part of the proposed 2023-2024 biennial budget;

B.  Make progress on planning for the K Line to reach three to five percent project design completed; and

C.  Make progress on planning for the R Line to prepare to transition from the planning phase to the project delivery phase during the 2023-2024 biennium.

P1 PROVIDED THAT:

A.  Of this appropriation, $600,000 shall not be expended or encumbered until the executive transmits a RapidRide restart report and a motion that should acknowledge receipt of the report and a motion acknowledging receipt of the report is passed by the council.  The motion should reference the subject matter, the proviso's ordinance number, ordinance section and proviso number in both the title and body of the motion.

B.  In recognition of the fact that ((three)) two named RapidRide lines (which are the R (Rainier)((, J (Roosevelt))) and K (Totem Lake/Bellevue/Eastgate)), which were planned to be implemented during 2024 and 2025, and for which community engagement and capital planning efforts have already been initiated, have been proposed to be deferred indefinitely, the report shall address the Metro transit department's efforts to implement these deferred lines as quickly as possible, including, but not limited to:

1.  Efforts to be undertaken during 2022 to hire staff, continue design, planning or project delivery work, prepare for community and partner engagement or otherwise prepare and present detailed capital program proposals and timelines for both the K and R RapidRide lines as part of the proposed 2023-2024 biennial budget;

2.  For the K Line, a description of work already completed or planned to be undertaken during 2022 to make progress on planning for the K Line to reach three to five percent project design completed, based on the fact that work on the K Line was paused with approximately one percent project design completed, as well as a description of efforts to be undertaken during 2022 to prepare to begin the next phase of work on the K Line during the 2023-2024 biennium;

3.  For the R Line, a description of work already completed or planned to be undertaken during 2022 to make progress on planning for the R Line to prepare to transition from the planning phase to the project delivery phase, based on the fact that work on the R Line was paused with approximately ten percent project design completed, as well as a description of efforts to be completed during 2022 to prepare to begin the next phase of work on the R Line during the 2023-2024 biennium;

4.  Efforts to secure grant or partner funding for capital improvements or operational costs and a timeline for when the Metro transit department plans to seek grant or partner funding for each line;

((2.  The status of)) 5.  A plan for ongoing partner and community engagement and planning efforts for these deferred lines during the 2023-2024 biennium;

((3.  The status of)) 6.  A plan for ongoing alignment and capital planning efforts for these deferred lines during the 2023-2024 biennium; and

((4.  The status of these deferred lines in the interim service network included in the proposed update to METRO CONNECTS, with the expectation that these three deferred lines will be prioritized for implementation in METRO CONNECTS and other proposed policy documents; and

5.)) 7.  A proposed timeline for implementation for each of the deferred lines based on the fact that both the K and R lines are proposed to be part of the Metro Connects interim network, as proposed through Ordinance XXXXX (Proposed Ordinance 2021-0286).

C.  ((Two of the three deferred RapidRide lines, the J line and t))The R line((, are)) is being implemented in partnership with the city of Seattle.  As a result, although ((these lines have)) the line has been deferred, operational analysis and planning efforts have already been undertaken.  The K line, however, is being implemented by King County, which has not yet completed operational analysis and planning.  To ensure that preparation for the K line is at the same level ((as the other two deferred lines)) and that ((all three)) both lines are able to move forward when funding is available, the report shall summarize operational analysis and planning efforts that have been completed related to the RapidRide K line and the surrounding area, including, but not limited to:

1.  Identification of a list of priorities and key projects in the area of the RapidRide K line that would support future interagency agreements or grant funding opportunities, as well as future environmental permitting requirements;

2.  A description of the Metro transit department's work with Sound Transit regarding coordination between planning for the RapidRide K line with East Link light rail and I-405 bus rapid transit; ((and))

3.  A description of the work already completed or planned to be undertaken during 2022 to make progress on planning for the K Line to reach three to five percent project design completed, based on the fact that work on the K Line was paused with approximately one percent project design completed;

4.  A description of work to be undertaken during 2022 that will identify key improvements for the K Line that could feasibly be advanced during the 2023-2024 timeline; and

5.  A description of the next steps and needed budget that would be required to proceed ((further)) during the 2023-2024 biennium with design and environmental analysis for the RapidRide K line.

D.  The executive should electronically file the report and the motion required by this proviso no later than March 30, 2022, with the clerk of the council, who shall retain an electronic copy and provide an electronic copy to all councilmembers, the council chief of staff and the lead staff for the mobility and environment committee, or its successor.

ANALYSIS

Proposed Motion 2022-0160 would acknowledge receipt of the RapidRide Restart Report, which covers efforts to restart work on the K and R RapidRide lines, and which was transmitted by the March 30, 2022, proviso deadline.

The report describes the pre-pandemic status, as well as efforts undertaken during 2021 and planned for 2022, to advance planning and design work for the two future RapidRide lines:

- K Line would be an approximately 18-mile north to south corridor parallel to I-405 within Bellevue and Kirkland connecting Totem Lake, Downtown Kirkland, South Kirkland Park & Ride, Downtown Bellevue, Bellevue College, and the Eastgate Park & Ride following portions of existing routes 255, 250, 245, 239, and 271 (see Attachment 3 for a map);

- R Line would be an approximately eight-mile north to south corridor between Downtown Seattle and the Rainier Beach Link light rail station that would upgrade and replace the existing Route 7 connecting to the Rainier Beach, Mt. Baker, International District, Pioneer Square, and (future) Judkins Park light rail stations (see Attachment 3 for a map).

The report begins by outlining a process “road map” for the delivery of a RapidRide line. The road map summarizes a four-and-a-half- to five-year process to complete the steps of project planning, preliminary design (to 30 percent design), final design (30 to 100 percent design), implementation, and closeout needed to plan and construct the capital improvements for a RapidRide line. The road map summarizes key Metro milestones along the way, as well as timing for contracting; alternatives analysis, design, and construction; service changes; environmental and sustainability work; outreach; and partnerships.

Using this road map, the report states that, at the time work was paused:

- K Line had just begun the preliminary design phase and was at about one percent design with estimated capital costs of $80 to $103 million (2021 dollars); and

- R Line was midway through the preliminary design phase, at about 10 percent design with estimated capital costs of $90 to $100 million (2020 dollars).

The report recommends that it would be most advantageous to wait to develop each line until funding is programmed into Metro’s budget and CIP for both capital and future operating costs, rather than proceeding in a segmented manner, because:

- Given the high level of construction inflation the region is currently experiencing, costing and other analytical work will need to be redone just prior to construction;

- Each project that is implemented will require federal, state, and local regulatory review and it will be most time- and cost-effective to go through this review process only once for each line; and

- The lines will be more competitive for federal Small Starts grant funding if each is submitted as a complete project (including local match investments from partner jurisdictions) rather than being submitted in segments.

The RapidRide Restart Report also includes the following information, as required:

Progress on both lines. Section B of the proviso requested information on the progress toward implementing both the K and R lines.

B.1. Efforts to be undertaken during 2022 to hire staff, continue design, planning or project delivery work, prepare for community and partner engagement or otherwise prepare and present detailed capital program proposals and timelines for both the K and R RapidRide lines as part of the proposed 2023-2024 biennial budget.

The report notes that budgetary authority was restored in 2021 for three positions to allow Metro to continue work on the K and R lines: a planning lead and project delivery staff to support the technical and project management work for both lines. Hiring for these positions is anticipated to occur in 2022.

The report notes that until these project-specific staff are in place, planning for the K and R lines is continuing as part of the development of Metro’s 2023-2024 budget proposal and the development of the RapidRide Prioritization Plan, which is required to be transmitted to the Council by June 30, 2024. The RapidRide Prioritization Plan must include corridor evaluations of RapidRide candidate corridors; preplanning level studies of candidate corridors that consider route alignment, capital investment needs, and cost estimates; a description of stakeholder engagement; and a list of the candidate lines organized by tier. (As noted above, the adopted Metro Connects requires that the K and R lines be identified in the RapidRide Prioritization Plan as the next new RapidRide lines to be implemented.)

B.2. For the K Line, a description of work already completed or planned to be undertaken during 2022 to make progress on planning for the K Line to reach three to five percent project design completed, based on the fact that work on the K Line was paused with approximately one percent project design completed, as well as a description of efforts to be undertaken during 2022 to prepare to begin the next phase of work on the K Line during the 2023-2024 biennium.

The report notes that, prior to pausing work on the K Line, Metro had developed a preferred alignment (from Eastlake Park and Ride to Totem Lake Transit Center) in coordination with the cities of Bellevue and Kirkland and local community members. As part of this effort, Metro had identified key capital improvements that would be needed, including roadway upgrades, intelligent transportation system (ITS) elements, station locations, and bike/pedestrian improvements. The report states that Metro’s plan had been to move toward 10 percent conceptual design, but that work was paused at the one percent stage after the pandemic began.

Metro resumed planning efforts for the K Line at the beginning of 2021, allocating $600,000 for alternatives analysis and design, including identifying key improvements along the corridor and conducting initial assessments of conformity with local jurisdictions’ code and regulatory requirements. Revised capital cost estimates of $80-$103 million were developed in 2021, though the report states that these estimates will need to be updated because of construction cost inflation.

The report states that Metro is continuing this work in 2022, with additional technical work scheduled to begin in May to further refine the conceptual design for improvements that present technical implementation challenges (such as how to integrate the K Line at the two termini).

B.3. For the R Line, a description of work already completed or planned to be undertaken during 2022 to make progress on planning for the R Line to prepare to transition from the planning phase to the project delivery phase, based on the fact that work on the R Line was paused with approximately ten percent project design completed, as well as a description of efforts to be completed during 2022 to prepare to begin the next phase of work on the R Line during the 2023-2024 biennium.

The report states that work during 2021 and into 2022 was limited to jurisdictional coordination with the Seattle Department of Transportation (SDOT) to determine if a future partnership is possible.

The report states that, prior to work on the R Line being paused, Metro had prepared a corridor planning and upgrade report, which summarizes the major capital improvements identified during the pre-design analysis for transit speed and reliability, passenger facilities, transit communications and technology, and pedestrian and bike access to transit. The report states that when funding is restored, Metro will advance the project into a NEPA environmental clearance but does not recommend doing additional work until ready to proceed with NEPA review.

B.4. Efforts to secure grant or partner funding for capital improvements or operational costs and a timeline for when the Metro transit department plans to seek grant or partner funding for each line.

The report states that Metro expects to fund the K and R lines through a combination of local, state, and federal grant programs, partner agency funds, and County funds. Historically, Metro has planned for approximately 45 percent of the capital costs for a RapidRide line to be funded by the County and 55 percent through external sources, including federal and state grants and local partners.

The report notes that Metro continues to work with the cities of Seattle (R Line) and Kirkland (K Line) to discuss potential contributions by the cities, such as roadway and frontage improvements or grants sought by the cities, but that until Metro’s CIP includes funding for these lines the discussions are conceptual only.

During 2021 and 2022, Metro studied construction cost trends to evaluate the potential impact on the cost of developing the K and R lines based on trends observed in the construction of the G, H, I, and J lines. The R Line’s estimates were developed prior to the pandemic, while the K Line’s estimates were revised in 2021. The report states that inflation has become a major factor and that work is underway to update these estimates for Metro’s 2023-2024 budget proposal.

The report states that Metro has also continued to evaluate the competitiveness of the two lines for federal Small Starts funding, noting that a key factor is a project’s ability to demonstrate that it will generate new ridership:

- R Line is expected to remain highly competitive due to the population density along the route and the high ridership on the current Route 7.

- K Line is currently less competitive unless and until ridership recovers from the pandemic due to the trend of many people in Kirkland along the K Line corridor telecommuting rather than riding transit to an office, although the corridor is experiencing significant jobs growth.

The report notes that Small Starts funding is not a requirement to develop a RapidRide line and that the H Line was completed without a Small Starts grant, but that Small Starts is the largest potential source of funding for a new RapidRide line, meaning that more County or other local funding would be needed if a Small Starts grant cannot be secured.

B.5. A plan for ongoing partner and community engagement and planning efforts for these deferred lines during the 2023-2024 biennium.

The report states that partner and community efforts will be resumed for both lines once funding is identified in the Metro CIP, and that, in addition, outreach will be performed as part of the RapidRide Prioritization Plan that is being developed as a requirement of the Metro Connects long-range plan. Specifically:

- K Line engagement to date has focused on jurisdictional coordination, outreach as part of the East Link Connections Mobility Project, and early outreach to community-based organizations and potentially impacted businesses/property owners. If the K Line is funded in the 2023-2024 budget, a 16-month engagement process would begin in May 2023 focusing on the project’s technical work, conceptual design, and required NEPA outreach. Following NEPA, engagement would continue during 2024-2025 into final design (30-100 percent).

- R Line engagement would resume in May 2023, if the project is funded in the 2023-2024 budget, and would focus on a 10-month process for required NEPA outreach. Following NEPA, outreach would continue during 2024-2025 into final design (30-100 percent).

B.6. A plan for ongoing alignment and capital planning efforts for these deferred lines during the 2023-2024 biennium.

The report states that Metro is currently analyzing current and forecasted revenues and prioritizing needs to develop a 2023-2024 budget proposal, which will include a six-year CIP. If the K and/or R lines are included in the 2023-2024 budget and associated CIP, Metro would conduct planning and design efforts consistent with the project timelines in the CIP.

B.7. A proposed timeline for implementation for each of the deferred lines based on the fact that both the K and R lines are proposed to be part of the Metro Connects interim network, as proposed through Ordinance 19367.

The report confirms that, per the adopted Metro Connects, the K and R Lines will be the next two RapidRide lines to be developed and will be operational no later than the time of the Interim Network.

In terms of a specific implementation timeline, the report states that the RapidRide road map process chart described above will be used to guide each line through the planning, design, and implementation process. The time at which work would be resumed for each line will be determined by whether the lines are funded in the 2023-2024 budget.

Progress on K Line. Section C of the proviso requested information on the progress toward implementing the K Line. The report states that additional operational analysis and planning efforts completed during 2021 have resulted in a RapidRide K Line Roadmap Report, which is included as Appendix A to the transmitted report.

C.1. Identification of a list of priorities and key projects in the area of the RapidRide K line that would support future interagency agreements or grant funding opportunities, as well as future environmental permitting requirements.

The report identifies a preferred alignment for the K Line, well as priority projects, including speed and reliability improvements, such as bus or business access transit lanes, queue jump lanes, and transit sign priority; access to transit improvements, such as pedestrian connections, bicycle parking, bicycle improvements, and multimodal enhancements; and proposed station locations and amenities.

It also identifies connections to transit centers, park & ride lots, the Cross Kirkland Corridor, and Sound Transit’s East Link and Stride bus rapid transit I-405 services; and describes a potential separate project to enhance transit connections to Bellevue College. (Maps showing these potential projects can be found on pages 23-26 of Attachment A to Proposed Motion 2022-0160.)

C.2. A description of the Metro transit department's work with Sound Transit regarding coordination between planning for the RapidRide K line with East Link light rail and I-405 bus rapid transit.

The report states that the K Line will form part of an integrated transit network with East Link light rail and Sound Transit’s I-405 bus rapid transit (Stride BRT). (Key integration points along the preferred alignment for the K Line are shown in a map on page 29 of Attachment A to Proposed Motion 2022-0160.)

The report states that Metro has met with Sound Transit approximately 60 times since the beginning of 2021 on East Link integration and approximately 50 times on the Stride bus rapid transit projects on I-405 and that the K Line has been discussed in these forums to ensure future system compatibility. The report notes that approximately 10 of the Stride meetings have focused on the future NE 85th Station and interchange, which has been identified as the primary transfer location between the K Line and Stride.

C.3. A description of the work already completed or planned to be undertaken during 2022 to make progress on planning for the K Line to reach three to five percent project design completed, based on the fact that work on the K Line was paused with approximately one percent project design completed.

The report notes that prior to work on the K Line being paused, Metro had worked with the cities of Bellevue and Kirkland to establish a preferred alignment that included identifying key project elements, such as stations, roadway improvements, intelligent transportation systems, and access improvements.

Metro resumed planning efforts for the K Line at the beginning of 2021, using $600,000 to advance planning work in the areas of next steps, speed and reliability investments, transit center operational recommendations, station locations, access to transit investments, communication system investments, and local agency system modifications.

The report states that by the end of 2021, work on the K Line was at the two to five percent conceptual design range, noting that technically challenging issues are usually addressed in the earlier phases of the design process.

C.4. A description of work to be undertaken during 2022 that will identify key improvements for the K Line that could feasibly be advanced during the 2023-2024 timeline.

The report states that during 2022, Metro will:

- Continue to advance key elements identified for the K Line, including candidate projects that require further vetting with Bellevue, Kirkland, WSDOT, and Sound Transit, including assessing funding and partnership opportunities.

- Procure $400,000 in technical support, planned to start May 2022, to focus on technically challenging improvements to continue to advance toward five percent design. A key focus of this work will be advancing the technical design for the specific routing and integration of the route at Totem Lake Transit Center, South Kirkland Park and Ride, and Bellevue Transit Center, as well as advancement of siting for K Line stations adjacent to these transit centers.

C.5. A description of the next steps and needed budget that would be required to proceed during the 2023-2024 biennium with design and environmental analysis for the RapidRide K line.

Capital costs for the K Line are estimated at $80 to $103 million (in 2021 dollars).

The report notes that, from that total, approximately $3 to $5 million would be required to complete the remaining technical work to reach 10 percent design and prepare needed environmental documentation. This amount is in addition to the $2.5 million forecasted to be spent by the end of 2022.

As noted above, Metro recommends not submitting environmental documentation for NEPA review until Metro is ready to apply for a Small Starts grant, which itself is contingent on the full project cost being included in Metro’s CIP. The report proposes that Metro continue with the 2023-2024 budget process, with next steps identified as part of the budget proposal.

Additional Information. The RapidRide Restart Report includes additional documentary information attached as appendices:

- K Line Project Roadmap Report

- R Line Corridor Planning and Upgrade Report

These two reports provide more detailed analysis of the preferred alignment and alignment alternatives, potential station locations, candidate capital investments, and a summary of community engagement.

Next Steps. The central recommendation of the Restart Report is that work should not proceed further on either line until capital and future operational funding is identified for that line in Metro’s budget and associated CIP. The report states that this recommendation has been made because of the impacts of inflation on cost estimates; because federal, state, and local approvals will be needed for each project, and it would be most time- and cost-effective to submit each line as a complete, single project; and because Metro believes that each line will be more competitive for federal Small Starts grant funding as a complete project than if submitted in segments.

Because of this recommendation, the proposed 2023-2024 budget will be important in determining the timing for moving forward with each line. While the adopted Metro Connects long-range plan commits that the K and R lines will be the next two RapidRide lines to be implemented and will be operational by the time of the Interim Network (approximately 2035), the specific timing of implementation will depend on decisions made by the Executive and Council in the 2023-2024 and future budgets about how and when Metro’s CIP should include capital funding for these lines.

The transmitted report also discusses options for partner and grant funding, noting that Metro’s experience to date is that King County has funded about 45 percent of the capital improvements for each RapidRide line, with 55 percent coming from partners or grant funds. The largest grant funding source is the federal Small Starts program, for which the report states that the ability to attract and increase ridership is a key consideration. Based on ridership, the report states that the R Line remains competitive for Small Starts funding, as ridership along that corridor has remained high throughout the pandemic and the Route 7 is one of Metro’s most productive routes, but that the K Line would be less competitive unless ridership recovers, as many residents along that corridor have been telecommuting during the pandemic.

As transmitted, the RapidRide Restart Report appears to comply with the requirements of the proviso.

ATTACHMENTS

- Proposed Motion 2022-0160 (and its attachments)

- Transmittal Letter

INVITED

- Alex Kiheri, RapidRide Expansion Lead, Metro Transit Department

National Environmental Policy Act

Ordinances 15582, 15670

Metro currently collects a total of 0.9 percent sales tax

Ordinance 18449, since updated through Ordinance 19367. Additional study in Motion 14956

The G, H, J, and R lines are being developed in collaboration with the City of Seattle, with capital improvements partially or fully funded from the Move Seattle levy.

In the proposed 2021-2022 budget, Metro forecast its revenues to be $349 million lower than in pre-COVID projections. In response, the budget included $483 million more in expenditures than revenues, with undesignated fund balance drawn down over the next several biennia to cover the gap.

In March 2020, Congress passed the Coronavirus Aid, Relief, and Economic Security (CARES) Act, from which Metro was allocated $243.7 million in April 2020. Metro used this funding to cover the revenue losses and emergency operational expenses it experienced during the early months of the pandemic, fully expending the funds by the end of 2020. CARES Act funds were not available to be used in the 2021-2022 budget.

Metro made emergency service reductions three times between March 23 and April 20, 2020. During much of 2020 and 2021, Metro operated with about 85 percent of its fixed-route network, with about half the suspended service restored in September 2021. Ridership, which was 562,000 average weekday boardings in February 2020, fell to 135,000 in April 2020. Since then, ridership has gradually improved, reaching 173,000 average weekday boardings in January 2022. Metro Strategic Plan Dashboard (link)

Metro’s adopted financial policies (Ordinance 18321) require that Metro recover at least 25 percent of passenger-related operating costs from fares, with a target of 30 percent. (This provision was suspended during the 2021-2022 biennium through Ordinance 19206.) Metro achieved seven percent fare recovery in 2020 and 10 percent in 2021.

Ordinance 18835 Fund 3641, Project 1132324 and Ordinance 19210, Fund 3641, Project 1134275

Ordinance 19210, Fund 3641, Project 1132325

Ordinance 19210, Fund 3641, Project 1132327

The Council approved this alignment for the J Line through Ordinance 19312.

Equity scores are calculations for each route and station area that are based on the makeup of priority populations (race, income, disability, foreign-born, limited English speaking) in the area. These scores are defined in the King County Metro Service Guidelines (Ordinance 19367, Attachment B).

Ordinances 18835 and 19210, Fund 3641, Project 1134237

Ordinance 18835, Fund 3641, Project 1134292

NEPA = National Environmental Policy Act (link)

Ordinance 18835, Fund 3641, Project 1132326

Ordinance 19210, Fund 3641, Project 1132326

Ordinance 19210, Section 113, Proviso P1. This proviso also asked Metro to address work to be done to move forward with the J Line, language that was removed when the proviso was amended given the City of Seattle’s agreement to provide capital funding for that line.

Ordinance 19364

The supplemental ordinance proposed a net increase in appropriation authority of $52.7 million for operational expenses and $113.8 million for capital investments, as well as 242.1 additional FTE and 136 TLT positions

The supplemental ordinance (Ordinance 19634) included a revenue estimate that was $681 million above the adopted 2021-2022 budget, with the two largest sources of increase revenue being sales tax ($196 million increase) and grants/federal aid ($387 million increase). In terms of federal aid, Metro received two additional tranches of federal aid: The Coronavirus Response and Relief Supplemental Appropriations Act (CRRSAA), from which Metro was allocated $258 million in April 2021, and the American Rescue Plan Act (ARPA), from which Metro was allocated $395.6 million in September 2021.

Ordinance 19367

The Interim Network is envisioned for the completion of the Ballard and West Seattle Link light rail extensions (for costing purposes, estimated at 2035). Metro staff have stated that the Interim Network was intentionally associated with transit expansion milestones, rather than specific dates (which were proposed to be delayed as part of Sound Transit’s realignment effort in 2021), because these milestones are what prompt major Metro service restructures. Updates to reflect changes in Sound Transit’s plans will be made through future updates to Metro Connects, as well as service change proposals.

Ordinance 19367, Attachment C, pp. 23, 100.

Ordinance 19364, Section 86, Expenditure Restriction ER1

Ordinance 19210, Section 113, Proviso P1, as amended by Ordinance 19364, Section 86, Proviso P1

Ordinance 19367

RapidRide K Line (link)

RapidRide R Line (link)

Proposed Motion 2022-0160, Attachment A, Figure 1, p. 13

These estimates are subject to inflation and will need to be finalized later in the process.

US Department of Transportation, Federal Transit Administration, Capital Investment Grants Program (New Starts, Small Starts, Core Capacity Improvements) (link)

Ordinance 19364

Ordinance 19367

Ordinance 19367, Attachment C

The H Line was funded with $42.7 million in County funding, $14.5 million in state grants, and $57.5 million from the City of Seattle.

The East Link Connections Mobility Project, which will propose a Metro restructure to coordinate Metro service with the new Sound Transit East Link light rail has undergone three phases of community engagement. A proposal is anticipated to be transmitted to the Council in July 2022. (link)

This recommendation even extends to the efforts of partner jurisdictions to make roadway or speed and reliability improvements. The report states that a Small Starts grant application will be most competitive if the entire project, including projects planned by local jurisdictions, is included. Including planned local projects will increase the local match for the project, making it more competitive.