## STAFF REPORT

| Agenda Item: | 4 | Name: | Jenny Giambattista |
| --- | --- | --- | --- |
| Proposed No.: | 2018-0120 | Date: | May 1, 2018 |

SUBJECT

A motion accepting the King County-Cities Climate Collaboration (K4C) 2018 Work Plan and Budget.

SUMMARY

Motion 2018-0120 accepts the 2018 work plan and budget for the King County-Cities Climate Collaboration (K4C), as requested by Motion 14449. The 2018 K4C budget includes expenditures of $56,625.

BACKGROUND

The K4C is a voluntary but formal partnership between King County and 13 cities to work together on climate and sustainability issues. The K4C is supported by an Interlocal Agreement (Ordinance 17285) outlining areas of focus for joint work and cost-share requirements. Through K4C staff from the partner cities share ideas and best practices and host an annual summit of elected officials from the partner cities to discuss climate related topics.

As specified in the interlocal agreement K4C is funded by a shared funding model, scaled to member jurisdictions’ population. Participating cities determine how to use shared resources to support regional climate progress. (The K4C Interlocal Agreement (ILA) includes a stipulation that 75% of parties must approve of budget expenditures.)

The K4C has established a shared regional vision for climate action, Joint Letter of Commitment: Climate Change Actions in King County (Attachment 3). The actions are intended to “get the region on track” towards shared and ambitious countywide, greenhouse gas (GHG) reduction targets formally adopted by King County in King County’s Strategic Climate Action Plan (SCAP). Many of the strategies and priority actions of the King County’s SCAP mirror the K4C commitments.

Motion 14449, adopting the County’s SCAP includes the following requirement for reporting on K4C:

“Consistent with Ordinance 17285, which authorized the Interlocal Agreement for the King County-Cities Climate Collaboration, the executive is requested to coordinate with staff of the transportation, economy and environment committee, or its successor, in developing the annual work plans and budget for the King County-Cities Climate Collaboration under the interlocal agreement.  The executive is requested to submit by January 31, and every year thereafter, the King County-Cities Climate Collaboration annual work plan and budget to the council for acceptance by motion.  The 2016 work plan should include recommendations on the timing and approach for an update to the interlocal agreement that includes addressing drafting issues identified during the council’s initial review of the agreement.”

ANALYSIS

The 2018 Work Plan includes a high level summary of the activities K4C will pursue in 2018. The proposed activities are organized around K4C’s Joint Letter of Commitments in the areas of better data and measurement of GHG emissions, energy supply, transportation and land use, green building and energy efficiency.

The 2018 K4C budget is listed below. As shown, there is $43,540 of unspent funds from 2017. For 2018, the budget shows total resources available for 2018 as $97,740. However, there is only $56,625 currently budgeted for expenditures. The K4C steering committee held a budget decision making meeting on December 7, 2017 to do an initial round of funding allocation.  According to Executive staff, the group will reconvene this spring to allocate the remaining cost share funds.

2018 K4C Budget

| 2018 K4C Revenues |  |
| --- | --- |
| ILA Defined Partner Contributions | $34,200 |
| Related King County Contribution | $20,000 |
| 2017 Unspent Funds | $43,540 |
| Total Resources Available for 2018 | $97,740 |
| 2018 K4C Approved Expenditures |  |
| 2018 Sustainable Cities Roundtable Series - Event Production Support | $10,000 |
| 2018 Sustainable Cities Roundtable Series - To support stipends, honorariums or other financial support for local events, especially for topics and speakers related to environmental justice, climate justice and broader equity and social justice topics, themes or Roundtable participants | $5,000 |
| 2018 Sustainable Cities Roundtable Series - to support audio/video recording or transmitting (e.g. webinars) of roundtables or trainings | $2,000 |
| 2018 K4C Event Catering | $1,000 |
| K4C and K4C Partner - Climate Action Infographics | $10,000 |
| Scope 5 – Greenhouse Gas Measurement and Tracking Program | $12,625 |
| High Performance Green Building Code - City Implementation Tools | $16,000 |
| Total Approved 2018 Expenditures | $56,625 |

Below is the information provided by Executive staff on some of the key expenditures for 2018.

$10,000 for climate action infographics

The content for the infographics will be developed in collaboration with K4C partner jurisdiction staff. Graphics work will be done in house with support from the King County KCIT Design & Civic Engagement unit, with funding support from the city and county cost-share contributions.

The infographics will build on a recently updated King County Climate Change Infographic (Attachment 4) to create a new K4C infographic that highlights the rationale for climate action, K4C accomplishments, areas of progress, and what’s next.  The infographic will include a section where cities can add information with their specific data/information/and actions that relate to K4C commitments.

SCOPE 5 –Greenhouse Gas Measurement and Tracking Program $12,625

This funding is to expected be used to continue to develop and maintain a web-based greenhouse gas emissions measurement platform for K4C partners that is transparent, current, and provides consistency across agencies based on best practices. K4C is currently developing a public facing dashboard that will share K4C and K4C partner sustainability data. The first set of data that has been published under this framework is by the City of Bellevue. It’s available here: https://k4c.scope5.com/dashboards/1

High Performance Green Building Code—City Implementation Tools $16,000.

This project is intended to develop model intake forms and guidance documents to support the successful delivery of high performance green building projects from intake of permit application through construction and certificate of occupancy. The project will develop the necessary tools for permit reviewers and inspectors in K4C cities on commonly used green building rating systems in King County (Living Building Challenge, LEED, Built Green, Salmon Safe and Passive House). Developers who work in multiple local jurisdictions will benefit from greater consistency and predictability across permitting systems.  This funding will also support a Green Inspector Training on green building techniques and certifications.

ATTACHMENTS

- Proposed Motion 2018-0120 (and its attachments)

- Transmittal Letter

- K4C Joint Letter of Commitment

- Climate change infographic

INVITED

- Matt Kuharic, Climate Change Program Coordinator, Department of Natural Resources and Parks

- Rachel Brombaugh, Energy Policy and Partnerships Specialist, Office of the Executive

- Megan Smith, Director of Climate and Energy Initiatives, Office of the Executive

Bellevue, Burien, Issaquah, Kirkland, Mercer Island, Normandy Park, Redmond, Renton, Sammamish, Seattle, Shoreline, Snoqualmie, and Tukwila

The funding source for the County’s $20,000 is the “Climate Change Cost Share” budget which is funded by cost shares from county agencies based on their greenhouse gas emissions from energy and fuel. DNRP and DOT agencies are the most significant energy and fuel users (and GHG emitters) and fund the vast majority (96%) of this cost share.