EXECUTIVE RECOMMENDED PLAN

Report on Vashon-Maury Island

Community Service Area Subarea Plan

Implementing Actions

# I. Overview

The scoping motion for the 2020 King County Comprehensive Plan (KCCP), adopted in Attachment A to Motion 15329, includes the following directive to which this report responds:

Review the Priority 1 and Priority 2 implementing actions from the Vashon-Maury Island CSA Subarea Plan and provide either a report or recommended policy or code changes to: 1) determine the implementing actions current status, 2) determine whether existing Comprehensive Plan policies or development regulations (or any other adopted plan) requires changes in order to proceed with implementation, 3) whether those changes are recommended for inclusion in the 2020 KCCP Update, and 4) for those items that are not currently on schedule, an explanation why and an evaluation of when they could be completed.

# II. Background

In 2017, the King County Council adopted the Vashon-Maury Island Community Service Area Subarea Plan (Attachment A to Ordinance 18623, as amended by Ordinance 18810). Chapter 11 of the Subarea Plan establishes a framework to translate the policies outlined in the adopted Plan into specific implementing actions. The actions are outlined in a set of Implementation Tables that are organized by priority level:

Short-term (Priority 1) actions, which were targeted to begin within two years of plan adoption (2018-19).

Mid-term (Priority 2) actions, targeted to begin no sooner than three to five years after plan adoption (2020-2022).

Long-term (Priority 3) actions, targeted to begin not sooner than six or later than eight years after plan adoption (2023-2025).

Ongoing actions, which link to existing King County departments, plans, or programs, and typically guide how or when to support activities that may occur or may be proposed at an undefined time.

A lead King County agency was assigned to each action, although the majority of actions require support from other County agencies or outside organizations. Some actions may be able to be achieved through current funding.  Actions that are not able to be addressed with existing resources are subject to the availability of additional funds, either through approval of appropriations in future King County budgets and/or from outside funding sources.

Priority 1 Implementation Actions (Short-Term, 2018-2019)

| Policy No. | Priority 1 Implementing Action – 2018-2019 | Responsible Party | 1. Current Status, as of 4/19/19 | 2. Are policy, code, or plan changes needed to proceed with implementation? | 3. Are those changes included in 2020 KCCP? | 4. If not on schedule, a) why and b) updated timeline |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Lead | Support |  |  |  |  |
| Chapter 5: Rural Area and Natural Resource Lands |  |  |  |  |
| R-2 | King County should seek grant funding to develop enhanced methods of public outreach and education to better assist Vashon-Maury Island’s PBRS participants with forestry, agricultural, and other land stewardship improvements, including topics, tools and property owner forums. | DNRP/WLRD | -- | DNRP/WLRD submitted a funding proposal to the Puget Sound Partnership to focus outreach to encourage owners of lands identified as Land Conservation Initiative priorities to enroll in the PBRS or Current Use Taxation programs. That would have included reaching out to Vashon-Maury Island landowners. Although the proposal made it through the initial review process, it was not ultimately selected for funding. In 2019, DNPR/WLRD plans to increase general outreach to PBRS landowners with a newsletter sent to all participating landowners and increasing our focus on monitoring. | No | n/a | n/a |
| Chapter 6: Housing and Human Services |  |  |  |  |
| H-5 | King County shall implement, evaluate, and report on the affordable housing incentive Special District Overlay (SDO) in K.C.C. 21A.38. King County should revise the SDO as indicated by the County’s evaluation of the SDO’s use, benefits, and impacts. | DPER | DCHS | The first annual report with evaluation and reporting on the SDO was transmitted to the Council on December 31, 2019 via Proposed Motion 2019-0016, consistent with the deadline in Ordinance 18623. | No | n/a | n/a |
| H-6 | King County shall research and consider drafting amendments to the Accessory Dwelling Unit (ADU) section of the King County Code. | DPER | -- | A code study has been completed and will be included in the 2020 KCCP transmittal. | No | n/a | n/a |
| Chapter 7: Environment |  |  |  |  |
| E-5 | 1. King County shall coordinate with island property owners, hazard mitigation specialists, engineers, and other key stakeholders to develop policy and public education tools targeted for use on Vashon-Maury Island, considering such topics as: a. Creating disincentives for new construction that is located in projected sea-level rise zones; b. In coordination with other King County departments and agencies, DPER shall research regulatory approaches for reducing flood hazards in marine zones; and c. Other Vashon-specific items derived from the sea level rise strategy being developed by DNRP/WLRD staff. 2. King County shall pursue a permanent funding source for routine monitoring of marine shoreline changes. Data collected from said monitoring shall be used to support future climate change mitigation and adaptation interventions. | #1 – DPER #2 – DNRP/ WLRD |  | 1. The public outreach began in 2018 as part of development of the 2019 update to the Shoreline Management Program and continued during development of the 2020 KCCP. 2. DNPR/WLRD has initiated work on this action item, is currently evaluating a permanent funding approach through the Water Resource Inventory Areas, and is also seeking additional grant funding. | 1. No 2. No | 1. n/a 2. n/a | 1. n/a 2. n/a |
| Chapter 8: Parks, Open Space & Cultural Resources |  |  |  |  |
| P-3 | a. King County should analyze its publicly-held property and road right-of-way to identify any potential opportunities for increasing public shoreline access or transferring to other agencies. b. DOT/Roads and DNRP/Parks staff shall develop a set of criteria to identify opportunities for appropriate shoreline access. c. King County shall cooperate with Vashon Park District to include any District-owned parcels or surplus land in a future shoreline access analysis. | DOT/Road Services DNRP/Parks | VMILT VPD | a. This task is scheduled to be collaboratively initiated, by Roads and Parks, in Q3 2019. b. This task is scheduled to be collaboratively initiated, by Roads and Parks, in Q3 2019. c. Upon initiation of P-3(a) and (b), Parks will reach out to Vashon Park District to facilitate this action. | a. No b. No c. No | a. n/a b. n/a c. n/a | a. n/a b. n/a c. n/a |
| Chapter 9: Transportation |  |  |  |  |
| T-1 | King County should provide additional alternative services for Island residents, such as: a. Implement the Community Van program which provides Metro vans for local prescheduled group trips that are arranged by a Community Transportation Coordinator and driven by volunteer drivers to meet community-identified transportation needs. b. Promote mobile carpool matching services that help people find one-time carpools in real time. | DOT/Metro | -- | a. The Community Van program has been implemented in partnership with the Vashon-Murray Island Chamber of Commerce. The service had its first revenue trip on January 13, 2018. As of February 2019, the Community Van pilot has recruited 23 volunteer drivers, who have driven 246 trips with a total of 906 boardings. b. The project partner, the Vashon-Maury Island Chamber of Commerce, and Metro agreed not to pursue Real-Time Ride Rideshare at this time. Together with the Chamber, Metro is for the moment focused on building on the success of the Community Van pilot, which came from that same outreach. As part of the same planning process, Metro was also able to plan for and restore Sunday service on Vashon Island, which had been a longstanding request and was identified as a high priority at the time. | No | n/a | n/a |
| Chapter 10: Services, Facilities and Utilities |  |  |  |  |
| F-8 | The VMIGPC should implement educational programs that monitor water quality and reduce potential pollution sources. Programs may include volunteer stream invertebrate monitoring, pesticide reduction education, septic pollution, well head protection and reducing stormwater runoff. | VMIGPC | DNRP/WLRD DPER KCD | The VMIGPC is funding numerous pesticide reduction programs, including working with island retailers to remove roundup from their shelves, holding gardening workshops, and tabling at the farmers market. VMIGPC is also funding volunteer water quality monitoring programs through the Vashon Nature Center, with whom the VMIGPC is also implementing the WLRD-sponsored rain gardens at the Vashon IGA to reduce stormwater impacts into Shinglemill Creek. | No | n/a | n/a |
| F-15 | King County shall analyze results of the Impact Bioenergy assessment and feasibility study in late 2018/early 2019 and determine next steps that will have the greatest impact on reducing the Island’s solid waste stream. | DNPR/SWD | CBO | The kick-off of a one-year anaerobic digestion pilot project for Impact Bioenergy occurred on April 16, 2019. SWD plans to issue a Request For Proposals in June 2019 for processing of organic waste at the Vashon Transfer Station. Data from Impact Bioenergy study and pilot will inform SWD feasibility study. | No | n/a | n/a |

Priority 2 Implementation Actions (Mid-Term, 2020-2022)

| Policy No. | Priority 2 Implementing Action – 2020-2022 | Responsible Party | 1. Current Status, as of 4/25/19 | 2. Are policy, code, or plan changes needed to proceed with implementation? | 3. Are those changes included in 2020 KCCP? | 4. If not on schedule, a) why and b) updated timeline |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Lead | Support |  |  |  |  |
| Chapter 5: Rural Area and Natural Resource Lands |  |  |  |  |
| R-9 | King County’s Farmland Protection Program shall work with local partners to explore opportunities for additional farmland protection on Vashon-Maury Island. Given the island’s limited groundwater supply, such a strategy should examine water rights and ensure that lands preserved for agriculture contain adequate water supply. | DNRP/WLRD | DPER KCD | This action item is ahead of schedule. Beginning in 2018, DNPR/WLRD has increased Farmland Preservation Program (FPP) attention on rural farmland in the County, including Vashon-Maury Island. These efforts included recently a recent acquisition of a FPP easement on Vashon, with several more in the pipeline. Vashon-Maury Island will be included in a countywide study that will establish a predicted range of agricultural water needs and sub-basin and agricultural zone-specific opportunities for solutions. | No | n/a | n/a |
| R-10 | a. King County shall review King County Code 21A and other pertinent policies for opportunities to streamline and create positive incentives for agritourism activities. b. King County shall support on-farm events that feature agricultural values and landscapes but do not detract from long-term commercial viability of agricultural businesses. | DPER | DNRP/WLRD DPH | a. Per the adopted Subarea Plan, this work will begin in 2020-2022. b. Per the adopted Subarea Plan, this work will begin in 2020-2022. | a. No b. No | a. n/a b. n/a | a. n/a b. n/a |
| Chapter 6: Housing and Human Services |  |  |  |  |
| H-7 | King County shall research universal design educational tools and partnerships and examine potential code or policy incentives to improve the accessibility of owner-occupied and rental dwellings (e.g. residential designer/contractor workshops, expedite building permits that contain universal design features, etc.). | DPER | Homebuilders | Per the adopted Subarea Plan, this work will begin in 2020-2022. | No | n/a | n/a |
| Chapter 8: Parks, Open Space & Cultural Resources |  |  |  |  |
| P-2 | To consolidate ownership, improve maintenance, and provide for improved land management schemes, King County shall develop a mid-to-long-term strategy that supports mutually beneficial exchanges between Vashon Park District, the Vashon-Maury Island Land Trust and King County Parks including consideration of special lease agreements, underutilized parcels, and related issues. | DNRP/Parks | VPD VMILT | Per the adopted Subarea Plan, this work will begin in 2020-2022. | No | n/a | n/a |
| P-7 | King County should form an interdepartmental and interagency working committee to seek funding to conduct a feasibility study that would assess the physical, environmental, financial and design feasibility for a new Regional Trail or other active transportation facility. | DNRP/Parks | DOT/Road Services VMILT | Per the adopted Subarea Plan, this work will begin in 2020-2022. | No | n/a | n/a |
| P-8 | King County should form a working committee to seek funding to: a. Scope, identify funding for, and conduct a feasibility study to expand the existing backcountry trail network, including reviewing whether trails are appropriate on state and County-owned land that is subject to forest management plans in areas that are logged; and b. Pursue voluntary public easements across private lands in order to connect public trails, potentially by exploring changes to existing King County conservation easement programs. | DNRP/Parks | DOT/Road Services VMILT CBO | Per the adopted Subarea Plan, this work will begin in 2020-2022. There are ongoing discussions and actions with VMILT to expand the trail network and promote easements. DNPR has discussed forming the committee. | No | n/a | n/a |
| P-12 | King County shall evaluate opportunities to install permanent and temporary public art in County buildings and facilities, such as: Use creative design elements such as paint, tile and texture at public crosswalks and squares Purchase and display local art inside and/or outside government facilities Solicit local artist involvement in the design and/or review of new or expanded government buildings Install island art on bicycle racks and benches at select/visible locations. | Any affected department |  | Per the adopted Subarea Plan, this work will begin in 2020-2022. | No | n/a | n/a |
| Chapter 9: Transportation |  |  |  |  |
| T-8 | King County should review the standards for roads in the Vashon Rural Town for compatibility with nonmotorized uses and potential nonmotorized infrastructure improvement needs as part of future countywide policy and needs analyses. | DOT/Road Services | -- | Per the adopted Subarea Plan, this work will begin in 2020-2022. | No | n/a | n/a |
| T-10 | In collaboration with the King County Airport District #1, King County shall perform a standard airport/land use compatibility appraisal to ensure minimum FAA guidelines and other safety precautions are in place for future development within a 1-mile radius of the runway. | DPER | KCAD VIF&R | Per the adopted Subarea Plan, this work will begin in 2020-2022. | No | n/a | n/a |

Responsible Party Acronyms

CBO = Community-Based Organizations (i.e., Neighborhood and Business Associations,

Faith-Based Organizations, Philanthropic Organizations)

DCHS = King County Department of Community and Human Services

DNR = Washington State Department of Natural Resources

DNRP = King County Department of Natural Resources and Parks (Parks and Recreation Division (Parks), Solid Waste Division (SWD), Water and Land Resources Division (WLRD))

DOT = King County Department of Transportation (now named the Department of Local Services – Road Services Division, or METRO)

DPER = King County Department of Permitting and Environmental Review (now named the Department of Local Services – Permitting Division)

DPH = Public Health – Seattle and King County (Environmental Health Division)

KCAD = King County Airport District 1 (Vashon)

KCD = King Conservation District

VIF&R = Vashon Island Fire and Rescue

VMIGPC = Vashon-Maury Island Groundwater Protection Committee

VMILT = Vashon-Maury Island Land Trust

VPD = Vashon Park District

Priority levels were identified by the lead King County agency based on considerations such as existing work programs, staff resources, budget considerations, etc.

Public Benefit Rating System

After adoption of the Subarea Plan, the Department of Permitting and Environmental Review (DPER) was restructured and is now the Permitting Division of the Department of Local Services.

After adoption of the Subarea Plan, the Road Services Division of the Department of Transportation (DOT) was restructured and is now the Road Services Division of the Department of Local Services.

After adoption of the Subarea Plan, the Metro Transit Division of the Department of Transportation (DOT) was restructured and is now the Department of Metro Transit.