STAFF REPORT

| Agenda Item: | 6 | Name: | Miranda Leskinen |
| --- | --- | --- | --- |
| Proposed No.: | 2019-0156 | Date: | April 23, 2019 |

SUBJECT

A motion acknowledging receipt of a PSERN status report in compliance with Ordinance 18409, Section 132, as amended by Ordinance 18734, Section 1, Proviso P7.

SUMMARY

The Puget Sound Emergency Radio Network (PSERN) project, once completed, will replace and upgrade the County's current emergency radio network. King County is responsible for leading and implementing the PSERN project through completion.

Proposed Motion 2019-0156 would acknowledge receipt of the PSERN status report in compliance with Section 132 of the 2017-2018 Biennial Budget Ordinance (Ordinance 18409, as amended by Ordinance 18734, Section 1, Proviso P7).

Ordinance 18734, enacted in May 2018, authorized approximately $123.5 million in supplemental expenditure authority to the PSERN Capital Fund for projected expenditures through July 2019, and included a proviso requesting a project status report by the Capital Projects Oversight Program of the Auditor’s Office by April 2019. The proviso requires that Council pass a motion acknowledging receipt of the report in order to release $100,000 of provisoed funds to the project. The proposed motion, if passed by Council, would fulfill the proviso requirement.

BACKGROUND

On April 28, 2015, King County voters approved a nine-year, $273 million property tax levy to fund PSERN, the replacement of the King County emergency radio communications system.

PSERN is a complex project with multiple tasks over the course of the implementation period including radio site design, acquisition and construction, as well as the acquisition of radios, consoles, and data systems. Once completed, PSERN will replace and upgrade the county’s over 20-years old emergency radio communications system, which is used to dispatch responders to incidents and allow responders to communicate with each other at those incidents.

The current county emergency radio communications system, also known as KCERCS, is owned by King County, the City of Seattle, Valley Communications Center (Valley Com), and the Eastside Public Safety Communications Agency (EPSCA). The vendor for the current system no longer provides existing system support, which it indicated it would no longer provide after 2018.

Implementation Interlocal Agreement. Under the terms of the PSERN Implementation Interlocal Agreement, King County is responsible for leading and implementing the PSERN project. Oversight during that implementation period is being conducted by a Joint Board, composed of one non-voting chair (the Executive or the Executive's designee) and four voting representatives, one representing each of the current system's owners. The four voting members of the Joint Board may appoint two additional non-voting participants: a chief of a police agency and a chief of a fire agency.

Under the terms of the contract between Motorola and the county, Motorola will provide design, development, implementation, testing and ongoing support, maintenance and upgrade services for the PSERN project.

Operations Memorandum of Agreement. Per a Memorandum of Agreement Regarding Future Operation of the Puget Sound Emergency Radio Network, ownership and operation and maintenance of PSERN after completion would be vested in a new, nonprofit organization governed by a Board of Directors. The parties (King County, the City of Seattle, Valley Com member cities and EPSCA member cities) will need to approve an Operations Period Interlocal agreement to create the PSERN Operator and establish the terms for governance of the PSERN Operator and the terms under which the PSERN Operator will undertake the ownership, operations, maintenance, management and on-going upgrading/replacing of the PSERN System. The Operations ILA is currently estimated to be transmitted to these legislative bodies in Q4 2019 for approval.

Council Committee Oversight. Motion 14437, enacted in October 2015, requires the Executive to brief the Law, Justice and Emergency Management Committee (or its successor) on a quarterly basis on the status of the PSERN project in relation to the project’s identified milestones, as indicated in the report attached to Motion 14437 (2015-RPT0134). The Regional Policy Committee has also requested to receive quarterly project updates. The Regional Policy Committee received a 2018 Q4/2019 Q1 briefing on March 13, 2019.

Project Budget and Schedule. As indicated by PSERN project staff, there have been several key events affecting the project that made it necessary for project staff to reevaluate both the original schedule and budget baselines, such as the system vendor needing more time than originally planned for testing the system once it is built, the addition of new radio tower sites to the site design, some radio tower sites becoming unviable, longer than anticipated lease negotiation processes, and necessary substantive technical changes to the system design. As further indicated, these issues resulted in the need for the project to redo their project budget and schedule. The PSERN Joint Board approved the new (re-baselined) PSERN project budget and schedule in January 2018. The Regional Policy Committee and the Law and Justice Committee were each briefed on the re-baselined budget and schedule in early 2018. An overview of the project budget, as of March 2019, is shown in Table 1.

Table 1: PSERN Project Budget Overview

2018 Supplemental Appropriation – Ordinance 18734. The PSERN project is subject to mandatory phased appropriations, meaning appropriation by project phases, as described in King County Code. A supplemental budget appropriation request for $204 million to fund the final two phases of the project (Implementation and Close-out) was transmitted to Council in April 2018. The adopted legislation (Ordinance 18734), as amended by the BFM Committee, authorized approximately $123.5 million in expenditure authority (rather than the full $204 million) to the PSERN Capital Fund for projected expenditures through July 2019, with another supplemental appropriation request anticipated in 2019, and added a proviso requesting a report by April 2019 on the status of the project from the Auditor’s Office Capital Project Oversight Program. The proviso is further described later in this staff report.

Project Schedule. The project schedule, as of February 2019, is shown in Table 2. Table 2 shows how the re-baselined schedule has impacted the major project milestones. Upon completion of re-baselining, project staff indicated that the identified project milestones would be reevaluated and potentially updated to provide a more defined measure of the project’s progress.

Table 2: PSERN Implementation Milestones, as of February 2019

Original Expected Completion Dates and Revised Expected Completion Dates

| PSERN PROJECT MILESTONES |  | Original Project Completion Date (As of December 2014 & 40% design) | Re-Baselined Expected Completion Date (As of September 2017 & 99% design) | Current Expected Completion Date (As of 2/28/19) |
| --- | --- | --- | --- | --- |
| Project Planning |  | Aug 2012 | Aug 2012 | Aug 2012 |
| Preliminary System Design |  | Dec 2014 | Dec 2014 | Dec 2014 |
| Final System Design |  | Jul 2017 | Sep 2017 | Sep 2017 |
| Motorola Site Construction Includes 2015-RPT0134- Identified Milestone #6 (Site Construction Complete) |  | Oct 2017 | Oct 2018 | Sep 2019* |
| Radio System Core and Initial Dispatch Console Transition |  | n/a | Jan 2019 | Nov 2019* (Plan A) Nov 2019* (Plan B) |
| PSERN (King County) Site Construction Includes 2015-RPT0134- Identified Milestones #1(Site leasing & final site design); #2 (Construction Permitting); and #6 (Site Construction Complete) |  | Oct 2017 | Aug 2019 | Dec 2019* |
| PSERN Non-Profit Operator Formation Includes 2015-RPT0134- Identified Milestone #10 (PSERN Non-profit Operator Formation) |  | Sep 2019 | Nov 2019 | Aug 2020* |
| Radio Site Equipment Installations (Motorola) Includes 2015-RPT0134- Identified Milestone #7 (Backhaul System Implementation) and #8 (Land Mobile Radio System Implementation) |  | Sep 2018 | Jul 2020 | Aug 2020* |
| System Optimization and Coverage Testing Includes 2015-RPT0134- Identified Milestone #9 (System Optimization and Testing) |  | May 2019 | Aug 2020 | Oct 2020* |
| Deploy & Transition End User Radios Includes 2015-RPT0134- Identified Milestone #11 (Transition Users to PSERN System) |  | Mar 2020 | Dec 2020 | Sep 2021* |
| Project Substantially Complete/ Transfer to PSERN Operator Includes 2015-RPT0134- Identified Milestone #12 (Full System Acceptance) |  | Sep 2020 | May 2021 | Feb 2022* |
| PSERN Project Closeout Includes 2015-RPT0134- Identified Milestone #13 (Project Closeout) |  | Sep 2021 | Dec 2022 | May 2023* |

PSERN Radio Tower Sites. Of the current 57 PSERN radio tower sites, site development work remains to be completed at 39 sites (including Motorola and County-led sites). Upon completion of the site development work at a radio tower site, the PSERN radio equipment (e.g. antennas) is installed at the site by Motorola. A summary of remaining site development work prepared by project staff is provided as Attachment 2 to this staff report.

Project Scope & In-Building Coverage. The PSERN project’s broad definition of “in-building coverage” refers to the ability of first responders to communicate with each other inside and outside of a building. In-building coverage was not included in the original project scope. As indicated by PSERN project staff, project partner representatives requested to revisit the topic of in-building coverage requirements and criteria under PSERN. Follow-up activities relating to this request have included formation of an in-building task force and outreach to building owners throughout the county to ensure that they are aware of PSERN and how their in-building systems can connect to PSERN.

In-Building Task Force. An in-building task force was formed, as indicated by PSERN project staff, comprised of first responders who will be using the system and the technical staff who run the current emergency radio communications system in King County. This group proposed utilizing the assistance of a technical consultant with expertise on in-building coverage, which the Joint Board approved at its October 26, 2017 meeting.

The task force reviewed multiple options for addressing in-building coverage concerns in King County and evaluated the options based on operational, technical and financial implications. Of the identified options, the task force-recommended option entailed a three-layered approach for addressing in-building coverage concerns in King County, including addressing in-building coverage in high and medium density areas with thirteen additional radio tower sites; bringing the exterior PSERN radio system coverage inside of building with distributed antenna systems; and utilizing vehicular repeaters for sustained incidents where coverage is challenging.

On August 23, 2018, the Joint Board voted to add in-building coverage to the project scope; the scope includes three additional radio towers. The project has asked Motorola for a bid and impact statement for adding the additional towers. Subject to Joint Board approval of the proposal, the project would execute a change order with Motorola to add the three in-building sites to the contract scope.

Of note, the most recent semiannual quality assessment consultant report on the project, dated December 2018, included a recommendation to re-baseline project schedule to update baseline project milestones completion estimates and correspond with pending scope changes resulting from the additional sites for enhanced in-building and an additional radio tower site for Cedar River Watershed coverage requested by the City of Seattle - Seattle Public Utilities. As indicated by project staff, the question of re-baselining will be asked of the Joint Board once these issues are resolved and the project will re-baseline if the Board agrees it is necessary.

King County Auditor Capital Projects Oversight. The Capital Projects Oversight (CPO) Program of the King County’s Auditor’s Office has released multiple reports on PSERN, including reports released in November 2015 and February 2017. Both of these reports focused on project scope, schedule, budget and risks, and included recommendations for the PSERN project team (identified in Table 3). Additionally, when the Law & Justice Committee was briefed in January 2018 on the re-baselined project budget and schedule, the committee also received a briefing from the Auditor’s Capital Project Oversight Program, which recommended to closely monitor the re-baselined project schedule for deviations or delays.

In May 2018, a follow up report by the Auditor’s Capital Project Oversight Program focusing on the status of the project toward completing recommendations from the November 2015 and February 2017 reports was presented to the Law and Justice Committee and to the Budget and Fiscal Management Committee. As indicated in the May 2018 report, four recommendations had been completed (#s 4-5 & 7-8); four recommendations were partially implemented (#s 1-3 and 6); and one recommendation (#9) remained unresolved.

Most recently, in April 2019, Council received a project status report from the Auditor’s Office Capital Project Oversight (CPO) Program. The report was requested in a proviso included in the most recent supplemental appropriation for the PSERN project (Ordinance 18734, Section 1, Proviso P7, amending Section 132 of the 2017-2018 Biennial Budget Ordinance – Ordinance 18409). As stated in the proviso:

“Of this appropriation for capital project 1126875, PSERN Capital, $100,000 shall not be expended or encumbered until a report by the capital projects oversight program on the status of the PSERN project is received by the council and the executive and the council passes a motion acknowledging receipt of the report. The report should include updates on the scope, schedule, budget, revenue forecast, risks of the project and progress toward fulfilling recommendations included in prior capital projects oversight program reports on PSERN released in November 2015 and February 2017. In accordance with K.C.C. 2.20.045, contingent on the council passing a motion to add the report to the work program for the auditor, the report should be provided to the council and the executive by April 1, 2019, and should be filed with the clerk of the council, who would retain the paper copy and distribute an electronic copy to all councilmembers, the council's chief of staff and the lead staff for the budget and fiscal management committee or its successor.”

ANALYSIS

Proposed Motion 2019-0156 would acknowledge receipt of the PSERN status report requested by Section 132 of the 2017-2018 Biennial Budget Ordinance (Ordinance 18409, Section 132, as amended by Ordinance 18734, Section 1, Proviso P7). Per the proviso, the report provides a status update on the PSERN project and progress toward fulfilling recommendations included in the November 2015 and February 2017 CPO reports.

As indicated in the report (Attachment A), the PSERN project is running nine months behind schedule and capital costs have increased by over $20 million from the re-baselined budget (refer also to Tables 1 and 2). As further indicated in the report, the PSERN Joint Board is in the process of evaluating proposed scope changes for additional towers, which could further impact both schedule and budget. Additionally, the report notes that the project will need to complete towers at a much quicker rate than it has over the past year to meet its current schedule. The report includes three new recommendations to address emerging risks, in addition to providing the status of previous report recommendations. A summary of CPO report recommendations to-date, including the three new recommendation, is provided in Table 3.

Table 3. CPO Report Recommendations Summary

| Report Recommendations | Status (as of April 2019) |
| --- | --- |
|  | Completed Auditor will no longer monitor | Partially Implemented Auditor will continue to monitor | Remains Unresolved Auditor will continue to monitor |
| November 2015 | 1 | Project team should revise the project schedule and communicate it to stakeholders before the end of 2015 to include reasonable time to accomplish the remaining tasks necessary to finish tower site construction. The schedule should be based on progress to date and identify the impact on the remainder of the project schedule. | X |  |  |
|  | 2 | Project team should improve reporting to clearly demonstrate to stakeholders the progress on leasing and constructing radio tower sites. Reporting should show how current cost and schedule forecasts compare to the assumptions used in the preliminary project estimate. | X |  |  |
|  | 3 | Project team should establish and document a project baseline prior to signing any construction contract. The baseline should use the certainties from the Motorola contract, best available information for tower site costs and schedule, and refined estimates of other costs |  | X |  |
|  | 4 | FBOD should provide ongoing technical assistance to the PSERN project team to help manage the cost risks of any construction work order contracts for this project. | X |  |  |
|  | 5 | Before seeking bids on a work order construction contract for the radio tower sites, the PSERN project team and FBOD should evaluate the relative benefits, costs, and risks specific to each site of inclusion in a work order contract or a traditional design-bid-build contract. This evaluation should be documented and result in a recommended approach for each individual site for consideration and approval by the project sponsor. | X |  |  |
| February 2017 | 6 | Project team should expand its outreach and communications plans to identify detailed, proactive engagement with building owners to allow them time to evaluate their systems and prepare for any needed changes. The complete updates should be presented at the first quarter 2017 PSERN project briefing to the Law and Justice Committee. |  | X |  |
|  | 7 | Project team should evaluate and compare the impacts on contract requirements, schedule, and costs for 1) the current plan of simultaneously constructing Primary Bounded Area sites, versus 2) extending the Primary Bounded Area site development schedule to allow construction of sites in sequence. Results of the evaluation should be presented at the first quarter 2017 PSERN briefing to the Law and Justice Committee. | X |  |  |
|  | 8 | Project team should complete updated site development cost estimates based on current information, should update the overall projects costs based on this information, and enter the project baseline costs into the County’s Project Information Center prior to the first quarter 2017 PSERN project briefing to the Law and Justice Committee. | X |  |  |
|  | 9 | Project team should refine the schedule to reflect realistic site development milestone achievement dates and should enter the project baseline schedule into the County’s Project Information Center prior to the first quarter 2017 PSERN project briefing to the Law and Justice Committee. |  |  | X |
| NEW April 2019 | 10 | PSERN should update the project schedule to account for all tower site delays after all site development procurement actions are complete including negotiations with Motorola over the new tower locations. |  |  | X |
|  | 11 | PSERN should provide Council a financing plan that documents the ability to fund infrastructure and equipment needed to achieve in-building coverage goals. PSERN should submit this plan to Council prior to requesting appropriations beyond the original $273 million levy approval. |  |  | X |
|  | 12 | PSERN should revise its project budget after all tower site construction is substantially complete and be ready for Motorola equipment installation. |  |  | X |

The report appears to meet the requirements of the proviso. The proposed motion, if passed by Council, would acknowledge receipt of the report and allow the provisoed funds restricted by Proviso P7 to be expended or encumbered by the PSERN project.

INVITED

- Ben Thompson, Deputy County Auditor, King County Auditor’s Office

- Michael Bowers, Capital Projects Oversight Analyst, King County Auditor’s Office

- David Mendel, Director, Emergency Radio Communications Division, King County Information Technology (KCIT)

ATTACHMENTS

- Proposed Motion 2019-0156 and following attachment:

- King County Auditor’s Office Puget Sound Emergency Radio Network Report, April 1, 2019

- PSERN Construction Status and Cost Estimates (prepared by PSERN project staff)

The 2017-2018 third omnibus (Ordinance 18766) included a supplemental appropriation of $1.4 million to the Radio Communication Services CIP Fund to extend the operational life of KCERCS until PSERN is completed. This work, funded out of fund balance reserves for radio infrastructure repair and replacement, includes replacing or sparing components at risk of failure, with an objective of maintaining current radio service availability and reliability of the existing system until it is replaced by PSERN.

Ordinance 18075.

The current members of the Joint Board are as follows:  Casey Sixkiller, non-voting Chair; Tanya Hannah, King County voting member; Chief Harold Scoggins, Seattle voting member; Kurt Triplett, EPSCA voting member; Lora Ueland, ValleyCom voting member; Chris Elwell, non-voting fire agency member; and Chief John Vinson, non-voting police agency member.

PSERN project staff indicate that the contract, with respect to duration, includes project implementation through 20 years after project completion.

In addition to the primary contract with Motorola, the Executive has hired consultants to develop the site design and to provide construction management oversight.

Ordinance 18074.

As indicated by PSERN project staff, the project provides a variety of reports and updates to several oversight and advisory groups on at least a monthly basis. Aside from Council committees, Executive Office leadership and KCIT leadership, the project also reports to the King County Auditor’s office, quality assurance consultants, King County Project Review board, PSERN Joint Board, PSERN Operations Board and PSERN Technical Committee.

2018-B0226, presented to the Law and Justice Committee on January 9, 2019, and 2018-B0022, presented to the Regional Policy Committee on February 14, 2018.

Three milestones identified in 2015-RPT0134 are not reported in Table 2, including Factory Acceptance Testing (milestone # 5), Site Construction Mid-point milestone (#3) and the Group 2 Site Leasing milestone (#4). Milestones #3 and #4 were eliminated, as previously reported and indicated by project staff, due to no longer being applicable to the project.

Current Completion dates, as indicated by project staff, assume that landlords meet proposed deadline for final agreement on leases. Additionally, dates do not assume worst case scenarios for wild fires and adverse weather conditions.

"n/a" for original schedule because this is a new milestone.

A Joint Board decision in 2018 moved this milestone date up by six months, from May 2020 to November 2019.

The Joint Board has requested a plan for how the remaining ten recommended by the task force could be funded and has set aside $1 million for an evaluation.

The report, prepared by CASE Associates Incorporated (CAI), includes recommendations for avoiding and/or responding to risks and issues identified by CAI that could impact the successful completion of the PSERN Project.

The report is available online at http://www.kingcounty.gov/~/media/depts/auditor/new-web-docs/2015/2015-cpo-psern/cpo-psern-final.ashx?la=en.

The report is available online at http://www.kingcounty.gov/~/media/depts/auditor/new-web-docs/2015/2015-cpo-psern/cpo-psern-2017.ashx?la=en.