## STAFF REPORT

| Agenda Item: | 7 | Name: | Mary Bourguignon |
| --- | --- | --- | --- |
| Proposed No.: | 2023-B0102 | Date: | October 18, 2023 |

SUBJECT

Today’s briefing will summarize progress on the planning and design of the RapidRide K and R lines, as required by a proviso to the County’s 2023-2024 budget ordinance.

SUMMARY

Metro currently operates seven RapidRide lines (A-F, H), and is working to develop five more lines (G, I, J, K, R) for planned openings between 2024 and 2030.

Work on the K and R lines was paused in 2020, then restarted in 2021. As part of the 2023-2024 budget, additional funding was appropriated to advance planning and design work on each line.

K Line

- Approximately 18-mile north-south corridor parallel to I-405 in Bellevue and Kirkland along portions of routes 255, 250, 245, 239, and 271

- Work was paused at one percent design, reached two to five percent in 2021

- 2023-2024 budget appropriated $7 million

- Goal to advance to 10 percent design and re-engage community, jurisdictions

- Capital costs estimated at $120 million (2023$)

- Goal of starting service in 2030

R Line

- Approximately eight-mile north-south corridor between Downtown Seattle and the Rainier Beach Link light rail station to upgrade the existing Route 7

- Work was paused in 2020 at approximately 10 percent design

- 2023-2024 budget appropriated $21.9 million

- Goal to begin final design, re-engage with community, City of Seattle

- Capital costs estimated at $129 million (2023$)

- Goal of starting service in 2028

BACKGROUND

RapidRide Implementation. RapidRide is the name of Metro’s bus rapid transit service. RapidRide lines offer high frequency operation; faster, more reliable trip times using exclusive lanes and/or transit signal priority at intersections; improved shelter waiting areas with off-board payment and real-time information at major stops; and branded buses and facilities with a unique ride and feel.

Metro currently operates seven RapidRide lines (A-F, H), and is working to develop five more lines (G, I, J, K, R) for planned openings between 2024 and 2030. Table 1 lists the existing RapidRide lines, as well as those currently under development.

Table 1. Rapid Ride Lines (Operating and Planned)

| Line | Pathway | Alignment Ordinance | Service Change Ordinance | Start Date |
| --- | --- | --- | --- | --- |
| A | Federal Way to Tukwila | 16725 | 16844 | Oct 2010 |
| B | Bellevue to Redmond | 16725 | 17100 | Oct 2011 |
| C | Westwood Village to South Lake Union | 16725 | 17320 | Sept 2012 |
| D | Crown Hill to Downtown Seattle | 16725 | 17320 | Sept 2012 |
| E | Aurora Village to Downtown Seattle | 17391 | 17584 | Feb 2014 |
| F | Burien to Renton | 17391 | 17584 | June 2014 |
| G | Madison Valley to Downtown Seattle | 19012 | -- | 2024 |
| H | Burien to Downtown Seattle | 18894 | 19422 | Mar 2023 |
| I | Renton to Auburn | 19098 | -- | 2026 |
| J | Downtown Seattle to U District | 19312 | -- | 2027 |
| K | Kirkland to Bellevue | -- | -- | 2030 |
| R | Rainier Beach to Downtown Seattle | -- | -- | 2028 |

Metro Connects, Metro’s long-range plan, anticipates that Metro will be operating 10 RapidRide lines (A-J) by 2026; 13 to 15 lines (including the K and R lines) by the mid- to late-2030s; and 19 to 23 lines by 2050. Metro Connects outlines a prioritization process to identify future lines beyond those listed above, in Table 1.

2021-2022 budget: pause on K and R progress. The 2021-2022 biennial budget was transmitted to the Council in September 2020, during the first year of the COVID-19 pandemic. Metro was experiencing financial and operational impacts from the pandemic, including significant declines in revenue, ridership, and fare recovery. As a result, the 2021-2022 budget paused work on the K and R RapidRide lines.

- K Line, an approximately 18-mile north-south corridor parallel to I-405 in Bellevue and Kirkland along portions of routes 255, 250, 245, 239, and 271, had received an initial appropriation of $3 million in the 2019-2020 budget for preliminary design work, with additional appropriations identified in Metro’s capital improvement plan (CIP) of $4.5 million that had been intended to be proposed for the 2021-2022 biennium and $57.9 million intended to be proposed for the 2023-2024 biennium, in anticipation of construction beginning in 2024.

However, as part of the transmitted 2021-2022 budget, Metro proposed that, because preliminary design work had only been partially completed prior to the onset of the pandemic (work on the K Line had reached one percent design) and because of the uncertainty around future capital funding, work on the line should be paused and no further capital appropriations should be made until a new implementation timeline could be developed.

- R Line, an approximately eight-mile north-south corridor between Downtown Seattle and the Rainier Beach Link light rail station to upgrade the existing Route 7, had completed planning through 10 percent design, although Metro had not yet sought federal NEPA environmental clearance.

The line had received an appropriation of $59 million in the 2019-2020 budget, but, based on a proposal from Metro that further work on this line be paused, the 2021-2022 budget disappropriated $54 million of that amount. Metro staff stated at the time that part of the reasoning to pause work on the R Line was that the R Line would replace Route 7, a route that already provided frequent all-day service.

In response to the proposal to pause work on these lines, the Council added a proviso requirement to the 2021-2022 budget ordinance that asked Metro to transmit a RapidRide Restart Report by September 30, 2021.

By mid-2021, when the mid-biennial supplemental budget ordinance was transmitted, Metro’s financial situation had improved due to an uptick in sales tax revenues and additional federal funding. In response to the improvement in Metro’s financial situation, the Council added an expenditure restriction to encumber $400,000 to be used for staff to continue design, planning, and community engagement, and to develop detailed capital program proposals for the K and R lines. In addition, the Council amended the proviso requirement to extend the due date for the RapidRide Restart Report until March 30, 2022, and to add more specificity about the work to be completed.

In late 2021, the Regional Transit Committee (RTC) and Council adopted an update to Metro Connects, Metro’s long-range plan. The updated Metro Connects states that 10 RapidRide lines (A-J) are expected to be in operation by 2026; 13 to 15 lines are expected to be in operation by the time of the Interim Network; and 19 to 23 lines are expected to be in operation by the time of the 2050 Network. Metro Connects states that the K and R lines have been prioritized as the next RapidRide lines to be implemented and that, because they have been prioritized for investment, they are not considered to be “candidate lines,” but rather are committed as the next two RapidRide lines to be developed.

2022 RapidRide Restart Report. The RapidRide Restart Report, which was transmitted in March 2022, covered progress on the K and R RapidRide lines. The report described the pre-pandemic status, as well as efforts undertaken during 2021 and planned for 2022, to advance planning and design work for the two lines:

- For the K Line, at the time work was paused, the K Line had just begun the preliminary design phase and was at about one percent design with estimated capital costs of $80 to $103 million (2021 dollars).

Prior to pausing work in 2020, Metro had developed a preferred alignment (from Eastgate Park and Ride to Totem Lake Transit Center) in coordination with the cities of Bellevue and Kirkland and local community members. As part of this effort, Metro had identified key capital improvements that would be needed, including roadway upgrades, intelligent transportation system (ITS) elements, station locations, and bike/pedestrian improvements.

Metro resumed planning efforts for the K Line at the beginning of 2021, allocating $600,000 for alternatives analysis and design, including identifying key improvements along the corridor and conducting initial assessments of conformity with local jurisdictions’ code and regulatory requirements. Revised capital cost estimates of $80-$103 million were developed in 2021, though these estimates will need to be updated because of construction cost inflation.

Metro continued its work in 2022, with additional technical work to further refine the conceptual design for improvements that present technical implementation challenges (such as how to integrate the K Line at the two termini).

- For the R Line, at the time work was paused, the R Line was midway through the preliminary design phase, at about 10 percent design with estimated capital costs of $90 to $100 million (2020 dollars).

Prior to work on the R Line being paused, Metro had prepared a corridor planning and upgrade report, which summarized the major capital improvements identified during the pre-design analysis for transit speed and reliability, passenger facilities, transit communications and technology, and pedestrian and bike access to transit.

The report stated that when funding is restored, Metro will advance the project into a NEPA environmental clearance but does not recommend doing additional work until ready to proceed with NEPA review.

Work during 2021 and into 2022 was limited to jurisdictional coordination with the Seattle Department of Transportation (SDOT) to determine if a future partnership is possible.

2023-2024 budget: additional appropriations. The adopted 2023-2024 budget appropriated funds to advance planning and design work for each line:

- K Line received an appropriation of $7 million to advance planning and design during 2023-2024 and then proceed with project design with the goal of starting service in 2030.

- R Line received an appropriation of $21.9 million to revisit the alternatives analysis and proceed with environmental documentation. At the time the budget was adopted, Metro anticipated that federal grants would finance approximately 60 percent of the estimated $130 million capital cost to develop the line, and that the City of Seattle could become a funding or delivery partner.

To track progress on the lines, the Council added a proviso requirement to the 2023-2024 budget requiring Metro to brief the RTC no later than November 30, 2023, on progress on the planning and design of the K and R lines. The briefing today is meant to fulfill that requirement and allow RTC members to weigh in on the work underway.

2023 progress to date. Metro will provide additional information during today’s meeting. Overall:

- For the K Line, Metro notes the K Line is now included in Metro’s 10-year financial plan at $120 million. Delivery could be as early as 2030. The plan for this biennium is to:

  - Advance work to 10 percent design

  - Re-engage the community

  - Work in partnership with Kirkland and Bellevue to:

    - Advance design and feasibility of candidate improvements from the K Line Roadmap

    - Develop a constrained scope and budget

    - Establish funding sources, including potential granting partnerships

    - Establish delivery schedule and methodology

  - Develop an alignment ordinance and Locally Preferred Alternative (LPA)

  - A consultant contract has been signed to restart work

  - Internal staff meetings will resume in October

- For the R Line, Metro notes that the R Line is now included in Metro’s six-year Capital Improvement Program at $129 million. Delivery could be as early as 2028. The plan for this biennium is to:

  - Refresh and update the 10 percent design, including updating the 10 percent scope, schedule, and cost estimate (this update work will be complete in early 2024, after which scoping for the Final Design phase will begin)

  - Work in partnership with the City of Seattle:

    - Rainier is a high priority corridor for the Seattle Department of Transportation (SDOT) for transit, multimodal, and safety investments

    - SDOT is working with Metro to assess partnership opportunities as Metro advances the R Line project

  - Begin final design

  - Re-engage the community

  - Develop an alignment ordinance

Metro’s presentation will include additional updates on each line.

ATTACHMENTS

- Metro presentation

INVITED

- Pierce Canser, System Expansion Integration Supervisor, Metro Transit Department

- Jerry Roberson, Project Manager R Line, Metro Transit Department

- Greg McKnight, Project Manager K Line, Metro Transit Department

Ordinance 19546, Section 114, Proviso P4

Motion 16153

The G, H, J, and R lines were/are being developed in collaboration with the City of Seattle, with capital improvements partially or fully funded from the Levy to Move Seattle.

Ordinance 19367

Since Metro Connects was adopted, the start date for the RapidRide J has moved from 2026 to 2027.

The Metro Connects Interim Network is envisioned for the completion of the Ballard and West Seattle Link light rail extensions (for costing purposes, estimated at 2035, but more likely late 2030s).

Ordinance 19367 requires a RapidRide Prioritization Plan, due to the Council by June 30, 2024, to identify the next candidate lines for development.

Ordinance 18835, Fund 3641, Project 1134292

NEPA = National Environmental Policy Act (link)

Ordinance 18835, Fund 3641, Project 1132326

Ordinance 19210, Fund 3641, Project 1132326

Ordinance 19210, Section 113, Proviso P1

Ordinance 19364

Ordinance 19367

Since Metro Connects was adopted, the start date for the RapidRide J has moved from 2026 to 2027.

The Interim Network is envisioned for the completion of the Ballard and West Seattle Link light rail extensions (for costing purposes, estimated at 2035). Metro staff have stated that the Interim Network was intentionally associated with transit expansion milestones, rather than specific dates (which Sound Transit has since delayed), because these milestones are what prompt major Metro service restructures. Updates to reflect changes in Sound Transit’s plans will be made through future updates to Metro Connects, as well as service change proposals.

Ordinance 19367, Attachment C, pp. 23, 100.

2022-RPT0044 (link)

RapidRide K Line (link)

RapidRide R Line (link)

These estimates are subject to inflation and will need to be finalized later in the process.

Ordinance 19546

The alternatives analysis that was conducted for the R Line studied future No-Build scenarios for 2024 and 2040, which were analyzed to determine the future intersection operations with the current roadway conditions, planned roadway improvements, and future volumes. Because this analysis was completed prior to the COVID-19 pandemic, Metro has indicated it must be reviewed and updated to address changes in traffic and roadway conditions that have occurred during the last several years.

Ordinance 10546, Section 114, Proviso P4