## Sheet1
US Department of Energy - Energy Efficiency Conservation Block Grant (EECBG)
Project/Program Status as of June 30, 2010
PROJECT TITLE | PRIMARY PROJECT MANAGER | DIVISION/SECTION | GRANT AWARD | YTD GRANT CODED EXPENDITURES | LTD GRANT CODED EXPENDITURES | GRANT BALANCE | STATUS
Black River facility LEED certification and lighting upgrade | Denise Thompson | FMD | 245000 | 26042 | 28221 | 216779 | Project underway, contracts with electrical firms and energy audit firms in place.
Earlington Building energy efficiency upgrades phase 1 | Maureen Thomas | FMD | 300000 | 0 | 0 | 300000 | Negotiating contract with energy services firm.
Maleng Regional Justice Center energy efficiency upgrades phase 2 | Stephen Swinburne | FMD | 805000 | 0 | 0 | 805000 | Negotiating contract with energy services firm.
Metro Transit East Base air compressor replacement | Ken Madden | DOT/Tran | 100000 | 44514 | 44514 | 55486 | Project nearing 90% design.
Metro Route 36 terminal overhead wire | Garret Stronks | DOT/Tran | 400000 | 28338 | 28338 | 371662 | Project design nearing completion, negotiating with property owners and city for wire attachment point permits.
Community based travel - transportation demand management | Matt Hansen | DOT/Tran | 150000 | 2977 | 2977 | 147023 | Project implementation has begun.
Vehicle electrification support at county facilities | Elizabeth Morgan | DOT | 700000 | 59366 | 61672 | 638328 | Site selection process continuing, site design underway for selected sites, preparing RFPs to be issued this fall.
Novelty Hill Road ITS | Aileen McManus | DOT/Roads | 300000 | 34581 | 34581 | 265419 | Project at 95% design.
Energy efficiency and conservation strategy (Buying Meter) | David Hartwell | DOT/Roads | 100000 | 28472 | 28472 | 71528 | Energy use meter purchased, building metering underway.
Engine/generator for Enumclaw dairy manure digestion and energy recovery project | John Smyth | DNRP | 160000 | 0 | 0 | 160000 | Project partners have secured final financing, NEPA documentation under review by USDOE.
Energy audit and implementation project | Carl Grodnik | DNRP/WW | 190000 | 0 | 0 | 190000 | Scope of initial energy audit negotiated, contracted with energy services firm to perform audit.
West Point Pre-aeration Blowers Replacement Project | Sibel Yildiz | DNRP/WW | 280000 | 29435 | 29435 | 250565 | Project in design phase.
Fluorescent bulb and tube market transformation | Lauren Cole | DNRP/SW | 100000 | 0 | 0 | 100000 | Project to begin in coming quarter once Council passes supplemental ordinance to provide budget authority.
Bow Lake Transfer Station Energy Upgrades (Cancelled) | (Cancelled) | DNRP/SW | 0 | 0 | 0 | 0 | Cancelled
Energy efficiency and sustainability | Chris Ricketts | DDES | 200000 | 7399 | 7299 | 192701 | Project underway as of April 2010.
Hybrid vehicle upgrades | Warren Cheney | DDES | 200000 | 0 | 0 | 200000 | Vehicles ordered, expect delivery this fall.
YWCA family village at Issaquah | Cheryl Markham | DCHS | 750000 | 0 | 0 | 750000 | Project under construction, EECBG elements are later in the project schedule, should be purchased and installed late 2010 or early 2011.
Korean Women's Association Senior city affordable housing | Cheryl Markham | DCHS | 250000 | 21947 | 250000 | 0 | Project complete.
Program and grant administration | Dave Morrison | DOT | 441000 | 42148 | 64433 | 376567 | Administration ongoing with internal site visits being scheduled in Q4 2010 to prepare for 2011 audits.
New Energy Solutions | Jared Jonson | DOT | 90000 | 1061 | 1061 | 88939 | Project underway, helping establish Energy Conference in Seattle this fall.
Community Greenhouse Gas Inventory | Josh Marx/Matt Kuharic | DNRP | 70000 | 0 | 0 | 70000 | Signed contract with consultant, project underway.
Engineering Tech Training | Dave Van Holde | DNRP | 125000 | 0 | 0 | 125000 | Project initiating in Q3 2010.
Green Schools Program | Lauren Cole, John Miller | DNRP | 125000 | 0 | 0 | 125000 | Project to begin in coming quarter once Council passes supplemental ordinance to provide budget authority.
Localize Sustainability Outreach | Richard Gelb | DNRP | 60000 | 0 | 0 | 60000 | Project scope finalized, determining most efficient method of web site development.
|  | Totals | 6141000 | 326280 | 581003 | 5559997
.
Prepared by Dave Morrison 8/18/2010