RCECC

PROJECT SCHEDULE

Updated June, 2006

Summary of Critical Schedule Milestones and Crosswalk of original project schedule:

Original		Actual

Date			Date

Full appropriation approved by King County Council		9/10/01			9/10/01

Bid Opening, early Sitework contract				10/11/01		10/11/01

Begin early Sitework Project					11/12/01		11/12/01

Advertising for Building Project bids				11/8/01			11/8/01

Bid Opening for Building Project				12/20/01		3/14/02

Begin Building Project work					1/2002			5/2002

Early Room Ready (Based on May 1, 2002 start)		3/2003			3/2003

Full operation &occupancy of Building 				Spring 2003		7/2003*

*(occupancy date selected by OEM & KCSO)