Project Management Plan

Green/Duwamish River Ecosystem Restoration Project

U.S. Army Corps of Engineers and King County, WA

Draft 11/15/01

1.0 General Management Strategy

1.1 General Overview of Agreement

This Project Management Plan (PMP) defines the scope of, and documents the process for, conducting Preconstruction Engineering and Design (PED) and studies for Phase 1 of the Green/Duwamish Ecosystem Restoration Project (ERP). The Green/Duwamish River Ecosystem Restoration Feasibility Report (2000), proposed that the construction of all 45 authorized sites identified in the Feasibility Report and authorized by Congress, be accomplished in a 10-year construction period in three phases (see section 2.1 for background information). The PMP is a consensus-driven document that provides a means for all parties involved to formally agree on the scope of the PED effort for the first phase, which involves the engineering and design of twenty projects. Parties involved are King County (the non-federal sponsor and referred to herein as Sponsor), cities participating in the Water Resource Inventory Area (WRIA) 9 Forum, and the U.S. Army Corps of Engineers (USACE) (see sections 1.3 and 4.1.1 for more information on the Forum’s function).

The PMP has been developed to plan, define, and control the development and delivery of the products to be completed during PED. The PMP documents the work requirements and the level of detail that will be necessary to initiate construction of those sites selected for Phase 1. With clearly defined work tasks, the PMP will provide a basis for cost and schedule control and minimize communication and review problems. The primary products of this PED phase include all the documents and analysis that will be necessary to construct those projects selected for Phase 1. These documents will be in sufficient detail to provide the basis for the Sponsor, its partnering jurisdictions, and the USACE to construct the selected sites. The PMP addresses the following topics related to the scope of PED:

- Tasks and responsibilities;

- Cost estimate of individual tasks and the total Phase 1 implementation cost;

- USACE and other professional criteria to assess the adequacy of the completed work effort, including references to regulations and other guidance that will be followed in performing and evaluating tasks;

- Schedule of performance and milestones;

- Specific coordination mechanisms between the parties involved;

- Procedures for reviewing and accepting the work of the parties involved in PED;

- Procedures leading up to the acceptance of a Project Cooperation Agreement for each site; and

- Procedures for managing and tracking work progress and budget expenditures.

1.2 Goal of PED

The goal of PED is to successfully complete design and permitting for a group of twenty projects constituting Phase 1 of the Green/Duwamish Ecosystem Restoration Project. Specific objectives include assuring federal and non-federal support for these projects, and assuring they will be designed to provide critically needed environmental restoration benefits at an affordable cost in a reasonable time frame. The Sponsor and its partnering jurisdictions are located throughout the entire watershed and are very concerned about the progressive degradation of the watershed and its fish and wildlife resources.

1.3 Committee Oversight

To date, the PED effort has concentrated on working with the ERP Technical Committee and the Program Management Committee (PMC) as described in Section 4.0 to develop this document.  The PMP was developed with input from the ERP Technical Committee comprising King County, cities within the basin, the City of Tacoma which obtains its municipal and industrial water supply from the basin, the Washington State Department of Fish and Wildlife (WDFW), the Muckleshoot Indian Tribe, Suquamish Indian Tribe, the U.S. Fish and Wildlife Service, the National Marine Fisheries Service, and local environmental and sportfishing interest groups.

Article III-A of the PED described a Design Coordination Team. In this PMP, this team will be described as the PMC, which will be comprised of staff from the USACE, County, and the cities.  The PMC will make ongoing decisions on how this PMP will be implemented.  Issues the PMC deems as significant will be presented to the WRIA 9 Forum for direction and/or decision.

While King County is the formal local sponsor for this PED phase, the cities involved in this effort are anticipated to be cost sharing participants through a combination of separate interlocal agreements enabling them to contribute funds to the Sponsor and of a separate regional funding source through the King Conservation District. Therefore, these cities have a particular need to be involved in management and oversight of PED and are referred to herein as partnering jurisdictions.

An Executive Committee comprising the elected officials of the cities of the WRIA 9 Forum and King County has accepted this PMP. The Executive Committee will be referred to herein as the WRIA 9 Forum or simply the Forum. The Forum was established as the governance structure for a planning process for salmon conservation and associated resource protection issues related to the Green/Duwamish Basin and a segment of Puget Sound adjacent to the basin.

2.0 Project Description

2.1 Background

The proposed restoration focuses on improving the overall health of the Green/Duwamish River Basin to enhance and restore fish and wildlife habitat. Of special interest are the habitat needs of the listed endangered species, chinook salmon and bull trout, present in the basin. The ERP was initiated in 1995 when the USACE, County, municipalities, and tribes in the watershed recognized the need to improve the natural resources in the basin. The USACE Ecosystem Restoration Program (Engineering Circular EC1105-2-210, Draft Ecosystem Restoration in the Civil Works Program, June 1, 1995) provided a convenient mechanism to address restoration needs in the basin. In 1997, the USACE completed the Green/Duwamish River Basin General Investigation – Ecosystem Restoration Study Reconnaissance Phase. Both the Green/Duwamish River Ecosystem Restoration Project Feasibility Report authorized under the Water Resource Development Act of 2000 and Programmatic Environmental Impact Statement (PEIS) were completed in 2000. Potential projects identified in the Feasibility Report and PEIS were proposed and screened by the ERP Technical Committee. Projects were scored according to environmental evaluation criteria and 48 sites were selected. The 48 sites which incorporated varying levels and degrees of restoration were then evaluated in an incremental cost analysis. Based on the results of the cost analysis, 45 sites were identified for construction in three phases over a 10-year period. The ERP Technical Committee then selected 20 sites for Phase 1 construction.

To complement the ecological criteria, local landowners and grass roots organizations provided input through a combination of public workshops and field trips. In these informal settings, the USACE received both verbal and written input to incorporate local needs and direction in the development of site specific restoration criteria supporting local goals. Assessing and incorporating the desires of landowners and local organizations into the restoration plan will continue throughout the PED phases.

Throughout this document, the Howard Hanson Dam Additional Water Storage Project will be mentioned. This project, a cost-shared effort by the USACE and the City of Tacoma, includes many restoration and mitigation sites upstream and downstream of Howard Hanson Dam that complement the ERP to provide an overall ecosystem restoration approach to the entire basin.  Additional information on this project is available at the USACE.

2.2 Project Purpose and Description

The purpose of the ERP is to improve ecosystem functions and processes in the Green/Duwamish Watershed and improve the quality, quantity, and connectivity of fish and wildlife habitat. The ERP maximizes site-specific benefits while generating basin-wide ecosystem restoration effects. It includes a multi-species approach to restore ecological resources and processes that would benefit multiple fish and wildlife species. The ERP incorporates programmatic measures aimed specifically at the rural portions of the basin. Here, there is a need to restore the natural physical processes that create habitat. Some examples of this include the introduction of gravel and large woody debris to the mainstem of the Green River, both of which are restricted by Howard Hanson Dam, and levee modification. These measures are intended to allow the river to meander within the floodplain and provide more aquatic habitat opportunities for fish and wildlife. Other site-specific design features include: culvert modifications and removal of stream blockages; restoration of estuarine/tidally influenced marsh habitat; alluvial wetland restoration; side channel modifications/restoration and reconnection; levee and revetment biostabilization, setbacks, and laybacks; tributary restoration; system wide revegetation; landslide rehabilitation; and slope and bank stabilization.

2.2.1 Authority.

The ERP was authorized under the Water Resources Development Act of 2000.

2.2.2 Authorized Project.

The Project, as authorized in 2000, is estimated to cost $112,000,000 (October 1999 price level). Project actions would enhance/restore over 1,900 acres of habitat or migratory corridors through implementation of restoration features on 45 distinct project sites and several systematic sites. Features would be implemented in 3 phases over a 10-year construction period.

2.2.3 Project Sponsorship.

The Feasibility Study and the PED effort will be sponsored by King County, with financial assistance from specific cities in the Forum.

2.3 Costs

The Phase 1 PED effort is estimated at $3,000,000.  Attached to the end of this document are the following tables:

- Table 1 shows the PED costs by year.

- Table 1a shows the breakdown of sites by year and construction costs.

- Table 2 shows the breakdown of costs by construction costs, real estate costs, real estate credit, contract type and project delivery team member cost on each site.

- Table 3 shows a breakdown of these sites by year and federal and non-federal component.

2.4 Project Schedule

Attached to this PMP are Figures 1, 2 and 3. Figure 1 is a schedule for the systematic studies, Figure 2 is a typical site schedule, and Figure 3 is a schedule for the 20 projects recommended in Phase 1.

3.0 Scoping of Preconstruction Engineering and Design

3.1 Current Scope

The following section discusses the Phase 1 project sites, the systematic studies and programmatic initiatives, and project management considerations. The initial list of projects and systematic studies that are represented in this document are described below.

3.1.1 Project Sites

3.1.1.1  Project Selection Criteria

The following is a list of criteria created and used by the ERP Technical Committee to select the 20 sites included in Phase 1:

- Local funding availability;

- Simplicity of  permitting;

- Real estate availability;

- Likelihood of significant habitat improvements for threatened species (chinook salmon, bull trout) and high feasibility phase evaluation score;

- Cost saving opportunities (e.g., availability of SeaTac airport 3rd runway project for fill disposal);

- Consistency with WRIA 9 Habitat and Limiting Factors Reconnaissance Assessment Report;

- Potential to serve as a demonstration project to help gain public support;

- Political considerations (e.g., goal of including projects in many of the partnering municipalities, public visibility; public safety issues);

- Geographic location – goal to distribute sites throughout the Green/Duwamish Basin to provide Phase 1 habitat improvements in a variety of ecological settings and landscapes; and

- Potential availability of additional funding sources (e.g., grant opportunities, local funding).

      - Individual Site Proposal Descriptions

The following is a short description of each selected site and elements of interest related to each site. Cost estimates given below are for the PED design phase work only. These cost estimates are approximate and will be subject to modification through the development of site-specific PMPs as described in Section 4.0. The construction schedule is shown in Figure 3.

Burns Creek:

PED Design Cost: $70,800. Burns Creek flows into the Green River at about River Mile (RM) 38 at the upstream end of Lones Levee. Burns Creek is about 2.1 miles long and at one time supported 5 species of anadromous salmon. The major issues associated with this project are the control of sediment from Bell Ravine and obtaining landowners’ approval to plant the buffers required for the full restoration of the stream. A final decision to move forward with PED design for this site will be based on the evaluation of landowner willingness and likely Sponsor construction costs. The proposed project calls for reducing sediment delivery from Bell Ravine into Burns Creek. In addition, this project calls for plantings along the toe of the slides in the ravine to help stabilize them, placing wood in the stream, fencing off live stock, control of invasive species, and planting riparian vegetation for the full length of the stream.

Elliott Bay Nearshore:

PED Design Cost: $34,400. This site design calls for placement of rock at the minus 30-foot contour at several locations in Elliott Bay in order to provide more diverse habitat. A demonstration project involving placement of small quantities of rock was implemented during the feasibility phase. Monitoring of these sites has shown a significant increase in marine life in and around these rock locations. The major issue will be coordination of this project with the resource agencies to ensure that the site is acceptable and materials are available before construction.

Gale Creek:

PED Design Cost: $51,750. This site calls for the replacement of an eight by 12-foot box culvert which is perched by two to three feet at its downstream end with a 50-foot bridge that will allow full access of fish to one of the larger stream basins upstream of Howard Hanson Dam. Geotechnical investigations at this site will include the determination of the adequacy of the abutment material for the proposed bridge.

Green River Park:

PED Design Cost: $49,400. This site is located at about RM 24.  The proposal calls for the construction of a 600-foot backwater slough into parkland owned by the City of Kent. The slough will provide summer rearing habitat at its mouth and fall and winter flood refuge throughout the entire channel length. One of the primary issues will be finding an appropriate disposal site for the excavated material.

Horsehead Bend:

PED Design Cost: $52,500. This site is located two miles upstream of the Green River Park site at RM 26.  This proposal calls for a 1,300-foot side channel excavated along the alignment of an old river channel. This site would also provide summer habitat at its lower end and flood refuge throughout the entire channel. A primary issue will be finding an appropriate disposal site for this excavated material.

Kanaskat North Side Channel:

PED Design Cost: $52,200. This site lies in an old river meander on the north side of the river several miles downstream of the Tacoma Diversion Dam at about RM 58. The proposed plan consists of constructing permanent access between the river and the downstream end of the former channel for fish access during all periods of the year, and tying this channel into a supplemental water source. The channel would be used for both fish and wildlife habitat and as a refuge channel during high flows. The channel is 3,600-feet long and has excellent riparian canopy for the majority of its length. In addition to the typical design and analysis elements described in Section 3.2.2, an appropriate source of ground water or river water to feed this channel must be determined. Two piezometers will be placed at the upstream end of the proposed channel and a groundwater pumpdown test will be performed to determine if a groundwater source is recommended prior to construction.

Lake Meridian Outlet:

PED Design Cost:  $85,000. This site is located in the Soos Creek Basin in the City of Kent. The outlet channel from Lake Meridian currently flows through a series of road ditches until it enters Soos Creek. The proposal calls for the construction of a new stream channel on public lands with a 100-foot riparian buffer, stream habitat amenities, and a new connection to Soos Creek. Some of the construction and design issues for this site include determining the subsurface condition of the proposed stream corridor so the stream does not disappear into its new channel, and a conducting a hydraulic design analysis to ensure the stream will provide functioning fish habitat in its new alignment.

Lones Levee:

PED Design Cost:  $97,800. The Lones Levee site is one of several training levees on the Middle Green River proposed for removal to allow the river to migrate as much as possible within its former meander bend. The proposal calls for excavating the entire levee and replacing it with a small setback levee constructed well landward of the existing levee with a buried toe to create a hard point to ensure that this proposal will not damage adjacent farmlands and homes.    This project also includes the relocation of the lower portion of Burns Creek into its original channel. The major design issues associated with this project include finding a disposal site for the levee material and doing a comprehensive hydraulic and geomorphology study.

Mainstem Maintenance (Boeing and Fenster sites):

PED Design Cost:  $43,400. This proposal consists of five sites on the Green River between Auburn and Tukwila. The two sites that are now being proposed for construction in Phase 1 are Boeing and Fenster. Both of the sites consist of several miles of bank improvements in the urban area of the Green River. The project would include the construction of biostabilization alternatives to bank stabilization and relocating the bank landward of its present location where possible. It will be necessary to determine whether this bioengineering technique will cause an increase in river elevation when compared to the condition of the river without the project.

Meridian Valley Creek:

PED Design Cost:  $63,500. This project is located in the City of Kent and consists of removing the creek from its current location in a 1000-foot long concrete flume and restoring it into a reconstructed natural channel connected to Soos Creek. Some of the issues to be considered include ensuring that the new stream bed and underlying geology will support perennial stream flow in the creek, and assessing and minimizing any wetland impacts associated with reconstruction of the stream mouth.

Middle Green Large Woody Debris (LWD) Demonstration Project:

PED Design Cost:  $94,350. One of the major limiting factors in the Middle Green River is the lack of large wood within the river channel and its flood plain. Much of the wood that could move down the system is trapped behind Howard Hanson Dam. Because of logging practices, this wood is much smaller than the material that historically moved down the Green River. In the past, large wood helped to hold gravel, trap food-generating debris, cause deep, cool pools to be formed, and generally made the river a great deal more diverse.  In this programmatic project, up to 40 large logjams throughout the Middle Green River are proposed over the ten-year life of the project. These jams could be of two different types. One is an “engineered log jam” where large key logs are placed in a jam along with numerous other racking and stacking pieces. The other type of jam places large pieces of wood instream, and lets the river provide the other components.  Phase 1 construction will consist of several examples of both types of jams and evaluation of their effectiveness both physically and biologically in the river system. The evaluation will provide insight as to which approaches should be used in subsequent design and construction phases. Design of these jams will be conducted under PED. The major issues associated with this project involve the potential for these jams to cause major changes in the river course and affect neighboring property, as well as the effects these structures could have on boater safety. The first jams will be placed only on public lands and only after close coordination with landowners, local citizens, and boater safety groups.

Middle Green Gravel:

PED Design Cost:  $45,400. Since 1954, Howard Hanson Dam has trapped gravel and limited its ability to move downstream into the middle Green River. Such gravel is critical for fish spawning in the main stem and also plays an important role in channel morphology. It is estimated that gravel scarcity is moving downstream at about 800 to 1,000-feet per year so that portions of the river as far downstream as the area around Flaming Geyser State Park are now lacking in gravel. If nothing is done, eventually this will degrade spawning habitat throughout the Middle Green River and further limit the river’s ability to flood its floodplain during large flow events. The gravel program proposed under the ERP, along with the Howard Hanson mitigation and restoration projects, will place enough gravel into the system to make up the deficit caused since 1954 and continue to furnish gravel to the system on a yearly basis. In the demonstration project being designed under PED and proposed for construction in Phase 1 of the ERP, up to 5,000 cubic yards of gravel per year would be placed in a location just upstream of Flaming Geyser State Park. The main issue associated with gravel placement is its effects on flood levels in the Middle and Lower Green River. Careful monitoring and modeling of gravel will determine effects and identify alternatives to alleviate them.

Mill Creek, Goedeke Reach:

PED Design Cost:  $66,500. This Mill Creek site is adjacent to Highway 167 just downstream of Peasley Canyon. A straight and shallow stream channel and a lack of riparian vegetation hinder the Geodeke Reach from functioning effectively as rearing habitat and storm refuge. The goal at this site is to create natural habitat for rearing and storm refuge by constructing a stream system with instream wood, riparian plantings and a realigned, contoured channel. Prior to construction, a comprehensive hydrological and sediment analysis is required to ensure that the site will function effectively.

Newaukum Creek:

PED Design Cost:  $205,950. The overall project calls for restoring up to 13 miles of  Newaukum Creek upstream from its confluence with the Green River. This Phase 1 proposal calls for restoring about one-third of this area. The plan calls for the placement of large wood in the stream and planting native vegetation in the riparian corridor for those areas being restored. Obtaining landowner permission to implement restoration projects on their property will be necessary. The County has been working with local landowners through several outreach meetings to keep them informed of project progress and to encourage participation.

Olson Creek:

PED Design Cost:  $55,250. Olson Creek is a tributary of the Green River and is located partially within the City of Auburn and partially within the County. The proposal calls for restoring the lower 1,500-feet of the stream by placing large wood in the stream, planting native vegetation in the lower reaches of the stream, and removing any upstream fish passage barriers. The project may include some modification of the culvert at the lower end of the project site under the Green River Road to assist fish passage.

Riverton Creek Restoration:

PED Design Cost:  $86,250. This site is located in the City of Tukwila immediately north and east of the intersection of State Route (SR) 99 and SR 599. The proposal includes restoring the lower section of this stream for year-round fish habitat and flood refuge and improving the access from the creek to the Duwamish River. The proposal includes riparian plantings, placement of large wood in the stream, and removing an existing flap gate where the stream enters the Duwamish River. The major concern on this site is the possible flooding impacts from the Duwamish River upstream when the flap gates are removed. Flood analysis will be conducted before the project is constructed.

Site One Duwamish:

PED Design Cost: $59,100. This site lies adjacent to the Duwamish River just north of South 112th in Tukwila. The proposal calls for the construction of an intertidal marsh. This project has the potential of being very beneficial to downstream migrating salmonids by providing refuge at the upstream end of the salt wedge. The construction will include excavating a significant amount of material from this site to reduce marsh elevations to intertidal levels. Riparian and marsh plantings and the placement of large wood will also take place. Initial tests at this site indicate the possible presence of hazardous materials on-site. Although their concentration is below current contamination guidelines, special clean-up procedures may be required prior to construction. Further testing may be necessary before making a final determination regarding clean up and construction.

Sunday Creek Revegetation:

PED Design Cost:  $37,600. Sunday Creek is located in the Upper Green River Basin approximately 2.5 miles upstream of the historic Lester town site. The length of the project is about three miles in an area where the stream lies under the BPA power line corridor. The practice in the past was for BPA to clear the power line corridors of vegetation under the power lines. In the case of Sunday Creek, this has created an area where the water temperature can increase over 5 degrees Fahrenheit in the three-mile site reach. The proposal calls for coordinating with BPA and the U.S. Forest Service in a joint effort to plant low-growing riparian species under the powerlines and to place large wood in the stream to help provide cover, food source, and shade. This may be included in the Volunteer Revegetation program described below.

Upper and Lower Springbrook Creek/Garrison Creek:

PED Design Cost:  $200,400. As part of the overall project, adding riparian plantings, relocating steam segments, and placing large woody debris in these streams will restore many drainages connected to the historic Black River. The downstream segment of this system is Springbrook Creek. Most of the creek lies in the cities of Renton and Kent. The Garrison Creek portion lies completely in the city of Kent. This Phase 1 design cost would include Upper and Lower Springbrook Creek and Garrison Creek. A subsequent PED design cost would include Mill Creek. The major concern is to provide outstanding fish habitat without compromising the ability of the creek to carry floodwaters.

Volunteer Revegetation:

PED Design Cost:  $19,200. This program was set up to promote habitat restoration in those areas not covered by the other 44 sites in the overall program. This program will provide up to $300,000 a year for plants, wood, and other materials that will be included in riparian restoration projects throughout the Green/Duwamish Basin. This program will support work done by volunteer organizations and schools, the Sponsor through its basin steward program, and many partnering jurisdictions and other stakeholder groups.

3.1.1.3 Site Design Elements and Project Delivery Disciplines

The following is a list of typical design analyses to be conducted for each site. Each site-specific PMP will outline the required design analyses.

Civil Design:

Site plans will be developed for each PED Phase 1 site, taking into account technical information generated pursuant to the other disciplines defined below. Final plans for the contractual advertisement package will be developed along with an estimate of construction quantities necessary for the development of the Micro Computer Aided Cost Estimating System (MCACES) government cost estimate. It is estimated that at least 6 design sheets per site will be required. The Civil Design effort will also be used as input to the local permitting process that will be done by the Sponsor.

Geotechnical Exploration:

This analysis will assess the stability of structures that are recommended as part of the restoration plan such as instream large woody debris placement or setback of flood control levees. Exploration will be necessary in restoration projects where a stream is being moved or modified to insure the availability of stable foundation that will support stream relocation in those areas.

Cultural Resources Analysis:

This analysis will determine if there are any significant historical or pre-historical impacts associated with the construction of the individual restoration sites. This effort will also include coordination with State Historic Preservation Officer and the local Indian tribes and cultural resource input to the Environmental Assessment.

Geomorphologic Analysis:

A geomorphologic analysis of the design elements of each restoration site will be conducted. Many of the proposals call for elimination of training levees or modifying river or stream channels. A geomorphologist will determine the effects that these river and stream modifications will have on upstream, downstream, and adjacent floodplain areas and help provide solutions that will be compatible with adjacent land uses and river functions.

Pre-Project Monitoring:

In order to evaluate the success or failure of the proposed projects, it is essential that the proposed sites be monitored prior to project construction. Therefore, it is anticipated that monitoring will be undertaken at each site included in the PMP during the design phase to collect necessary data to ultimately determine the success of the restoration feature. Pre-project monitoring will be site-specific.

Environmental Assessment and Permitting:

As discussed in the PEIS, each site may require its own Environmental Assessment.  Additionally, all of the projects will need environmental coordination and specific project permits. The USACE will be responsible for all federal permits including those associated with the Endangered Species Act and the Clean Water Act. The local jurisdiction will be responsible for all state and local permits.

Hazardous, Toxic and Radiological Waste (HTRW) Analysis:

This analysis will determine whether HTRW issues exist at each site. The analysis may be as simple as a literature search and field trip, or may require a more complex approach such as full subsurface exploration and testing of each site. If waste is found, a determination will be made regarding action to be taken.

Hydrology and Hydraulic (H&H) Analysis:

This analysis will determine hydrologic and hydraulic (flooding and erosion) impacts associated with projects involving the placement of material in the stream or river, and for design of river or stream channel features necessary to avoid, minimize, or mitigate those impacts. Information regarding flow characteristics of the stream or river for a given site will be prepared to assist in the design analysis.

Real Estate Analysis:

This analysis will help ensure that lands, easements, rights of way, relocation, and disposal areas needed for the ERP have been obtained. The analysis will provide input for the Project Cooperation Agreement (PCA) for each site. The PCA identifies the lands, easements, rights of way, relocation, and disposal area responsibilities, and the financial responsibilities of the federal and local sponsors for construction, operation, and maintenance of a given site or sites. The PCA is an agreement between the USACE and the local sponsor that is prepared separately for each restoration site. A product of the PED will be a PCA for each site and no additional costs for development of these PCAs will be required after the PED is completed. The Project Manager for USACE will be responsible for preparing the PCA for each site.

Cost Estimating Analysis:

The cost estimating analysis will use the Microcomputer Aided Cost Estimating System (MCACES) to prepare a cost estimate for each site. This cost estimate will be based on the quantity takeoffs provided by the Civil Design product delivery team. The estimate of construction costs will include contingencies.

Survey:

Each project site will be surveyed using existing USACE data, GIS files, and data from the county and cities to develop a current base map.  In general, 1 to 200-scale mapping for both plan views and cross sections will be developed for each site.  Some surveys will require field verification, depending on base map adequacy and the complexity of the individual project.

Specifications:

Construction specifications will be developed for each site to ensure that restoration elements will be constructed as designed and to appropriate engineering standards.  The specifications will assist the rest of the team in preparing the request for the proposal package that will be going out for bid prior to construction of the projects.

3.1.2 Systematic Studies and Programmatic Initiatives

3.1.2.1 Identification of Necessary Studies and Initiatives

In order to effectively implement the complex set of 20 projects included in this PED, a number of systematic studies have been identified that will each provide information necessary for design, permitting, and eventual construction of multiple sites (these studies are outlined in Table 1; all tables are attached and incorporated herein). Some of these studies were originally identified in the PEIS. In addition, several program-wide initiatives will also be completed to facilitate design and permitting. The systematic studies included in this PMP were identified and discussed in several scoping meetings with the ERP Technical Committee. Criteria for study identification included requirements of the EIS and studies the ERP Technical Committee determined would be necessary before project construction.

For each study and initiative, a project delivery team will be established to formally develop a detailed scope, budget, and deliverables, and to monitor study progress. This team may include appropriate USACE staff as well as representatives from the Sponsor, partnering jurisdictions, and ERP Technical Committee members as appropriate. The specific responsibilities and typical membership of these project delivery teams are described in Section 4.0.

Table 1 shows the cost estimates for the entire PED phase including each systematic study and the breakdown by years in which the studies will be conducted. The first bar chart (Figure 1) shows how this effort will be accomplished over a three-year period starting in FY 2002. The schedule for construction of the different sites took into consideration the prerequisite systematic studies that will need to be accomplished before certain sites can be constructed. Tables 1 and 2 list the studies and design efforts described below and their costs. Table 1a shows the construction costs for the different sites based on the Feasibility Report. Figures 1, 2, and 3 show the work schedule throughout the PED phase.

The following PED Phase 1 studies are the systematic studies and programmatic initiatives recommended by the ERP Technical Committee, endorsed by the Forum, and included herein for cost sharing. These studies will begin upon execution of the PED agreement. The costs shown below are those proposed for coverage under PED and associated cost-sharing agreements.

3.1.2.2 Descriptions of Systematic Studies and Programmatic Initiatives

Hydrologic and Engineering Management Plan (HEMP):

Cost: $300,000. This analysis includes a hydraulic model and geomorphic analysis of the mainstem Green River and key tributaries. This work is necessary before the major components of gravel and LWD placement can be incorporated in the project. This analysis will also include modeling input for specific projects throughout the basin.  The HEMP will be jointly funded by the Green/Duwamish Ecosystem Restoration Project under the PED agreement and by the Howard Hanson Dam Additional Water Storage Project, which will also use the results.

Baseline Biological Evaluation:

Cost: $100,000. This evaluation will use data collected by the existing screw trap at approximately RM 34. The study will estimate current fish populations in the Green River to: 1) determine the location and timing of migratory fish on a reach scale; 2) estimate current fish populations to determine if the restoration projects are helpful at a population level; and 3) provide information for individual ESA consultations needed for the LWD and gravel projects.  Most of the cost of this evaluation will go toward operating the screw trap. Additional funding may be provided from the Howard Hanson Dam Additional Water Storage Project and WDFW.  The USACE is working with WDFW, Muckleshoot Indian Tribe, and other resource agencies to operate the screw trap, collect data, and share information.

Monitoring Plan:

Cost: $35,000. This monitoring plan will establish clear goals, provide sampling protocols for data consistency, help establish a data base, describe how to develop a sampling plan, and provide adaptive management guidance and contingency plans. The PEIS requires that monitoring occur on a site-specific, reach, and basin scale.

Water Quality:

Cost: $30,000.  This study will attempt to quantify changes in certain water quality parameters that affect fish resulting from construction of restoration sites (turbidity, suspended solids, dissolved oxygen, and temperature). A two person crew would use a hydrolab and develop transects in the river in the proximity of construction projects. Water quality sampling will take place before construction. This data will be important during ESA consultation. Water quality sampling will occur during and after construction as part of the construction phase of this project.

Juvenile Residency in the Estuary:

Cost: $120,000. This study was adapted from the limiting factors analysis evaluation described in the PEIS. Little is known about how long juvenile salmon (chum, chinook, coho, sea-run cutthroat) reside in the lower Green River and Duwamish estuary. Increased residency time probably relates to increases in ocean survival and greater fish returns. This study will provide information about what habitats and locations are beneficial and whether juvenile fish increase in size and weight during their stay in the Duwamish.

Public Safety and Recreation:

Cost: $25,000. This effort includes dispersing public safety information to the Boating Safety Advisory Committee and other entities on the placement of large wood in the Middle Green River and root wads in the Lower Green River. A safety information web site, signage, and other materials to make the ERP compatible with boaters will be developed.

Real Estate, Landowner Outreach:

Cost: $10,000. Permission will be obtained from the State Department of Natural Resources (DNR) real estate section prior to construction of mainstem Green/Duwamish River. The DNR has jurisdiction over lands beneath rivers in the state. The landowner outreach initiated by the County throughout the basin will be continued, keeping landowners involved in the overall process and obtaining easements.

###### Maintenance Issues:

Cost: $5,000. Several workshops will be held on invasive species control in areas targeted for revegetation. Systematic methods of controlling invasive species will be developed as well as several test sites. Field trips to sites where successful alternatives have been tried will be conducted. Discussions will also be held on maintenance strategies that will be ultimately be outlined in the PCAs.

Cultural Resources Programmatic Agreement:

Cost: $10,000. In order to comply with the National Historic Preservation Act and honor commitments stipulated in the PEIS, the USACE is required to develop a Programmatic Agreement (PA) for the treatment of cultural resources with King County, affected tribes, the State Historic Preservation Officer, and the Advisory Council on Historic Preservation. The PA will set forth a plan detailing how to address the following for each ERP restoration site: 1) cultural resource inventory survey; 2) site evaluation; 3) tribal, King County, and SHPO consultation; 4) construction monitoring; 5) protocol for inadvertent discoveries; 6) treatment of human remains; and 7) permanent curation of field documents and cultural materials. In addition to being a requirement, the development of this PA early in the process will be more efficient and cost-effective than attempting to address these issues on a site-by-site basis.

3.1.3 Project Management

This effort will include all activities related to USACE management of the PED process.  Activities include: 1) coordinating with local, state, tribal and federal governmental agencies, ports, industry, interest groups, and the general public; 2) oversight management of USACE, Sponsor, and contracted efforts; 3) coordinating the public involvement program; 4) coordinating with the Sponsor; 5) attending meetings and conducting briefings throughout the course of the PED phase; 6) responding to congressional and other inquiries; 7) preparing budgetary documents and upward reporting; 8) programming, managing and tracking PED phase obligations and expenditures; and 9) managing numerous reviews of PED phase products, including reviews by the project delivery teams, technical review team, the USACE Northwestern Division and the PMC.

Detailed quarterly reports on scope, schedule, budget, and accomplishments to date shall be provided to the Sponsor and the PMC for each individual project and/or study, and programmatic initiative.

3.2 Cost Overruns and Scope Changes

The following section describes approaches for dealing with project scope or cost revisions through the use of project contingency funds, or through the USACE’s betterments and post-authorization change procedures. The potential use of USACE continuing authority programs for site additions is discussed as well.

3.2.1 Project Contingency

A total of $494,250 has been set aside to deal with cost overruns associated with work specified in this PMP scope. The overall contingency is equal to 20% of the combined cost of all of the site design, systematic study, and programmatic initiative work described in Table 1. Funds will be added to the contingency on an annual. If these funds are not used, they will carry over to the following year. If excess funds still remain at the end of the Design Agreement effort, these funds will be credited in the final accounting to reduce the overall cost of the Design Agreement. Use of the contingency funds must be approved by the USACE and the PMC and must be associated with a specific site, study, or programmatic initiative. If a modification is contemplated that would potentially add a new site or study to the overall PMP scope, associated costs should be proposed as a betterment or post-authorization change as described below.

Prior to using contingency funds, the USACE Project Manager must work with the Project Delivery Team for the site, study, or initiative for which the cost overrun is contemplated, to discuss alternatives or options for completion of the scope. These alternatives or options should be presented to the PMC early enough to allow the PMC to fully review them to decide whether the use of contingency funds is warranted. If possible, these alternatives should be presented when 75% or less of the site- or study-specific budget has been expended.

3.2.2 Site Additions and Major Modifications

During the course of PED design for the projects described above, it is possible that the Sponsor or one of its partnering jurisdictions may wish to add one or more additional sites or to request significant modifications to the scope of a project. Requests such as this will be discussed by the USACE, the Sponsor, and the PMC in order to determine which of the following approaches should be used to accomplish the scope change.

3.2.2.1 Betterment

Under a betterment, the PMC and the USACE would determine that the modification requested by the Sponsor or a partnering jurisdiction is beyond the functional intent and scope of the ERP and therefore is not eligible for cost sharing. For example, if a city wants to add a component to a site not addressed in the ERP such as flood control elements, the city could propose adding this as a betterment. Since a betterment would require 100% funding from the Sponsor and/or its partners, a decision to add a betterment would require approval by the PMC and the Sponsor, and would be dependent on the Sponsor’s ability to develop an agreement for provision of the necessary local funding from the city proposing the betterment. Any other similar changes could be made to a site as a betterment and funded 100% by the Sponsor or one of its partnering jurisdictions.

3.2.2.2 Post Authorization Change

If the PMC and the USACE determine that the modification requested by the Sponsor or partnering jurisdiction is consistent with the restoration intent of the program and a priority for inclusion in PED but beyond the current scope of PED, then the USACE may request a post-authorization change. An example would be a request by a city to add a restoration site or sites to the original 45 that were authorized by Congress. Since a post-authorization change would require additional Federal and Sponsor funding, a decision to pursue such a change would require approval by the PMC and the Sponsor and would be dependent on the Sponsor’s ability to develop an agreeable cost-sharing arrangement with the city proposing the change. If the PMC determines that the change justifies broad cost sharing among the jurisdictions, it could elect to utilize contingency funds for the change or could recommend to the Forum that the overall project cost (and local share) be increased. Alternatively one or more of the partnering jurisdictions could provide the additional local share required for the change.

If the PMC approves the proposed change and the Sponsor can develop suitable cost-sharing arrangements, then one or more PMC representatives would work with the USACE to prepare a General Reevaluation Report (GRR) which is a concise feasibility report for this site. Depending on the scope and cost of the Post Authorization Change, this report would be sent to the USACE Northwestern Division Office (Portland) for approval or to USACE Headquarters (D.C.). If it is a very large change, it would require approval from Congress. Less than a 20% variation from the original scope may be approved at the Division level.

## 3.2.2.3 Use of USACE Continuing Authority Programs

The PMC may determine that the most effective way to implement a proposed scope modification from the Sponsor or one of the partnering jurisdictions is to request project funding from the USACE through one of its continuing authority programs such as the Puget Sound Initiative or the programs implemented under Sections 205, 206, and 1135 of the Water Resources Development Act of (2000). In this case, the project would be pursued independent of the ERP through a separate cost sharing agreement between the USACE and one or more local jurisdictions. In all cases, the Sponsor must make the formal request for a betterment or post-authorization change on behalf of the partnering jurisdictions. A request for continuing authority funding can be made by any of the jurisdictions directly to the USACE.

4.0 Project Management and Coordination

4.1 Project Teams

Although the PED agreement calls only for a Design Coordination Team to oversee the PED Phase 1 portion of the Green River ERP, additional oversight will be required to conduct and manage the complex PED Phase 1 work. The function, membership, operating protocols, and tasks of each entity involved in overseeing PED are described below.

4.1.1   WRIA 9 Forum

## Function and Membership

The WRIA 9 Forum acts as the governing body for joint local sponsorship of PED Phase 1. The Forum is comprised of elected representatives from King County and cities having jurisdiction or major interests in the Green/Duwamish and Central Puget Sound Basins. Forum member jurisdictions have entered into an interlocal agreement enabling them to share local sponsorship responsibilities for PED Phase 1.

## Operating Protocols

The WRIA 9 Forum meets regularly as needed.

Operating protocols, including decision-making mechanisms, are as outlined in the Interlocal Agreement for the Watershed Basins within Water Resource Inventory Area 9, as originally executed in January 2001.

## Tasks

- Review Project information, including progress reports and financial status, as provided by the PMC.

- Address the following issues relating to scope of work and budget:

- Review PMC recommendations for addressing potential or actual cost overruns on the scope of work as documented in this PMP; decide on an appropriate mechanism (including study rescoping, recommending to partner jurisdictions’ legislatures to budget additional cost share amounts).

- Review and decide on PMC recommendations addressing potential scope of work additions to be cost-shared among partner jurisdictions.

- Review and decide on PMC recommendations for addressing potential deletions from the scope of work as documented in the PMP.

- Review and decide on any issues as forwarded for decision by the PMC.

4.1.2   Program Management Committee (Design Coordination Team per the PED Phase 1 Agreement)

Function

The PMC is responsible for ongoing PED Phase 1 oversight, including:

- monitoring work progress and budget and providing progress reports to the WRIA 9 Forum;

- approving scope and/or budget changes within the existing scope of the PED agreement including the contingency;

- forwarding appropriate issues for decision, including recommendations, as appropriate, to the WRIA 9 Forum; and

- where needed, addressing specific issues related to PED Phase 1 work such as design issues, anticipated real property and relocation requirements for implementing individual project sites, and anticipated requirements for operation, maintenance, repair, replacement and rehabilitation of individual project sites.

Membership

The PMC consists of:

- the USACE’s and the Sponsor’s overall Project Managers;

- other senior representatives as named by the Corps and the Sponsor; and

- one representative for each of the Sponsor’s partnering jurisdictions, as named by that jurisdiction.

## Operating Protocols

The Program Management Committee will meet monthly or as needed. Meetings will be co-chaired by the USACE’s and the Sponsor’s overall Project Managers. Except as otherwise specified, the PMC will make decisions by consensus.

Tasks

- Review and approve site-specific and study-specific PMPs.  As work progresses, the PMC will ensure that both site-specific and systematic project criteria are being met and will review and approve possible changes to criteria.

- Provide Project information and updates to the WRIA 9 Forum, including progress reports, financial status information, and any information necessary for the Forum to make decisions over which it has authority. The PMC Chairs are responsible for preparing briefing materials for the WRIA 9 Forum; other PMC members will review and assist with materials preparation as appropriate.

- Review status and financial reports provided by the USACE on a quarterly basis and any other time that changes to the budget are contemplated that may require scope of work changes or possible use of contingency funds.

- For PED Phase 1 cost issues:

- Review/approve the use of contingency funds to complete site design or study work. If the USACE proposes to expend contingency funds, it must request approval from the Program Management Committee and concurrently present a review of costs, together with consideration of alternatives to expending contingency funds, including reduction of work or implementing efficiencies. The contingency fund expenditure request must be approved by the Sponsor and by a majority vote of the Program Management Committee (members must be present at the meeting to vote).

- Address potential budget overruns. If it appears likely that the budget will be exceeded for any individual site design or study as delineated in this PMP and the site and study-specific PMPs, the PMC will review alternatives for managing the overrun, including use of contingency funds, scope of work modification, or requesting a budget modification. The PMC may approve the use of contingency funds as outlined above. If the PMC determines that a budget modification should be requested, it will prepare a specific recommendation, including a cost-sharing plan, for consideration by the WRIA 9 Forum. If the PMC determines that a scope of work modification should be pursued, procedures as outlined below will be followed.

- For PED Phase 1 scope of work changes:

- Scope of work changes may take the form of revisions to work as set out in this PMP and the approved site- and/or study-specific PMPs, and the addition or deletion of specific sites and/or studies.

- The PMC may approve scope of work revisions for specific PED Phase 1 site designs or general studies that would not result in that site design’s or study’s budget being exceeded, or that would be covered through the use of contingency funds.

- For additions to the scope of work (i.e. the addition of new sites or studies or the addition of components to existing site or study work), the PMC will determine whether the proposed addition should be addressed as a Betterment, Post Authorization Change, USACE continuing authority programs (as addressed in Section 3.2.2), through an additional cost share to be borne by the Sponsor and/or partnering jurisdictions, or some other mechanism. The PMC may approve any addition proposed to be paid for by the jurisdiction in which an individual site would be constructed; if such funding is proposed to be made through this PED Phase 1 Agreement, the addition is subject to the Sponsor’s approval and a satisfactory cost payment arrangement.

- For any additions proposed to be cost-shared among partner jurisdictions, the PMC will prepare specific recommendations and alternatives for the WRIA 9 Forum. Any cost-share proposal not involving all the partner jurisdictions must be approved by those jurisdictions proposed to take part in the cost-share. Any cost share mechanisms that would be implemented through this PED Phase 1 Agreement must be approved by the Sponsor.

- For deletions from the scope of work (i.e. the deletion of specific sites or studies due to technical or other factors as may be raised by Project Development Teams), the PMC will develop a recommendation for deletion to present to the WRIA 9 Forum, including a proposal for addressing cost decrease issues.

- Forward for decision to the WRIA 9 Forum any decisions that cannot be reached by the PMC.

4.1.3   Project Delivery Teams/Project Co-Managers

Function

A Project Delivery Team (PDT) will be created for each PED site, systematic study, and programmatic initiative.

PDTs are responsible for conducting the PED Phase 1 general studies and preparing the plans and specification documents for the individual site designs.

## Co-Managers/PDT Representatives

Each PDT will be led by one Project Co-Manager from the USACE and one Project Co-Manager representing the Sponsor. The Sponsor’s Co-Manager may be a representative of the Sponsor or of one of its partnering jurisdictions. The Co-Managers will be selected by the site sponsor . The Co-Managers will select PDT design/engineering/ technical members.

#### Operating Protocols

- The project Co-Manager designated by the Corps will schedule and lead regular PDT meetings during the study or site design period, to be scheduled according to the timing and sequence of work to be done. The purposes of the meetings are:

- to review project progress according to the site- or study-specific PMP and address any arising issues, in order to ensure that work is conducted on schedule;

- to discuss evolving design requirements and changes, stimulate interdisciplinary communication and design compatibility, and serve as a forum to stimulate individual designers to function as an integrated design team and enhance the collective quality of the design package.

- A designated team member will prepare minutes of PDT meetings, which will be provided to each team member. Significant communications will also be confirmed in writing to all team members through e-mail or other appropriate methods.

- As an initial task, each PDT will clearly define team member roles and responsibilities. The Corps Co-Manager will prepare and distribute a roster of PDT members with names, PDT role, and contact information.

- Each PDT will also agree on guidelines for conducting work to be completed, including review of draft documents and responding to requests for information. The schedule for task completion shall provide for adequate time for review by the Sponsor and/or partnering jurisdictions, including time for additional independent reviews if appropriate.

- In the course of completing work, each PDT will agree upon the steps for moving to a subsequent task or construction phase.  Criteria for such a transition may include assignment to a successor team, determination of construction methods, establishment of responsibilities, permit requirements, staging, phasing, and safety.

- PDT members agree to be responsive in communicating with each other.

#### Tasks

- As an initial task, the Project Co-Managers will prepare a site- or study-specific PMP. The PMP will document the specific scope of work and project objectives, study- or site-specific success criteria, timelines for task completion and product delivery,  roles/responsibilities of team PDT members, and per-task project budget to be consistent with the overall site and study budgets established in this PMP. Each site- and study-specific PMP will be submitted for review and approval by the PMC.

- PDTs will, according to the agreed-upon PMPs, develop well-integrated and technically sound site designs that meet the local jurisdictions’ requirements in accordance with governing criteria and regulations as well as current local, state, and federal permitting requirements.

- PDTs will conduct detailed interdisciplinary coordination reviews subsequent to the specific technical discipline analyses described in Section 3.1.1.3 and prior to submission of the design package. During this review, designers will check for discrepancies, inconsistencies, or conflicts between their work and the work prepared by other PDT members to improve the quality of the plans, specifications and cost estimates.

    - Technical Committee.

The Technical Committee, composed of representatives from the USACE, the Sponsor and partnering jurisdictions, tribes, resource-related governmental agencies, and nonprofit groups, worked during the Reconnaissance and Feasibility phases of ERP to select sites and provide technical oversight to the overall effort. During PED Phase 1, the Technical Committee will act as an advisory body to review work products and processes with special focus on permitting and implementation issues. The Technical Committee will meet as needed as determined by the Project Co-Managers with input from the partnering jurisdictions.

4.1.5   Independent Technical Review Team

The USACE requires the District to conduct  technical reviews of all site designs and analyses completed as part of a PED cost-sharing agreement. These reviews must be completed prior to development of Project Cooperation Agreements (PCAs) for construction of projects designed under PED; specifically, the review must be completed before PCAs are transferred to the Northwest Division (NWD) of USACE for review or for advertisement. To complete the reviews, an Independent Technical Review Team (ITRT) will be convened primarily from USACE staff not otherwise affiliated with PED Phase 1. Any recommendations for project changes forthcoming from the ITRT will be submitted for consideration to the appropriate design- or study-specific PDT.

4.2   Dispute Resolution

Article V of the PED Phase 1 agreement addresses formal dispute resolution mechanisms for use at a high level by the USACE and the Sponsor. The USACE, the Sponsor and partnering jurisdictions recognize that disputes may arise in the course of conducting PED Phase 1 work that will require resolution at a lower functional level and agree to use the dispute resolution levels outlined below, subject to the provisions in the PED Phase 1 agreement. The USACE, Sponsor and partnering jurisdictions will make every effort to resolve disputes at the lowest level possible. If disputes cannot be resolved at a given level within a reasonable timeframe, the dispute will be referred to the next level.

For site- or study-specific disputes:

- level one: Project Co-Managers for the Project Delivery Teams, unless the dispute involves budget in excess of the site budget, in which case the dispute is referred immediately to level two below.

- level two: Program Management Committee

- level three: WRIA 9 Forum

For general PED Phase 1 disputes:

- level one: Program Management Committee

- level two: WRIA 9 Forum

In the event that disputes cannot be resolved at the functional levels outlined above, they may be submitted for non-binding alternative dispute resolution by a qualified third party, per the terms of the PED agreement.

5.0 Quality Control/Assurance Plan

5.1 Purpose

The purpose of this Quality Control Plan (QCP) is to formally establish and implement USACE Seattle District policy that ensures quality management, services, and products in support of the Project Manager, Program Manager, Project Delivery Team, and the sponsor.

5.2 Elements

The QCP will involve the following elements:

Criteria Review. This is a PDT function to be accomplished early in the design process and throughout the design. Site specific criteria for the project shall be discussed and documented in the site-specific PMP. This information will be provided to the PDT for use in preparation of the project design. During the design process, these criteria may change.  The project team will assess the impacts of these changes or clarifications and provide budget and schedule impact assessments to the sponsor. Information relating to criteria review shall be documented in memorandums as appropriate and provided to team members and the sponsor.

Sponsor –USACE Relationship Management, including On-Board reviews.

The PMC will meet monthly or as needed to review project progress, ensure site-specific and systematic project criteria is being met, and review incoming information or possible changes to criteria.

Consultant Quality Control/Quality Assurance. The professional quality, technical accuracy and the coordination of all designs, drawings, specifications, design analyses, cost estimates, bid schedules and other documents and services are the responsibility of any consultant hired by the USACE to complete assigned PMP tasks. Any such consultant shall have a logical and functional quality control program and project specific Quality Control Plan (QCP) to assure errors or deficiencies in all submittals are avoided. Any such consultant shall perform reviews during the design process and just prior to completion of all work. Work shall be reviewed for technical accuracy, coordination and conformance to sponsor requirements. All errors and deficiencies shall be corrected prior to submission for sponsor review. Any such consultant shall submit two copies of its QCP for approval within 15 calendar days after award of the design contract.  One copy shall be sent to the USACE Project Manager and the Contracting Officers Representative (PM/COR), and one copy shall be sent to the Chief of the Technical Engineering and Review Section of the USACE. Any such consultant shall revise the QCP as required by the PM. An approved version of the QCP shall be completed prior to the first submittal.  QCP requirements are described in Volume 1, Chapter 2, Section 2.1.4, Design Quality Assurance Plan of the Guide for Consultants. At the option of the USACE, USACE representatives may visit any such consultant prior to submittal dates to check the consultant’s internal quality control process.

Interdisciplinary Coordination Review. A detailed interdisciplinary coordination review should be conducted by the PDT subsequent to the Specific Discipline Overviews and prior to submission of the total design package to the USACE PM. During this review designers will check for discrepancies, disconnects and interference’s within and between their work and the work prepared by other PDT members. The goal is to eliminate flaws and conflicts within and between the plans, specifications and cost estimates. The PDT will be responsible for developing a well-integrated and technically sound design that meets the sponsor’s requirements in accordance with governing criteria and regulations. Minutes of PDT meetings shall be prepared by the PM or the designated team member and provided to each team member. In this way, each team member is aware of decisions made that might affect their portion of the project.

Specific Discipline Peer Checks/Overview. Within each discipline, an independent spot check and review of the designer’s assumptions, analyses, and calculations shall be performed throughout the design process on a periodic basis. This effort, which is the standard operating procedure of the Seattle District, will be conducted by senior level personnel within the same technical discipline or section who are not directly involved with the development of the project design being reviewed. The resource manager for the discipline in question is responsible to ensure that tools (e.g., internal quality control plan, checklists) and procedures are in place to ensure that the level of quality negotiated between the USACE PM, the Sponsor, and the PDT is met.

Independent Technical Reviews. Within the USACE, its contractors and the sponsor, an independent review team, composed of specialists in each discipline will perform an independent technical review of the designer’s assumptions, analyses and calculations throughout the design process. Senior level personnel will perform the review effort. The resource manager of the discipline in question is responsible to ensure that internal quality control plans, checklists, etc. and procedures are in place to ensure the expected level of quality is met. Review comments in electronic or written format will be submitted by reviewers, annotated with responses by the consultant, back-checked to ensure a complete and timely response by reviewers and collected by the USACE PM. A review meeting will take place between the sponsor, consultant, USACE PM and other interested parties.  Every comment will be incorporated or resolved to the satisfaction of the USACE PM. Dr. Checks (computer aided review system) will be incorporate for this review.

Biddability, Constructability, Operability and Environmental (BCOE) Review. The USACE Resident Engineer Office will conduct a BCOE review as required by ER 415-1-11. The Sponsor will also perform a functional, operability, maintainability and environmental review. The Engineering and Construction Division will provide a formal written certification that all appropriate BCOE comments have been considered and as appropriate incorporated in the design documents prior to award of the construction contract. The BCOE review will be conducted in strict accordance with ER 415-1-11 to include a minimum the following checks:

- Accurate depiction of existing conditions at the site to include utility availability, obstructions, drainage, adequacy of storage and working space and general configuration;

- Appropriateness of contract sequencing, contract performance time, contractor quality control requirements and submittal requirements;

- Any special environmental conditions;

- Local availability of special materials and labor skills, if required; and

- Any base/location specific requirements.

Value Engineering (VE). The USACE PM will coordinate with the Seattle District VE Officer and the Sponsor and its partnering jurisdiction to schedule and conduct a VE study for appropriate projects (including those sites with an estimated construction cost of $2,000,000 or greater). When applicable, the PM will insure that a VE study is implemented early in the design process to maximize quality enhancement and cost reduction ideas and minimize impacts on the design schedule and lost design effort.

6.0 Additional Considerations

6.1 Construction Techniques

Construction will not be performed under this PED agreement.  However, since construction techniques will be selected, and associated cost estimates and specifications will be developed for each Phase 1 site in the design process, possible construction techniques are described below. Selection of one or more of these techniques for each site will affect implementation costs.

- Equipment Rental. This is a method that has been developed by the Seattle District’s Emergency Operations group. District Personnel are used as construction supervisors and equipment and operators are obtained through contracted rental equipment and materials  purchased through purchase orders. This system has been found to be very effective for small projects with a potential for significant changes as the project is constructed.

- Lump Sum. This contract would be used for larger projects where the entire project would go out for competitive bid and be constructed by the contractor providing the lowest bid.

- Design/Build.  This technique would involve an open-ended contract that would be set up so that each contract would be through a work order. The contract would be set up so that one entity would be responsible for both the design and the construction of an individual site.

- Performance Contract.  This contract would be similar to a Lump Sum contract but would include a specification to bid on individual items that may be required above and beyond the scope of the original scope of work. This gives more flexibility than what is available in a normal Lump Sum contract and allows an increase in the contract scope without the need for change orders.

6.2 Real Estate Plan

The real estate process will follow the plan outlined in the Real Estate Appendix of the feasibility report. Phase one sites were selected because the majority of them are in public ownership or will soon be in public ownership. The majority of these lands are held in fee with some of them being obtained with an approved environmental easement.

6.3 Local Sponsorship Financial Plan

The County is the Sponsor of the PED phase. However, the County is relying on cost-sharing contributions from a number of other partnering local jurisdictions that collectively comprise both the WRIA 9 Forum and the PMC. The County anticipates using an existing Inter-Local Agreement (ILA) with these partnering jurisdictions that will outline the financial obligation of each participant in the ILA. Funding may also be augmented through funds from the King Conservation District. This is similar to the financial plan that was used to finance the Feasibility Study. Table 3 shows how this Federal, Sponsor, and partnering jurisdiction funding could be spread over the four-year period of the PED agreement.

6.4 Policy Compliance Memorandum

The Policy Compliance Memorandum, Green/Duwamish River Ecosystem Restoration Draft Feasibility Report (2000), a document prepared by Headquarters, USACE, verified that the Feasibility Report is compliant with USACE policy. The USACE Project Manager determined that this PMP is in full compliance with the memorandum.

6.5 Environmental Compliance

The USACE will be responsible for assuring that Phase 1 projects are in compliance with all applicable federal regulations. All state and local regulations will be the responsibility of the jurisdiction where the project is to be constructed. All federal permitting costs are covered under the PED agreement, but state and local permitting costs will be the responsibility of the Sponsor and its partnering jurisdictions and will not be covered under PED cost sharing arrangements.

6.5.1 Federal Environmental Regulations

## The National Environmental Policy Act

The NEPA process includes public participation in addition to other process requirements. A Programmatic Environmental Impact Statement (PEIS) was completed for all Phase 1 sites during the Feasibility Phase. However, even with a PEIS, site-specific projects will still require additional environmental review. Section 1 of the programmatic EIS describes in more detail the NEPA process for subsequent environmental documents. This programmatic EIS is intended to accomplish partial NEPA compliance.  Project-specific NEPA documents will need to be prepared for each proposed restoration project.  The USACE will continue to act as lead agency for the NEPA process.

Section 401 of the Clean Water Act, Water Quality Certification

A Water Quality Certification under the CWA Section 401 is required from the State of Washington for activities requiring a federal license or permit that may result in any discharge into the navigable waters. In order to obtain the required certification, the State of Washington may require a water quality modification

## Section 404 of the Clean Water Act, Discharge of Dredge or Fill Material

This permit is required for the discharge of dredged or fill material into water of the United States. Waters of the United States is defined to include wetlands. Site or project-specific compliance under Section 404 will occur prior to any construction.

## Coastal Zone Management Act Compliance

The Coastal Zone Management Act encourages and assists with the responsible use and protection of the nation’s coastal zones. The National Oceanic and Atmospheric Administration (NOAA) oversees the implementation of the act by assisting state and local shoreline agencies to achieve wise use of land and water resources. The Washington State Department of Ecology leads the effort in implementing the act with assistance from each coastal county’s planning departments. An evaluation of coastal zone consistency will be done during the project-specific permit phase and that determination will be provided to the appropriate agencies.

## Federal Endangered Species Act

The Endangered Species Act (ESA) requires federal agencies to conserve endangered and threatened species. Consultations with the federal agencies that govern fish and wildlife are required to ensure that federal actions do not jeopardize listed, proposed, or candidate species or destroy their critical habitats.

## National Historic Preservation Act: Section 106

The Section 106 process of the National Historic Preservation Act is triggered for projects that are federal undertakings or that require a federal permit, license, or approval and are subject to state or local regulation pursuant to approval by a federal agency. Section 106 requires that a federal agency having direct or indirect authority to issue a license authorizing an undertaking shall take into account the effect of the undertaking on historic properties. The Section 106 process includes research and field investigation in consultation with the Washington State Office of Archaeology and Historic Preservation, the Advisory Council on Historic Preservation, concerned Tribes and local governments.

6.5.2 State and Local Environmental Regulations

## State Environmental Policy Act (SEPA), Ch. 43 RCW

As with NEPA, there will be subsequent environmental review to meet SEPA requirements for the specific sites. Site-specific NEPA/SEPA documents will be prepared prior to any construction.

State Hydraulic Code (HPA), Washington Department of Fish and Wildlife (WDFW)

Work that uses, diverts, obstructs, or changes the natural flow or bed of any freshwater or saltwater of the state requires a Hydraulic Project Approval (HPA) from WDFW. The statutory authority for this requirement is contained in Chapter 75.20 RCW and Chapter 220-110 WAC. HPAs may be needed for restoration projects since most would involve some degree of work within the streambed of the Green/Duwamish River or one or more of its tributaries.

Local Permits

These permits include all those required by the jurisdiction in which each site will be constructed. Examples include clearing and grading permits, flood plain ordinances, noise ordinances, etc.

6.6 PED Execution

This PMP identifies the minimum work considered necessary to meet the requirements to execute a Design Agreement and the efforts necessary in the PED phase. Coordination throughout the process will continue between USACE and King County and cities with a view to adjust and revise the PMP, when appropriate, to reflect information developed by the study and the current analysis of potential measures and alternatives. Work identified in this PMP will be accomplished by USACE, King County, city representatives and designated consulting firms. USACE will use Federal and Sponsor funds to accomplish activities as identified in this PMP.  King County has used its own funds and obtained funds from other local governments to accomplish work and will continue this practice for future planned work during PED. This PMP identifies the anticipated split between the Federal and Local share.

6.6.1 Additional Work Needed for Project Construction

Other work in advance of project construction includes the preparation and execution of multiple Project Cooperation Agreements (PCA) that identify the responsibilities and contributions of the USACE and the local sponsor. Each restoration site will require a PCA. Funding necessary for the USACE to develop PCAs for each Phase 1 site is included in the Project Management estimate.  State and local permitting fees have not yet been secured for this effort and would need to be provided in the future.