Scope of Work

2024 King County Comprehensive Plan

March 2022

The 2024 King County Comprehensive Plan Update ("2024 update") is an opportunity to make substantive policy changes that address our community's long-term needs and advance the County's policy goals.  This update is also the Washington State Growth Management Act's ("GMA") statutory periodic review, which requires a comprehensive review and update to the Comprehensive Plan to ensure compliance with GMA goals and requirements.  This update is required by state law to be completed by December 31, 2024.

As part of the 2024 update, the County will complete a State Environmental Policy Act ("SEPA") Environmental Impact Statement ("EIS") for the Comprehensive Plan.  The County will also complete an equity impact analysis of the proposed update prior to adoption.

The following sets the scope of work for the 2024 update, as required for eight-year updates by King County Code ("K.C.C.") 20.18.060.

## Topical Areas for the 2024 Update

A primary goal of the 2024 update will be to implement the 2021 Countywide Planning Policies ("CPPs") recommended by the Growth Management Planning Council and adopted by the King County Council.  This update will reflect, create alignment with, and advance current plans, regulations, and practices – including state law, VISION 2050, CPPs, 2022 King County Comprehensive Plan Performance Measures Report, 2016 Comprehensive Plan Workplan action items, and current case law.  The 2024 update will also streamline the plan and relevant code sections King County Code Title 20, where possible and appropriate.

The 2024 update will also be rooted in the value of making King County a welcoming community where every person can thrive. In support of this value, which is also consistent with the core themes of the most recent CPPs, the 2024 update will have three focus areas: pro-equity, housing, and climate change and the environment.  By focusing on these critical issues, the County intends to prioritize policies and regulations that address our community's most pressing long-range planning needs.

The following table is the list of scoping topics that will be considered as part of the 2024 update.  The list is organized according to the three focus areas noted above, as well as other general changes.  Within each topic are possible issues within those topics that might be evaluated, pending additional analysis and available resources.  Because the focus areas are broad, complex, and inter-related, they contain topics and issues that overlap.  Given this, the Executive intends to prevent siloed work within the focus areas by coordinating and integrating relevant departmental analysis and proposals.

The scoping list reflects key topics and issues resulting from collaboration with departmental staff, direct community input from the public Docket process, and Council consultation.  Based on community feedback about planning and engagement fatigue, and as recommended by the Office of Equity and Social Justice, the Executive did not conduct extensive scoping engagement with the community.  Instead, the scope was further informed by: community input from the Skyway and North Highline subarea planning processes; community recommendations from the Climate Equity Community Task Force, Mobility Equity Cabinet, and Open Space Equity Cabinet; and building on the guiding principles of the King County Immigrant and Refugee Commission.  Scoping topics and items that align with this input and recommendations, as well as recommendations from the 2022 Performance Measures report, are indicated in footnotes in the list.

Additional topics and/or issues not on this list may also be considered as part of the 2024 update, where appropriate and consistent with required SEPA review.

| Focus Area | Scoping Topic | Possible Issues to be Evaluated |
| --- | --- | --- |
| - Pro-Equity | - Reduce displacement and advance housing equity for low-income populations; Black, Indigenous, and other People of Color; and immigrants and refugees | Advance 2021 Anti-Displacement Report recommendations and housing equity policies from the CPPs, such as: - Advance community-driven development - Increase homeownership - Improve housing stability - Advance inclusionary housing regulations - Preserve manufactured housing communities |
|  | - Integrate a pro-equity and anti-racist policy framework that improves outcomes for low-income populations; Black, Indigenous, and other People of Color; and immigrants and refugees | - Review entire plan to advance community-driven anti-racist, pro-equity strategies; ensure alignment with Equity and Social Justice Strategic Plan - Review and document the local history of racially exclusive and discriminatory land use and housing practices, including explaining the extent to which that history is still reflected in current development patterns, housing conditions, tenure, and access to opportunity - Improve process equity to support full and equal participation in County planning and decision-making by all community members, implement CPP requirements mandates for community engagement, and integrate and align with King County equitable engagement best practices - Advance community recommendations from the King County Climate Equity Community Task Force, Immigrant and Refugee Commission, Mobility Equity Cabinet, and Open Space Equity Cabinet - Advance County investment upstream, where needs are greatest and in partnership with communities that are most directly impacted, such as low-income communities, communities of color, and immigrant and refugee populations - Improve tribal coordination |
|  | - Improve health equity outcomes in communities with the greatest and most acute needs | - Increase open space investments in urban areas, such as Skyway and North Highline, to help improve physical, emotional, and community health - Improve equitable and sustainable healthy food access, especially in Skyway and North Highline - Update cannabis regulations, where appropriate, based on Social Equity in Cannabis Task Force and Public Health – Seattle-King County King County Department of Community and Human Services recommendations, - Improve health outcomes for housing near high-capacity roadways |

| Focus Area | Scoping Topic | Possible Issues to be Evaluated |
| --- | --- | --- |
| - Housing | - Comprehensive housing policy review and updates | - Update and streamline housing policies - Evaluate "should" and "shall" policies for alignment with current practice and resources - Align policies with current regional housing funding guidelines and priorities |
|  | - Improve affordable housing supply, especially for low-income populations; Black, Indigenous, and other People of Color; and immigrants and refugees | - Plan for and accommodate housing affordable to all income levels - Align housing policies as directed in the CPPs - Identify opportunities to advance applicable recommendations from the Regional Affordable Housing Task Force report - Increase development of eco-friendly and climate-resilient affordable housing - Evaluate strategies to incentivize or require, where appropriate, housing affordable to households earning less than 80 percent of area median income; consider displacement impacts and mitigation strategies as part of the approach - Update the Residential Density Incentive Program to improve incentives for development of affordable housing - Review outcomes of Vashon Affordable Housing Special District Overlay |
|  | - Expand housing options | - Evaluate the types of housing allowed in low-density urban residential zones and how more multifamily and middle-density housing could be developed in urban unincorporated King County |

| Focus Area | Scoping Topic | Possible Issues to be Evaluated |
| --- | --- | --- |
| - Climate Change & Environment | - Alignment with and advancement of 2020 Strategic Climate Action Plan to reduce greenhouse gas emissions, support sustainable and resilient communities, and prepare for climate change | - Build on the goals of House Bill 1099, which did not pass the state legislature in 2022, by strengthening the County's climate policies and regulations to reduce greenhouse gas emissions and increase resiliency to local climate impacts - Advance environmental justice and reduce climate-related health impacts - Increase climate resilience by supporting investments in urban green spaces, including in Skyway and North Highline - Support decarbonization/elimination of fossil fuel use in the built environment and increase affordable and equitable access to energy efficiency and decarbonization programs - Reduce transportation-related emissions - Examine development regulations in wildfire risk areas - Support development of and access to green jobs that advance sustainability and living wage opportunities and increase representation and access for low-income populations; Black, Indigenous, and other People of Color; and immigrants and refugees |
|  | - Integrate and implement Clean Water, Healthy Habitat goals | - Update shoreline armoring regulations - Support net ecological gains and accelerate improvements to salmon habitat and removal of barriers to fish passage - Improve integrated floodplain management - Advance key Farm, Fish, Flood goals |

| Focus Area | Scoping Topic | Possible Issues to be Evaluated |
| --- | --- | --- |
|  | - Increase land conservation | - Increase open space investments to help eliminate disparities in access, especially in urban areas such as Skyway and North Highline - Review Four-to-One Program - Strengthen Transfer of Development Rights Program |
| IV. General | - Implement unincorporated area-related changes from the CPPs | - Adopt new housing and jobs growth targets for unincorporated King County - Evaluate designating Skyway and North Highline as countywide centers |
|  | - Implement Subarea Planning Program | - Evaluate possible unincorporated-wide policies and regulations for applicable issues raised during subarea planning processes - Vashon p-suffix and special district overlay review |
|  | - Update transportation policies | - Support equitable access to mobility options and invest in transit services where the needs are greatest, especially for low-income populations; Black, Indigenous, and other People of Color; and immigrants and refugees - Support investments to increase safe access to public transit - Advancing integrated approaches to enhanced traffic safety for all users, such as supporting complete streets and equitable infrastructure investments - Make Urban Growth Area boundary corrections for road rights-of-way |
|  | - Review rural and natural resources regulations | - Advance key Farm, Fish, Flood goals - Increase the amount of farmland in active production - Evaluate regulations for resorts in the rural area - Review mineral processing regulations in forest zones |
|  | - Advance public Docket amendment requests, where appropriate | - Evaluate Vashon grange retail proposal - Review materials processing standards in rural area |

## SEPA Work Program

SEPA review for the 2024 update will commence with the release of the scope of work for the update in the spring 2022.  The County anticipates conducting an EIS process, with release of an EIS concurrent with transmittal of the Executive recommended plan.  The environmental review will continue through Council's review of the plan and will be concluded in advance of final action by the full Council in December 2024.

## Public Participation Work Program

The GMA and King County Code requires early and continuous public participation in the preparation of comprehensive plan amendments. Consistent with this, the County will conduct a multi-phased approach to public engagement for the 2024 update.  Throughout the process, the County will center the voices of low-income, immigrant, Black, Indigenous, and other People of Color communities and partner with King County equity cabinets and community-based organizations (hence referred to as “community”).

Phase 1 – Scoping

The scoping phase included sharing information about comprehensive planning and the 2024 update and requesting public input through the Docket on the issues to be addressed in the scope of work.  Based on community feedback about “process fatigue,” and as recommended by the Office of Equity and Social Justice, the Executive did not conduct extensive scoping engagement with the community.  Instead, the scope was further informed by review of recent community input from the Skyway and North Highline subarea planning processes, as well as the community recommendations from the King County Immigrant and Refugee Commission, Mobility Equity Cabinet, Open Space Equity Cabinet, and Climate Equity Community Task Force.

Phase 2 – Development of Executive Public Review Draft

The Executive will engage with the community to develop the Executive Public Review Draft of the 2024 update.  This will begin with educational engagement to expand the knowledge base about what comprehensive planning is and why it matters.  Then, the Executive will involve and collaborate with the community in developing policy concepts and proposals that will be included in the Executive Public Review Draft of the 2024 update.

Phase 3 – Development of Executive Recommended Plan

The third phase will take place after the Public Review Draft has been released and will start with a 45-day public review and comment period.  This engagement will encompass the Executive leading broad engagement with the community.  Once public feedback has been compiled, updates to the Public Review Draft based on input will be identified, where appropriate.  At that time, the Executive will report back to the community on how the input shaped the Executive recommended plan and share next steps for the process.  An Executive recommended plan informed by this public engagement will be transmitted to the Council by December 29, 2023.

Phase 4 – Council Review, Refinement, and Adoption

The Council review, refinement, and adoption phase will include additional public outreach and opportunities for public input as part of their decision-making process.  This will include the ability to submit written feedback throughout the process, opportunities for verbal public testimony, a formal public hearing before the full Council, a 30-day notice of the public hearing date and a formal comment period, emailed notices of key milestones and opportunities for input, and a postal mailed notice to properties nearby proposed land use and/or zoning changes.

Public participation plan

To support early and continuously engagement, especially with the community, the Executive will develop a public participation plan.  Development of this plan will include:

- Asking how the community would like to be engaged;

- Working with the community to identify the names of groups that should be included in the engagement process;

- Reflecting a desire to meet people where they are by attending community meetings held by community-based organizations and other King County agencies; and

- Incorporating language access strategies, including offering interpretation services and translation of key materials.

A key aspect of the public participation plan will be identifying the strategies for informing, consulting, and involving the community throughout the entire planning process. As required by K.C.C. 20.18.160, at a minimum this will include posting information online about the Comprehensive Plan and the 2024 update, the update schedule, opportunities for public involvement and ways to provide input, and the range of proposals under consideration by the County.  Information and project updates at key milestones will also be provided, as appropriate, via a variety of methods, such as the Comprehensive Plan email list, other County email lists, social media, and hard-copy materials at key locations.

Chapter 36.70A Revised Code of Washington (RCW) [LINK]

Per RCW 36.70A.130, as amended by House Bill 1241 [LINK]

King County Code Title 20 [LINK]

2021 Countywide Planning Policies as adopted inordinance 19834 [LINK]

The 2022 Performance Measures Report was transmitted to Council concurrent with transmittal of this scope of work.

King County Comprehensive Plan Workplan, Action 16 [LINK]

King County Docket website [LINK]

Link to Open Space Equity Cabinet Recommendations [LINK]; Mobility Framework Report [LINK]; Sustainable & Resilient Frontline Communities section of the 2021 Strategic Climate Action Plan [LINK]; King County Immigrant and Refugee Commission Guiding Principles [LINK]

Alignment notation key: CECTF: Climate Equity Community Task Force; IRC: Immigrant and Refugee Commission; MEC: Mobility Equity Cabinet; OSEC: Open Space Equity Cabinet; PM: 2022 King County Performance Measures Report; SWH/NH: Skyway-West Hill and North Highline subarea planning processes

Aligns with CECTF, MEC, OSEC, PM, SWH/NH

2021-RPT0112 [LINK]

Aligns with CECTF, IRC, MEC, OSEC, SWH/NH

Equity and Social Justice Strategic Plan [LINK]

As required by the CPPs

Aligns with CECTF, IRC, MEC, OSEC, SWH/NH

Aligns with CECTF, MEC, OSEC, SWH/NH

Including as directed by House Bill 1717 [LINK]

Aligns with CECTF, MEC, OSEC, SWH/NH

Aligns with CECTF, OSEC, PM, SWH/NH

Aligns with CECTF, PM, SWH/NH

Social Equity in Cannabis Task Force website [LINK]

Health and Human Services priorities regarding marijuana legalization [LINK]

Aligns with SWH/NH

Aligns with CECTF, MEC, OSEC, PM, SWH/NH

As required by House Bill 1220 [LINK]

Regional Affordable Housing Task Force Final Report and Recommendations [LINK]

Aligns with CECTF

Aligns with CECTF, MEC, OSEC, PM, SWH/NH

As required by Comprehensive Plan Workplan Action 17

As required by Ordinance 18623, Section 10 [LINK]

Aligns with PM, SWH/NH

2020 Strategic Climate Action Plan as adopted in Motion 15866 [LINK]

Aligns with CECTF, MEC, OSEC, PM, SWH/NH

House Bill 1099 [LINK]

Aligns with CECTF, MEC, OSEC, PM, SWH/NH

Aligns with CECTF, OSEC, PM, SWH/NH

Aligns with CECTF

Aligns with MEC

Aligns with CECTF

Aligns with CECTF

Aligns with CECTF

As required by Senate Bill 5273 [LINK]

Snoqualmie Fish, Farm, Flood Advisory Committee Action Recommendations [LINK]

Aligns with CECTF, OSEC, PM, SWH/NH

As required by Ordinance 19384, Section 4

Aligns with SWH/NH

Vashon-Maury Island Community Service Area Subarea Plan, VMI CSA Workplan Action 1 [LINK]

Aligns with CECTF, MEC, SWH/NH

Aligns with CECTF, MEC, SWH/NH

Aligns with MEC, SWH/NH

Aligns with CECTF, PM

RCW 36.70A.140 [LINK] and K.C.C. 20.18.160 [LINK]