## Attachment A
Attachment A
Update of Cardwell/Thomas Project Scope Completed or Planned for Completion in the 2008-2013 MMRF Financial Plan
Cost Estimates are for Construction Costs Only (Excluding Contingency, Tax, Design, Administration Project Costs)
| Project Scope Category | 1988 Estimated Cost | Completed Prior to 2008 |  | Financing for pre-2008 project work | 2008-2013 MMRF Plan | MMRF Project Number in 2008-2013 Six Year Plan
|  |  | Dollars | Percent
| Loading Dock and Tunnel | 1456816.04 | 0 | 0% |  | Ineligible
| South Entry | 708655.94 | 0 | 0% |  | Ineligible
| 3rd and 4th Ave Entry and Corridor Floors 2-9 | 1550051.35 | 835051.35 | 53.87% | Debt/Property Sale | Yes | 344603, 344604
| Wood, Aluminum and Bronze Windows | 2046921.14 | 319791.14 | 15.62% | MMRF Infrastructure model | Yes, except for ineligible Window covering removal | 342440
| Attic Windows (Floors 10-12) | 1116972 | 0 | 0% |  | Yes | 342440
| Roof: Main, N. and S. Courtyards | 629051.8 | 629052 | 100% | MMRF Infrastructure model | Yes | 344601
| Cornice | 974802 | 692334.5 | 71.02% | MMRF Infrastructure model | Ineligible
| Cleaning and Tuckpointing Building Exterior | 630722.27 | 630722.27 | 100% | MMRF Infrastructure model | Yes | 342454, 342647
| Sub-Total | 9113992.54 | 3106951.26 | 34.09%
| Contractor Cost Burden Factor | 606768.75
| Total | 9720761.29