## STAFF REPORT

| Agenda Item: | 26, 27 & 28 | Name: | Polly St. John |
| --- | --- | --- | --- |
| Proposed No.: | 2014-0438 2014-0439 2014-0440 | Date: | November 4, 2014 |

SUBJECT:

Three ordinances are proposed that would rewrite and amend King County Code, Title 4 – Revenue and Financial Regulation – Chapters 4.04 and 4.06.  The legislation would significantly reorganize the chapter and make fundamental changes to the handling of capital project budgeting.  Council staff has developed the legislation, working in conjunction with the Prosecuting Attorney's Office, Council Legal Counsel, the Office of Performance, Strategy and Budget (PSB) staff, and the Code Reviser and Clerk of the Council.  The three ordinances are:

- Proposed Ordinance 2014-0438:  regarding fiscal note procedures,

- Proposed Ordinance 2014-0439:  regarding budgeting and reporting, and

- Proposed Ordinance 2014-0440:  regarding capital project oversight, including the Auditor's Capital Project Oversight Program, the Real Property and Major Capital Projects Joint Advisory Group, and mandatory phased appropriations.

SUMMARY:

In 2011, the committee directed staff to rewrite Title 4 and received briefings that highlighted Title 4 work needed on areas such as taxes, fees and funds ordinances.  The Clerk of the Council recommended that a series of ordinances be used to rewrite Title 4 to ensure that codification of the full title could occur in measured stages and not overburden the workload of the Clerk's Office and other staff.  The proposed ordinances include revisions to Title 4.04 and Title 4.06 and move those chapters to the new Title 4A.  Some corresponding revisions would also be made in sections of Title 2 and definitions in Title 4A are also adjusted.

BACKGROUND:

Title 4 covers "Revenue and Financial Regulation" and is comprised of 60 chapters, covering areas of (1) budgeting and reporting, (2) procurement, (3) property, (4) claims against the county (risk management), (5) taxes and (6) fees.  Some of these areas – such as fees – have already been revised and moved into the new Title 4A, as shown in Table 1 of this report.

Title 4 has not been comprehensively reviewed in over thirty years.  King County Code should accurately reflect state law, be updated for current county processes, include consistent formats, and recognize the county’s migration to a new financial and budgeting system.

Between July and September 2011, staff presented a series of briefings that covered the major categories in Title 4.  Staff sought and received direction from the Budget and Fiscal Management (BFM) Committee regarding the task of examining and rewriting the Title.

The BFM committee directed staff to proceed with a review of the entire Title 4 and to migrate to a new Title 4A.  As a result, Title 4 is being migrated to a new Title 4A or, if appropriate, elsewhere in the code.  This is the same process that was used to rewrite Title 19A, Land Segregation, and Title 21A, Planning and Zoning.

The Title 4 revision process consists of reorganizing chapters and moving them to appropriate titles.  In the process, substantive clean-up work is also occurring.  (As an example, procurement procedures previously located in Title 4, were better located in Title 2 which deals with administrative direction.  Ordinance 17522 moved procurement procedures to Title 2 in February 2013.)

Past Council Action:

Work has been on-going for the Title 4 review.  The following table shows the bodies of work for Title 4 comprehensive review and Title 4A migration.

- Table 1.  Bodies of Work for Title 4 Comprehensive Review and Title 4A Migration

| Date of Action | Subject Area | Citation | Description of Work |
| --- | --- | --- | --- |
| - 07/25/11 | Court Fees | Ord. 17150 (2011-0222) | Ordinance 17150 incorporated Superior Court and Dept. of Judicial Administration-related fees into the new Title 4A. |
| - 11/09/11 | Interim Definitions | Ord. 17229 (2011-0403) | Ordinance 17229 aligned Title 4 phase definitions with the Accountable Business Transformation (ABT) project management system that was about to go live. |
| - 04/02/12 | Taxes | Ord. 17291 (2012-0086) | Ordinance 17291 moved tax chapters relating to sales and use taxes, excise taxes, and hotel-motel tax to Title 4A, including 4.28, 4.29, 4.30, 4.31, 4.32, 4.33, 4.34, and 4.42. |
| - 04/02/12 | Title 4 Fees | Ord. 17292 (2012-0087) | Ordinance 17292 moved the rest of Title 4 county fee chapters to Title 4A, capturing non-court-related fees such as vehicle license fees, sewer rates, transit fares, etc. |
| - 04/02/12 | Definitions | Ord. 17293 (2012-0088) | Ordinance 17293 moved all Title 4 definitions into the new Title 4A. |
| - 09/10/12 | Risk Mgmt. | Ord. 17408 (2012-0236) | Ordinance 17408, heard in GAOFP Committee, updated Chapter 4.12 and 4.13 risk management provisions, and recodified them in Title 2, relating to county administration. |
| - 01-28-13 | Fees | 2012-0453 | Title 14 Real Estate Services fees would be moved to Title 4A. |
| - 02/11/13 | Procurement | Ord. 17522 (2012-0445) | Procurement provisions (4.16) were moved to Title 2, relating to county administration. |
| - 02/19/13 | Funds | 2012-0438 | The ordinance adopting funds and fund managers would be cleaned up, and Funds (4.08) moved to Title 4A. |
| - 03/25/13 | Bonds | 2012-0472 | Bonds (4.20, 4.84) would be moved to Title 4A. |
| - 09/09/13 | Contracting | Ord. 17652 (2013-0245) | Contracting opportunities programs (4.18, 4.19) |
| - 06/02/14 | Property Taxes | Ord. 17822 (2014-0188) | Property tax provisions (4.52, 4.62, 4.63, 4.64) |
| - 06/02/14 | Property Taxes | Ord. 17823 (2014-0189) | Property tax provisions (4.60, 4.68) |
| - 06/02/14 |  | Ord. 17824 (2014-0190) | Property tax provisions (4.48) |
| - Lapsed | Property Taxes | 2012-0358 | Property tax provisions – included in Ordinances 17822, 17823, 17824 |
| - 2014 | Budget, Reporting & Capital Oversight | 4.04, 4.06 | Proposed Ordinances 2014-0438, 2014-0439, and 2014-0440 |
| Date of Action | Subject Area | Citation | Title 4 Chapters Remaining to Migrate (may be multiple pieces of legislation per subject area) |
| - 2015 | Funds | 4.10, 4.24 | Investment of funds, Executive Finance Committee and interfund borrowing |
| - 2015 | Contracting | 4.14 | Bidding Procedures For Financial Services Contracts |
| - 2015 | Art Financing | 4.40 | Financing Art in Construction Projects |
| - 2015 | Real & Personal Property | 4.36, 4.44, 4.56 | Real and personal property (county property payment of rent, tax title sales, sales and leasing) |
| - 2015 | Excise Taxes | 4.35 | Excise taxes from timber harvested from public lands |
| - 2015 | Misc. | 4.29, 4.57, 4.81 | Public transportation funding, concession contracts, law library support |
| Date of Action | Subject Area | Citation | Other Titles with Parts to Migrate to Title 4A |
| TBD | Fees | Various | Department fees in other titles, such as K.C.C. 10.12 Solid waste site disposal fees, could be moved to Title 4A. |
| TBD | Misc. | Various | This is a placeholder for other areas that might be identified as the Title 4A work continues. |

The goal is to continue working on Title 4 revisions throughout 2015.

ANALYSIS:

The Title 4 rewrite occurs in three ordinances and covers changes for budgeting and reporting, fiscal notes, and capital project oversight, including mandatory phased appropriations, the Joint Advisory Group (JAG) and the Auditor's Capital Project Oversight (CPO) program.  The proposals would make changes recommended by the work group for the project.  The proposals have also been reviewed by the Prosecuting Attorney's Office (PAO) and the Council's Legal Counsel.

The legislation would make the following overall changes:

- Reorganize the budget and reporting chapter,

- Reflect the change from annual to biennial budgeting,

- Update definitions, as needed, in Title 4A,

- Incorporate updated county policy documents, such as the Comprehensive Financial Policies adopted by the Council in April,

- Align with current operational practices,

- Align with King County Charter,

- Align with the county financial system (ABT),

- Delete flexible budgeting, replacing with a capital fund contingency model,

- Update reporting requirements to reflect changes such as move to contingency model for unanticipated needs,

- Clarify when and in what timeframe lease or use agreements should be transmitted to the council for approval,

- Update requirements for Mandatory Phased Appropriations (MPA) and aligns with capital improvement program oversight,

- Officially establishes the Capital Projects Oversight Program in the Auditor's Office, and

- Update the Joint Advisory Group processes to reflect current practices.

Reorganization of Chapter 4.04

Certain sections in the current KCC were often not located with similar subject matter areas.  The rewrite would organize those sections to accomplish a more logical flow within the chapter.  As an example, KCC 4.04.247 language dealing with CIP supporting data and procedures would be repealed and the language moved into the capital program section where the data requirements are able to inform the capital budget requirements.  Another example is that KCC 4.04.266 regarding the major maintenance financial program would also move into the capital budget requirement area.

Move to Biennial Budgeting

The 2015-2016 budget will be the first county budget that is biennial across all appropriations.  As a result, references to budgeting in annual or yearly time frames will be updated to reflect the county's move to biennial budgeting.  Any remaining annual references in the rewrite are related to state law or to other requirements.  As an example, the Comprehensive Annual Financial Report (CAFR) and state audits are required annually, as are some Comprehensive Plan updates.  However, most references would be to biennial budgeting.

Updates Definitions

Definitions have been updated to reflect the rewrite.  Ordinance 17229, adopted in 2011, aligned Title 4 definitions with the Accountable Business Transformation (ABT) project management system – the project to convert the County to a unified accounting and budget management system – and moved Title 4 definitions to the new Title 4A.  In the rewrite, these 4A definitions are further amended to reflect the proposal.  As an example, "scope change" was previously undefined and has been added.  Other definitions have been updated or removed to align with the proposal.

Incorporates County Policy Documents and Operational Practices

The Council has adopted policies that are reflected in the rewrite legislation, such as the King County Strategic Plan, the move to agency business plans, the Real Property Asset Management Plan (RAMP), the Technology Business Plan and Benefit Achievement Plans (BAPs), the Comprehensive Financial Policies, and the Equity and Social Justice Initiative.  Previous references to operational master plans and facility master plans have been removed because the components of these plans are now incorporated in other planning documents.  As an example, agency business plans should reflect current and future operational and capital planning components and will replace the need for operational master plans and facility master plans.  (K.C.C. chapter 2.10 defines business plan components.)

In the capital project oversight section, the current practices for representation and administration of the Joint Advisory Group have been updated.

Aligns with the King County Charter

The proposal reflects the current King County Charter.  As an example, in 2009, the voters approved the repeal of Section 475 of the Charter that required the executive to provide estimates or "allotments" of what each county agency would spend each quarter.  (In 2007, the King County Financial Policies Advisory Task Force recommended that the requirement be deleted from the Charter.)  This proposal incorporates the removal of allotments from KCC to reflect the change in the Charter.  It should be noted that because the Code and the Charter are often, and should be, aligned, any future changes to either document will need to be incorporated in the other.

Aligns with the County Financial System

In 2012, King County launched an integrated system called the Accountable Business Transformation Program (ABT) to manage its financial, human resources, payroll, and budget operations.  Components include:

- PeopleSoft Human Capital Management, Time & Labor and Payroll system

- Oracle E-Business Suite (EBS) Financial system

- Hyperion Budget system

ABT tracks all budget accounts at the lowest possible level, allowing review at a detailed level.  The Code previously required that a detail spending plan accompany the budget to show this financial activity at the section level.  The rewrite would delete this requirement because the document was administratively burdensome and frequently out of date.  However, it should be noted that the rewrite would require that the budget transmittal must include access to database details, so there is no question as to the availability of the information.

Institutes Capital Fund Contingency Model and Deletes Flexible Budgeting

The King County Code currently includes "flexible budgeting" provisions for five separate capital programs, including the Major Maintenance Reserve Fund (MMRF), Roads, Solid Waste, Wastewater and Surface Water Management.  Flexible budgeting is a several step process for approving capital project budget adjustments without using the supplemental budget appropriation procedures.  A rough outline of the current process includes:

- Identification of a capital project or projects that need changes in adopted expenditures authority

- Written notification by the Executive to the assigned Committee Chair and thus the Council

- A 14 day waiting period for councilmembers to reply to the Chair

- A 30 day period to respond to the Executive's request

- If there are any objections, the budget adjustment is not approved

- If the Chair notifies the Executive that there are no objections or does not respond to the Executive’s letter, the budget adjustments are approved

The budget and reporting section would eliminate the flexible budgeting process, resulting in a significant policy change on how to manage expenditure authority for capital projects experiencing unanticipated needs.  Unanticipated needs are usually the result of project delays, insufficient cost estimates at the time of appropriation, or scope changes.

Proposed Ordinance 2014-0439 would introduce a new approach by instituting the ability to approve an appropriation in each capital fund at the time of budget adoption to address evolving needs.  The rewrite refers to these projects as emergent need contingency projects.  Using this approach, the size of these contingency projects may not exceed five percent of the total proposed fund amount for the fiscal period or ten million dollars, whichever is less.  (Mandatory phased appropriation – MPA – projects would not be eligible for this process.)

Capital project appropriations requiring a transfer of less than 15 percent of a project's total budget must be reported in the quarterly management and budget reports.  For transfers of 15 percent of more, the Executive must notify the Council in advance of any action.  Councilmembers would be informed of the request by inclusion on a Council agenda at an open public meeting.  Members would have two meetings to raise any objections.  If an objection is made, the transfer may not proceed.  If no objections to the transfer occur, the Clerk of the Council would notify the Director of the Office of Performance, Strategy and Budget of the outcome.

Reporting Requirements

Quarterly management and budget reports are created by the Office of Performance, Strategy and Budget.  Reporting requirements for these reports have been updated to include reports on emergent needs contingency project transfers, use of reserves exceeding two percent, and on baselined capital projects greater than $1 million.

Lease and Use Agreements

Currently, K.C.C. 4.04.040 requires that the Council approve leases when the County is a lessee and the term of the agreement is longer than two years.  However, the Council has often received these approval ordinances well after a lease has been executed.  The amended language would clarify processes and state that any lease, including potential options, extensions or renewals, for longer than five years must be approved by the Council before execution of the lease agreement by the Executive.  Also, any lease with tenant improvements or other alterations to the property in excess of $50,000 for the benefit of the county, regardless of the term of the lease, must be approved by the Council before execution by the Executive.

Mandatory Phased Appropriations (MPAs)

In 2010, the Council passed Ordinance 16764 that required new controls for high value capital projects, including appropriation by project phase.  (Phases include planning, preliminary design, design and acquisition, and implementation.)  These projects are now referred to as mandatory phased appropriations or MPAs.  The MPA program standardized reporting requirements for all capital project appropriation requests and required quarterly reporting.  MPA quarterly reports address performance relative to project baseline, highlight any significant variance from project baseline, summarize the top risks in the risk register, summarize change orders, explain change orders that have the cumulative potential to carry the project over project baseline and summarize the results of the latest earned value analysis.

The requirements in 4.04.245 and 4.04.246 had not been updated and the language needed to be updated to reflect current terminology and practices – many of which have been established by the Capital Project Management Working Group (CPMWG) to improve project management and functions to assure accountability and transparency.  Council staff has worked with PSB, affected departments, and the Auditor's CPO program staff to update the code requirements to reflect refinements in value engineering reporting and risk assessment reporting deadlines, increasing the amount of appropriation that can be expended by non-General Fund projects before MPA requirements are triggered, and clarifying types of capital projects that are exempt from MPA requirements, including exempting open space acquisition because they are generally single phase.

Capital Project Oversight Program

The 2007 budget included the capital projects oversight program within the King County Auditor's Office.  The program was established to mitigate capital project overruns and potential problems, contain costs, and inform decision-making processes through adequate, timely and useful standardized reporting.  However, the program was not formally established in the KCC.  This ordinance would include the program in code.

Real Estate and Major Capital Projects Review Joint Advisory Group (JAG)

In 2004, Ordinance 14921 established the JAG to provide coordination and policy level discussion between the executive and legislative branches of government for real estate asset management and major capital project discussions.  The JAG is codified in the existing code in K.C.C. chapter 4.06.  Proposed Ordinance 2014-0440 would update the code to reflect the group's current practices.

AMENDMENTS:

An amendment and title amendment are being prepared to address identified corrections to the ordinance.  The amendments will make the following corrections:

- Inserts two words that were inadvertently omitted in the final version;

- Adds a section regarding the "leasing" requirements to provide a window of time within which the executive must transmit for council approval those executed leases that would not comply with the revised requirements;

- Changes use of reserve reporting for significant funds from a two percent threshold to a five percent threshold;

- Inserts a definition in 28.86.010 to define "operational master plan" for the chapter because it is deleted in Title 4; and

- Asks the clerk to renumber the sections, as needed.

The title amendment reflects the amending of 28.86.010.

As noted in the background section of this report, ordinances will be forthcoming to address remaining Title 4 subject areas in 2015.

INVITED:

- Anne Noris, Clerk of the Council

- Bruce Ritzen, Code Reviser

- Dwight Dively, Director, PSB

- Sid Bender, CIP Budget Manager, PSB

- Aaron Rubardt, Analyst, PSB

ATTACHMENTS:

(Attachments are the same as last week.  Amendments will be distributed at the meeting.)

Accountable Business Transformation

Previously termed "high risk"

This link will direct to the Executive's CPMWG website:  http://dnr-web.metrokc.gov/projects/cpm/index.htm