## Sheet1
Defense Team Partial-Year Technology Request
State v. Ridgway
|  | Hours | Rate | Amount
PHASE I: INFRASTRUCTURE SET-UP
Preliminary design
| N. Yee | 10 | 110 | 1100
| G. Placencia | 10 | 85 | 850
Coordination with KCPO/PG&E
| N. Yee | 40 | 110 | 4400
| G. Placencia | 40 | 85 | 3400
Equipment specification and ordering
| N. Yee | 4 | 110 | 440
Equipment setup and testing
| N. Yee | 8 | 110 | 880
| Certus Network/IS staff | 15 | 110 | 1650
Summation Database development
| N. Yee | 4 | 110 | 440
| Certus Staff | 4 | 65 | 260
| Server hardware, software, misc. network equipment <a> |  |  | 15000
| Summation software 15-node license <a>, <b> |  |  | 10016
| Laptop computers for ACA <c> | 3 | 2200 | 6600
PHASE II: TEAM TRAINING
Training Prep
| N. Yee | 8 | 110 | 880
| G. Placencia | 8 | 85 | 680
Summation Database Training
| N. Yee | 80 | 110 | 8800
| G. Placencia | 80 | 85 | 6800
Individual one-on-one tutoring
| G. Placencia | 80 | 85 | 6800
PHASE III: INTERNAL DOCUMENT MANAGEMENT <d>
Preliminary design
| N. Yee | 8 | 110 | 880
| G. Placencia | 8 | 85 | 680
Document scanning
| N. Yee | 4 | 110 | 440
| Certus Staff | 24 | 65 | 1560
Objective document coding
| N. Yee | 2 | 110 | 220
| Certus Staff | 12 | 65 | 780
| Certus Clerks | 24 | 25 | 600
TOTAL |  |  |  | 74156
Notes:
<a> This amount has been reduced since the preliminary proposal provided to the Council. Based upon
further research and other cost-savings measures, Certus is able to reduce the expected actual costs for these items.
<b> If additional lawyers and/or investigators are added to the team, the number of concurrent software seat
licenses may need to be increased.
<c> Laptop computers were not originally included in the preliminary Certus proposal provided to the Council.
Per David Chapman, the cost of these laptops are included in this "Immediate Needs" budget.