##### Metropolitan King County Council

Capital Budget Committee

| AGENDA ITEM No.: | 2 |  | DATE: | April 5, 2006 |
| --- | --- | --- | --- | --- |
| PROPOSED No.: | 2005-0460 |  | PREPARED BY: | Patrick Hamacher |

STAFF REPORT

SUBJECT:

Proposed MOTION 2005-0460 would approve a request for proposal (RFP) to solicit proposals for the consolidation of elections operations into a single facility.

BACKGROUND:

In adopting the 2005 2nd Quarter Omnibus ordinance, the Council inserted a proviso requiring the Executive to transmit a Request for Proposals (RFP) for facilities that would provide for consolidation of elections operations. This illustrated the desire of the Council to conduct an open and competitive process to find a facility.  The Council’s requirement is also consistent with the intent of Motion 12099 which directed the Executive to consider a range of options to consolidate elections.

Council oversight and leadership of King County elections operations has steadily increased from 2002 to the present.  This is due to a number of serious management and operational problems that were manifested in numerous elections.  County elections operations have been reviewed by the Secretary of State, three citizen groups, and a consultant; and, an independent audit has been done by elections experts.  To date, six reports have been issued with long-term and short-term actions to improve the conduct of elections and restore voter confidence.

Many procedures have been changed and documentation improved, but more work remains.  A common theme among five of the six reports to date, was the recommendation for consolidation of elections ballot operations into a single facility.  This means that the elections ballot processing functions located at the 5th floor Administration Building, the Elections Distribution Center (EDC) at 12th and Fir, and the Mail Ballot Operations Satellite (MBOS) functions should be co-located into a single facility.

The Executive’s proposal for the 1130 Rainier Building did not include the EDC Warehouse function based on an interpretation that the close proximity of the two facilities would satisfy the intent of consolidation.  However, the subsequent Audit of King County Elections Operations (October 3, 2005) and the CEOC final report (March 2006) specifically include the EDC warehouse function as a necessary component of elections consolidation recommendations.

Temporary Elections Relocation:

In a letter dated October 18, 2005, the Director of Records, Elections, and Licensing Services Division, informed the Council that effective October 24, 2005, mail ballot operations would be relocated from their current location in the Mail Ballot Operations Satellite (MBOS) facility on First Avenue South to new leased space at the Airport Office Center (AOC) Building located on East Marginal Way at King County Airport.  It is anticipated that all remaining elections (primarily ballot tabulation) will be relocated to the AOC prior to MBOS lease termination in May 2006.

All-Mail Voting System:

On Tuesday December 20, 2005, the Executive announced his recommendation for an all-mail voting system for King County.  According to newspaper reports, the system could be in place in time for the primary election in either 2006 or 2007.  If implemented, King County would become the largest all-mail voting system in the nation.  The Executive asked the Director of Elections to submit an implementation plan by the end of January 2006 and that has been done.  However, legislation has not been transmitted that would authorize a switch to all-mail voting.  According to newspaper accounts views differ as to whether or not a transition to an all-mail voting system in King County could be implemented as early as 2006 or 2007.

ANALYSIS/CURRENT STATUS:

The Executive’s transmittal letter for the proposed legislation recommended a broker assisted process rather than the Council recommended RFP methodology.  On November 30, 2005, the BFM Committee was briefed on the proposed RFP legislation.  Council staff requested and received committee direction to proceed with application of a “Solicitation for Offers” (SFO) selection methodology proposed by the Council’s independent consultants, Staubach NW LLC.  This alternative solicitation methodology, used nationally by the General Services Administration (GSA), combines the advantages of the Council-preferred open, competitive, public process of an RFP with the flexibility of the Executive-recommended brokerage firm process.  A detailed comparison of alternative procurement methods (SFO broker assisted, broker market search, and RFP methodologies) was included in the November 30th staff report.

Between the November 30th committee meeting and January 12, 2006, Council staff, Executive staff, Elections Division representatives, the Prosecuting Attorney’s Office (PAO), the Council’s legal counsel, and Staubach representatives continued to incorporate the unique County and elections consolidation requirements into the GSA “Solicitation for Offers” format.  Progress was slower than anticipated due to the holiday season.  On February 1, 2006 a letter was sent to the Chair of the Capital Budget Committee from Kathy Brown, Director, Facilities Management Division, stating that proposed legislation regarding the new SFO concept would be forwarded soon.  However, proposed legislation still has not been received.

The February 1 letter also notified the Chair that a preliminary cost analysis was being prepared to evaluate the feasibility of constructing a new consolidated elections facility on County-owned property adjacent to the new county garage.  Per the letter, the FMD analysis showed that a build-to-suit new facility would cost less than providing elections space in the new County office building (NCOB).  FMD estimated that a new facility could be constructed for roughly $178 per square foot, as opposed to $247 per square foot in the NCOB.  The letter further stated that FMD was committed to continuing market research to see if there is an acquisition option on the market that could achieve greater savings for the county. Council staff has not yet received any additional information regarding these estimates.

Data Center:

Another issue that is also pending is the relocation of the County’s Data Center. There need to be preparations made for the transfer of this function when their lease in the Seattle Municipal Tower expires at the end of 2007.  Preliminary analysis shows that a location outside of the downtown core, such as Tukwila, could provide savings to the County. There are also strategic reasons for examining the location of this function outside of downtown Seattle. If the Goat Hill site is pursued, however, inclusion of the Data Center on that site may provide for efficiencies. This move may also allow the County to adhere to policy when building a new facility by building the site out to its full potential.

Elections Programming:

In the 2nd Quarter 2005 Omnibus CIP Ordinance (15246), the Council appropriated $75,000 for the Executive to complete the elections program and prepare an RFP.  These funds were authorized because the program was incomplete in July and Staubach representatives reported to the committee that the program was fairly conservative and needed further refinements.  Additionally, the architect that had prepared the draft elections program in July 2005 stated that additional efficiencies could be realized if programming specialists familiar with elections processing were retained to complete the program.  Ultimately, finalization of the program was assigned to in-house Facilities Management Division (FMD) staff working with elections representatives.  The program was still incomplete at the time the legislation was transmitted in October 2005.  Executive staff provided written explanation regarding the status of the draft elections program which is summarized below:

- Changing Requirements:  The July program assumptions (44,000 rsf) were based on previous elections.  Subsequent to development of the July program the Elections Division has incorporated numerous new legally-required accountability standards, internal processes, and quality improvements during the September 2005 Primary Election.  These changes have tended to increase space needs

.

- Opportunity to Test Assumptions:  The experience gained in the September primary forced a reconsideration of previous program assumptions.  The decision to temporarily relocate MBOS functions to the AOC has provided an opportunity to test the program assumptions in a live election but under temporary conditions.  The move became the number one priority.

An updated draft elections program was provided on January 12, 2006; however, despite assurances, the program requirements continue to be modified.  The July 2005 program for elections at the 1130 Rainier Building provided for 44,000 rentable square feet of office and ballot processing space; this was projected as the space needed for an all-mail ballot.  However, the EDC Warehouse function was excluded entirely based on the interpretation that the two facilities were in reasonably close proximity to each other and that consolidation of the EDC warehouse was not necessary.

In December 2005, after the elections audit and CEOC draft recommendations clarified the intent that the EDC warehouse was a necessary component of consolidation, the draft SFO requirements were modified to provide for a flexible facility that could accommodate both an all- mail vote system plus the current polling place vote system.  In January 2006, following the Executive’s all mail vote proposal, executive staff modified the program to exclusively accommodate only an all mail voting system.  To date, the Council has not yet received any legislation pertaining to all-mail voting. Table 1 provides a summary of the programmed space calculations beginning with the Executive’s proposal to purchase the 1130 Rainier Building (July 2005) to the most recent proposal for a facility that would accommodate all-mail voting only.

Table 1:  Elections Program Transitions

|  | Exclusive All Mail Vote Draft Program | Flexible All Mail Vote + Existing Polling Place Warehouse Storage** | 1130 Rainier Bldg Draft Program* & Proposed Legislation RFP |
| --- | --- | --- | --- |
|  | 01/06 | 12/05 | 07/05 |
| Office & Mail Ballot Processing | 56,122 | 45,000 | 44,000 |
| Poll Distribution Center | 17,253 | 30,000 | 0 |
| Total | 73,375 | 75,000 | 44,000 |

*   Excluded 20,000 RSF EDC Warehouse at 12th and Fir

** EDC Warehouse space needs increased to accommodate HAVA required accessible voting machines

The draft program appears to reaffirm the architect’s recommendation that efficiencies could be achieved with the aid of specialty programming expertise. Section 3.3.2.3 Cyclical Workload states in part:

“Current operations and facilities are functioning on a ‘make-do’ basis and could be substantially streamlined through investment in process analysis, equipment, training and an ’intentional’ design effort.”

The Committee may want the Executive to search for a facility that could accommodate both the current dual-voting system and an all-mail voting system until such time as a formal voting system policy decision is made by the full Council.  If so, then policy direction is needed to direct a modification to the search requirements.  At a minimum, the current programmed space needs for the warehouse storage function (poll distribution center) would have to be increased by approximately 12,747 RSF - from 17,253 rentable square feet to 30,000 rentable square feet (RSF).   However, acquisition of a facility that could accommodate both the current dual-voting system and all-mail voting would be more costly than a facility designed solely for all-mail voting.  And, if the County eventually transitions to an all-mail voting system, the warehouse space would be oversized by approximately 12,747 RSF (74%) due to the reduction of voting equipment storage.  In this eventuality, it would likely be possible to convert this extra space to other County uses, such as records archives, however.

Temporary Elections Annex (TEA):

The TEA currently is located at the Airport Office Center (AOC).  It is understood that the ballot tabulation function, which is currently housed at the MBOS, will be moved to the TEA facility sometime prior to the MBOS lease termination in May 2006.  According to Executive staff, the AOC has adequate additional vacant space that could be used to accommodate a transition to an all-mail voting system.

Solicitation For Offers:

As noted earlier, staff to staff discussions to merge the County format and GSA Solicitation for Offers format have not occurred since January 12th.  However, a selection of previously discussed key topics include the following:

- Occupancy Dates:  The SFO will include multiple potential occupancy dates which are contingent upon whether the proposal is for a lease or lease with option to own in an existing building or a ground up development.

Latest Occupancy Date:	June 2009 – Ground up development without a Master Use Permit

Preferred Occupancy Date:	June 2007 – Lease/ownership option in an existing building

- Parking and Access:  Parking and access requirements are based on the numbers of regular and peak temporary employees, observers, and delivery vehicles.  Parking and access requirements will have a significant influence on the selection of a facility.

- Facility Location:  At the last Committee meeting, members were informed that the search criteria discussions include areas outside the downtown core (approximately 12 miles) and included such areas as Shoreline, White Center, Burien, Tukwila, and Renton. The most recent draft from the Executive has narrowed this language to the following:

  - A: The acceptable location range is within approximately 15 minute peak traffic drive time of the King County Administration Building/downtown Seattle core. The preferred site is loosely defined as an area bounded by 1) US Postal Service Outgoing Mail Center @ 4th Ave. S. and Lander St.; 2) US Postal Service Central Distribution Center @ E. Marginal Way; 3)Diebold printer @Mukilteo. Should the proposed location significantly vary from the desired location, the square footage requirement may need to be increased for added warehouse and distribution capacity.

  - B: Acceptable location will be within 2 miles of I-5, and other major arterials such as Highways 99, 518, 405 and 509.

- Project Budget:  Executive staff have stated that a supplemental appropriation request will be forthcoming to fund the elections consolidation search process.

- The most recent version also includes language indicating a preference for choosing a location between the printing vendor and the US Postal Service facilities.

Furthermore, Council staff has received comments back from Staubach Northwest, the firm providing independent consultation on this issue to the Council. Staubach has some additional concerns which are summarized below.

- Language related to the identification of a building in “warm lit shell” condition has been removed.

  - This has the net effect of making an apples to apples comparison very difficult. This is a fundamental piece of the SFO process.

  - Executive staff have indicated that the removal of this language was not intended and that it would be added back into the SFO. This has not yet occurred as of the most recent draft.

- Staubach further delineated the items which they believe should be included in the SFO, they are:

  - Security Requirements

  - Role of the broker and the role of the County

  - The process by which the proposals will be evaluated

  - Typical base building requirements.

- It should be noted that on the items listed above, Council staff has noticed that some items are included in the most recent draft of the SFO, but we have not yet had sufficient time to assure that all areas have been addressed.

- Finally, Staubach indicated that the SFO should attempt to eliminate any things which could be considered variables depending upon the build out.

  - Council staff has not yet had sufficient time to examine whether these items have been eliminated from the most recent draft.

TIMELINE OF ELECTIONS RELATED EVENTS AND COUNCIL ACTIONS:

February 1, 2006 Letter Regarding a Preliminary Cost Analysis for a Consolidated Elections Building on Goat Hill

On February 1, 2006 a letter was sent to the Chair of the Capital Budget Committee from Kathy Brown, Director, Facilities Management Division, notifying the Chair that a preliminary cost analysis was being prepared to evaluate the feasibility of constructing a new consolidated elections facility on county-owned property adjacent to the new county garage.  Per the letter, the FMD analysis showed that a build-to-suit new facility would cost less than providing elections space in the new county office building (NCOB).  FMD estimated that a new facility could be constructed for roughly $178 per square foot, as opposed to $247 per square foot in the NCOB.

January 12, 2006 Latest Executive/ Council staff SFO negotiation meeting

Executive staff announced that the latest elections program update that included the Executive’s proposed all-mail voting system increased the size of the facility to 73,000 square feet, including 17,000 square feet of warehouse space.

December 20, 2005 Executive proposed all-mail voting system for King County

To date, no legislation has been submitted to implement this proposal.

December 7, 2005 BFM Committee reviewed Proposed Motion 2005-0460

Prior Council action required the Executive to transmit an RFP to determine a site for a consolidated elections facility.

November 30, 2005 BFM Committee reviewed Proposed Motion 2005-0460

October 25, 2005 Executive transmitted Proposed Motion 2005-0460, the Elections RFP

The Executive’s recommendation was for a traditional broker-assisted methodology, where the County would hire a real-estate broker to find a site for consolidated elections facilities.

October 25, 2005 Executive transmits a request for supplemental appropriation.

The Executive proposed spending $50,000 to pay a real estate broker to assist the County in finding a property for elections consolidation.

October 10, 2005 Adopted Motion 12206

Council adopted Motion 12206 requesting the Executive to undertake actions to improve the conduct of the elections process in King County.

July 25, 2005 Ordinance 15426, 2nd Quarter Omnibus

The Council added a proviso requirement for the Executive to transmit an RFP for elections consolidation. The RFP was due on October 15, 2005.

April 25, 2005 Adopted Ordinance 15157

The Council adopted an ordinance establishing the King County Elections Oversight Committee

April 18, 2005 Adopted Motion 12107

Council adopted Motion 12107 calling for an independent and comprehensive audit of the elections section of the King County Records, Elections, and Licensing Services Division.

April 4, 2005 Adopted Motion 12099

Council adopted Motion 12099 directing the Executive to undertake actions to improve the conduct of the elections process in King County and supporting election reforms in Washington State.  Motion 12099 directs the Executive to undertake previous recommendations of the Citizen’s Election Oversight Committee and the Labor, Operations and Technology Committee, and proposed by the Director of Records, Elections, and Licensing Services.

March 28, 2005 Adopted Motion 12096

Council passed a Motion identifying essential election reform measures for King County support in the Washington State Legislature.  The Motion urged changes in Washington State law to move the date of the state’s primary election to an earlier date, extend the certification time for primary and special elections from 10 to 15 days, and extend the certification time for general elections from 15 to 20 days.

August 30, 2004 Adopted Motion 11987

Council passed Motion 11987 adopting a work plan to implement recommendations of the King County Election Citizen’s Oversight Committee.

The motion adopted a work plan and required the manager of records to file quarterly reports on implementation of the work plan.

July 14, 2003 Adopted Ordinance 14711

Council adopted Ordinance 14711 establishing a Citizen’s Election Oversight Committee.

March 2003 Council Hired Consultant

Council hired an elections consultant to conduct an independent review of County elections.

February 3, 2003 Adopted Ordinance 14570

Council adopted Ordinance 14570 which revised the management and organization of the Records, Elections, and Licensing Division to include Council confirmation of persons serving in the position of division director, records, elections and licensing services division, and the position of superintendent of elections, elections section.

NEXT STEPS:

- Council Staff needs direction in the following areas:

  - Location of the Facility

  - Factors for Preference in evaluating bids (other than price)

- Once this direction is provided, Council Staff will work to finalize a document for Committee adoption.

INVITED:

Kathy Brown, Division Director, Facilities Management Division

ATTACHMENTS:

- Proposed Motion 2005-0460

- Transmittal Letter, dated October 25, 2005

- Letter regarding NCOB and elections consolidation on the Goat Hill site, dated February 1, 2006

- Site-Plan of Goat Hill site

Leased Space: Technically the space is part of a space use agreement between King County Property Services and King County Airport.

HAVA; Help America Vote Act.