Metropolitan King County Council

- Regional Policy Committee

Staff Report

| Agenda Item No.: | 6 |  | Name: | Kelli Carroll and Beth Mountsier |
| --- | --- | --- | --- | --- |
| Proposed Motion No.: | 2014-0269 |  | Date: | September 10, 2014 |

SUBJECT

Proposed Motion 2014-0269 accepts the annual progress report on the implementation of the King County veterans and human services levy service improvement plan, as required by Ordinance 17200.

SUMMARY

Proposed Motion 2014-0269 (Attachment 1) accepts the 2013 annual progress report on the implementation of the King County Veterans and Human Services (VHS) Levy Service Improvement Plan as required by Ordinance 17200.  This legislation had a dual referral to the Law, Justice, Health, and Human Services (LJHS) Committee.   LJHS has taken action to give a ‘do pass’ recommendation.

A briefing on the report was presented to the committee on July 9, 2014 familiarize the committee with the progress report.   Questions regarding the report and the Community Services Division responses are attached to this staff report (Attachment 2).

This is the second annual report for the 2012-2017 VHS Levy. This report documents King County’s implementation of the activities and strategies identified in the Veterans and Human Services Levy Service Improvement Plan. The transmitted report contains a description of services and the status of activities, individual program statistics by strategy and activity, a report from the VHS Levy boards, and an evaluation report.

Representatives of the oversight boards for the VHS Levy implementation are anticipated to address the committee at the September 10th meeting.

BACKGROUND

The Renewed Levy: In 2011, King County voters approved a renewed Veteran’s and Human Services Levy (VHSL) which provides approximately $15-18 million per year ($0.05 per $1,000 assessed valuation plus annual increases by the percentage increase in the consumer price index or 1 percent, whichever is greater, with a maximum increase of 3 percent) for six years starting in 2012. Fifty percent of the levy proceeds is dedicated to these services for veterans, military personnel and their families; and fifty percent is dedicated to improving health, human services and housing for a wider array of people in need.

The levy’s purpose is to provide revenue that supports health and human services such as housing assistance, mental health counseling, substance abuse prevention and treatment, and employment assistance, as well as capital facilities and improved access to and coordination of services for veterans, military personnel and their families.

Levy proceeds are to be used to pay the costs associated with provision of regional health and human services to a wide range of people in need of such services, including, but not limited to:

- Services that increase self-sufficiency for veterans, military personnel and their families

- Services that reduce involvement in the criminal justice system

- Services that reduce emergency medical costs

- Services for children and youth, the elderly, the unemployed and underemployed

- Services specific to veterans' needs such as treatment for posttraumatic stress disorder and specialized employment assistance

- Costs associated with strengthening and improving health and human services system and infrastructure to provide greater access to services and engender better coordination and integration of regional health and human services addressing the needs of veterans, military personnel and their families

The provision of services include a range of regional health and human services and related capital facilities including, but not limited to, housing assistance, homelessness prevention, mental health counseling, substance abuse prevention and treatment and employment assistance.

Oversight: The first levy was overseen by two community boards, the Veterans Citizen Levy Oversight Board (VCLOB) and the Regional Human Services Levy Oversight Board (RHSLOB). The boards play an integral role in reviewing the plans for expenditure of levy proceeds and monitoring progress of service and program implementation.  These two boards continue in the second levy period.

Reporting: The renewed levy will also continue regular reporting to the King County Executive and the County Council of performance evaluation and financial status information. Ordinance 17200 specifies that an annual report shall be transmitted to the Council by June 30 each year of the levy. Performance reports are included with each annual report.

Ordinance 17200 also outlines the specific reporting requirements of the VHSL annual reports, calling for:

- A description of services procured and delivered to date and the status of service and project and activity implementation

- An updated, detailed financial plan that includes

- Individual program statistics for by strategy, sub-strategy, activity or program

- The geographic distribution of levy resources across the county, including numbers of individuals served by jurisdiction

- A report or reports from the Citizen Oversight Boards regarding their assessment of progress and any recommendations they may have for improvement of levy program operations and result

- Detailed explanation of any revisions to the adopted service improvement plan strategies, activities or should any strategy or activity be eliminated or added, and should there be any changes to allocation plan's funding amounts for any strategy or activity greater than fifteen percent

- An evaluation report that identifies outcome and output targets and assesses performance by the county and its contractors strategy, sub-strategy, activity and program in meeting the identified outcome and output targets.

Funding Requirements: Ordinance 17200 identifies explicit amounts (or up to a specific amount) of funds to set aside from the levy for certain purposes. The set aside amounts and areas are as follows:

- Up to $2.5 million per year that may be set aside for housing capital, including funding of transitional housing for homeless youth and young adults

- At least $2 million per year from the portion of the levy proceeds used for services for veterans, military personnel in need and their families that shall be expended on maintaining the expansion and improving current county veterans program services

- At least $2.5 million from the portion of the levy proceeds used for services for veterans, military personnel in need and their families shall be expended on strategies, sub-strategies, programs and activities related to veterans justice programs including the veterans incarcerated program, veterans legal assistance, the veterans treatment court or other emerging veterans justice programs

- At least $1 million per year from the portion of the levy proceeds not specifically designated for services for veterans, military personnel in need and their families that shall be invested in early intervention and prevention programs that have demonstrated effectiveness in reducing dependency and criminal justice problems in the long run

In addition, Ordinance 17200 limits the county's administrative expenses for managing and administering the levy proceeds to five percent, excluding evaluation and board support expense.

The Service Improvement Plan: In December 2011, the Council passed Ordinance 17236 adopting the VHSL service improvement plan for 2012 through 2017. The service improvement plan (SIP) provides guidance on the goals, investments and implementation of the King County VHSL. The SIP outlines the 2012-2017 levy goals as follows SIP goals:

2012-2017 Levy Goals

1. Prevent and reduce homelessness.

2. Reduce unnecessary criminal justice and emergency medical system involvement.

3. Increase self-sufficiency of veterans and vulnerable populations.

The 2012-2017 SIP also requires that the Department of Community and Human Services to work in cooperation with other county departments and branches of government and with the levy oversight boards to ensure that the goals and strategies of the levy are achieved.

The SIP describes VHSL priority populations and investment areas, specifying them as follows:

- Veterans, military personnel, and their families who are struggling with mental and physical health problems, unstable housing or homelessness, or unemployment and in need of supports that will help them build on their strengths and respond to the unique challenges they face

- Residents who are currently experiencing instability in their lives resulting in involvement in the homelessness, criminal justice, or emergency medical systems.

- Families and individuals for whom prevention and early interventions will help lay the foundation for a successful future and prevent involvement in crisis systems.

Similar to the first levy, the plan states that while many activities are focused on families and individuals who have already become involved in costly public systems, the renewed levy SIP recognizes that it is also important to target those who are at-risk of such involvement. The levy will also continue to invest in proven interventions for mothers and children at the very earliest point of their lives, prenatal to age three.

The plan notes that further targeting of people and communities to be served with levy resources occurs at the level of the specific program activity. Similar to the first SIP, need continues to be a key factor in allocations and activities.

Levy Strategy Areas: The levy funds are dispersed into the four strategy areas outlined in the box below:

- Veterans and Human Services Levy Strategy Areas 2012-2017

- Supporting veterans and their families to build stable lives and strong relationships

- Ending homelessness through outreach, prevention, permanent supportive housing and employment

- Improving health through the integration of medical and behavioral health services

- Strengthening families at risk

2013 ANNUAL REPORT HIGHLIGHTS

Specific highlights include:

- Five new levy-supported affordable housing projects opened, providing 252 new housing units

- Data on 112 individuals placed in housing through the Client Care Coordination program showed use of community psychiatric hospital days declined by 85 percent and emergency department admissions declined by 66 percent

- Eighty-seven percent of the 204 homeless individuals served by Community Employment Services found employment, with 70 percent earning enough to be self-sufficient

- The Cultural Navigator Program provided linguistically and culturally appropriate services to 1,016 individuals, assisting them with referrals, and employment and health insurance applications

- The Veterans Call and Services Center received 914 calls from veterans seeking information or assistance, with nearly all being connected to veteran specific resources such as housing, health care, and employment training

- The Veterans Legal Assistance Program served 236 veterans needing assistance with civil cases; 63 cases were resolved

- The Nurse Family Partnership had 244 individuals enrolled, nearly double the target of 133

- There were 2,554 individuals screened in the maternal depression reduction program

The report states that 38,298 individuals and families, including 7,312 veterans and their families were served by VHSL programs. However, subsequent data from the department indicates that the veterans’ number is slightly greater at 7,907 veterans and their families. Compared to 2012 report data, the adjusted total figure of 38,893 reflects a decline of over 14,000 served.

The department indicates that in terms of the overall decline, there were some programs that saw numbers increase while other programs experienced decline.  Staff reported that the Public Health program “Play and Learn” accounted for the largest drop (from 17,976 in 2012, to 5,420 in 2013), due to the fact that previous data submissions reported duplicate clients in 2012 and before. DCHS notes that its staff is reviewing data numbers contained in the report.

Evaluation and Performance Report

As required by Ordinance 17200, an evaluation report that identifies outcome and output targets, and assesses performance by the county and its contractors by strategy, sub-strategy, activity and program in meeting the identified outcome and output targets is also required. The Executive has included this information in the annual report starting on page 19.

Evaluation and levy staff collected and analyzed year-end data and reports from 43 levy activities in 2013. A summary of performance data finds that of 38 activities and 88 individual service measures finds:

- 31 out of 43 activities achieved 85 percent of their target

- 12 activities reached between 85 and 66 percent of their target

- Zero activities fell below 65 percent of their target

The report indicates that evaluation staff met with underperforming contractors to collaboratively determine cause of underperformance and provide technical assistance. While this appears to be an improvement in the report over last year, the performance report does not specifically address issues or factors related to underperforming activities. Subsequent reports should include an analysis of underperforming activities.

The majority of individuals served lived in Seattle (44 percent) or south King County (42 percent), with the east showing about ten percent and north about four percent.

Annual Financial Report

The annual report is required to include the following detailed financial information:

- Total actual and projected revenue and expenditures for the veterans and regional human services funds for each year of the levy and cumulatively for the life of the current levy;

- the total amount of funding expended to date by strategy, sub-strategy, activity or program;

- the total amount of funding contracted to date by strategy, sub-strategy, activity or program;

- explanations of all changes from the previous year's financial plan and changes from the projected budget; and

- all levy operation and administration costs, including all full-time equivalents and term-limited temporaries supported by the levy, the number of contracts administered from levy funds.

The financial data submitted with the 2013 annual report contains all required information. In addition, the department included detailed information on updated financial management practices (Exhibit A to the annual report) demonstrating enhanced communication, review, and accountability of VHSL contracts.

ATTACHMENTS

- Proposed Motion 2014-0269 and attachments

- Responses from the Community Services Division regarding July 9, 2014 questions related to Briefing 2014-B0116

LINKS

Additional information regarding the Veterans and Human Services Levy and the Services Improvement Plan for 2012 – 2017 can be found at:

http://www.kingcounty.gov/operations/DCHS/Services/Levy.aspx