## Sheet1
Exhibit A
Ravensdale Scope Adds / Change Orders
Adds related to enhanced treatment system |  | 248236
Additional improvements to existing park area per request of King County |  | 8788
| Subtotal | 257024
King County Per Proposed Amendment | Plus Sales Tax | 279128.064
Adds to original project design / scope |  | 123225
Additional electrical wire & conduit do to error on the scale of drawings. |  | 43250
RPF Contingency and Additional Fundraising |  | 166475
ITEM DESCRIPTION | DATE | COST
SUBMITTED
Maintenance Building
Concrete & Paving around Maintenance Building | 2014-05-09 | 23500
Concrete Floor in Maintenance Building & Place Owner Provided Building Poles | 2014-05-09 | 25265
Provide 50 LF of Additional Electrical Trenching for Maintenance Building | 2014-05-09 | 540
Materials package for Maintenance building | 2014-05-09 | 25500
Sub total Building no assembly labor |  | 74805
County Permit Revisions per 4/9/14 Civil Revisions
Add Culvert & Ditch at Kent-Kangley Road | 2014-05-09 | 14113 | *
Add 1-1/2" Overlay at Kent-Kangley Road | 2014-05-09 | 45529 | *
Add 4" Concrete Sidewalk & Curb at Entry Drive | 2014-05-09 | 20354 | *
Add CBs, Storm Drain, and Bio-swale | 2014-05-09 | 33693 | *
Add Pre-settlement Vault | 2014-05-09 | 96427 | *
Add Flow Spreader | 2014-05-09 | 6536 | *
Backhoe, Operator, & Water Truck for Percolation Test - REVISED | 2014-08-15 | 1892 | *
Removable Baffle and Grating at Pre-settlement Vault - MATERIAL ONLY | 2014-09-08 | 22482 | *
Added Cost for 18" N-12 Pipe from South Field to North Field | 2014-09-08 | 5949 | *
Added Engineering for Contech Structures Revisions | 2014-09-18 | 1261 | *
Sub total enhanced treatment system adds |  | 248236 | *
Extra Concrete at Path and Bleachers at Phase I per request by King County | 2014-09-23 | 8000 | *
Remove For Additional Trees at NE Corner of Parking Lot - per request by King County | 2014-08-15 | 788 | *
Improvements to current part of park per request of King County. |  | 8788 | *
Added boys and girls Lacrosse lines and tick marks to both fields | 2014-08-10 | 23400
Added 256 LF of 16' High Netting | 2014-08-15 | 9814
Changes at Practice Area | 2014-08-18 | 7462
Added Cost for Revised Dugout Column Baseplates | 2014-08-19 | 1252
Clear Area for PSE Pad/Excavate for Transformer Vault - REVISED | 2014-09-08 | 17464
Added 4" Conduit for Data/WIFI | 2014-09-08 | 2664
Added Plumbing Work at CXT Building | 2014-09-15 | 12149
Hand Dig to Expose Existing Phase I Feeders for Potelco | 2014-09-18 | 366
Added railing to Plaza | 2014-10-01 | 15000
Maintenance add - asphalt to access to North field | 2015-03-23 | 15226
Maintenance add - asphalt to access South field | 2015-03-23 | 18428
Sub Total adds to project design / scope |  | 123225
Additional electrical wire do to error on the scale of drawings. | 2014-07-23 | 43250