## STAFF REPORT

| Agenda Item: | 7 | Name: | Greg Doss |
| --- | --- | --- | --- |
| Proposed No.: | 2015-B0203 | Date: | December 8, 2015 |

SUBJECT

This briefing provides an update on the current status of relocation plans for the Community Corrections Division of the Department of Adult and Juvenile Detention, and on plans for the redevelopment of the Yesler Building to house the new Department of Public Defense.

SUMMARY

The County continues to have a pressing need to relocate the County offices and programs currently located in the county-owned Yesler Building, which is slated for redevelopment to accommodate the employees of the newly created Department of Public Defense (DPD).  The primary current tenant  is the Community Corrections Division (CCD) of the Department of Adult and Juvenile Detention.

Based on predevelopment work funded last year, the Executive had planned to submit for Council approval a request for a capital appropriation and a redevelopment plan targeting CCD relocation in March 2015 and DPD moving in to Yesler in mid-2016. This schedule now faces significant delays and associated cost increases because the Faciliites Management Division (FMD) has been unable to find a suitable location to house the CCD programs.

The Executive has considered several CCD relocation options that have not proved viable because they were a poor fit for operational need, cost prohibitive or met with resistance that is typical to the relocation of a correctional facility.  FMD staff continues to contend with these issues and will provide the Committee with a briefing that will highlight their efforts over the last several months.  Executive staff have been asked to provide as part of today’s presentation an overview of the relocation options considered to-date, an updated project timeline and any costs associated with the delay.

BACKGROUND:

Council passed Ordinance 17882 in September 2014 to provide funding to support pre-development work associated with the potential redevelopment of the Yesler Building to house the new Department of Public Defense. Analysis supporting that ordinance identified the relocation of the primary current tenant of the Yesler Building, the Community Corrections Division (CCD) of the Department of Adult and Juvenile Detention (occupying approximately 15,000 square feet) as a significant risk within the proposed Yesler redevelopment timeline. Specifically, the Yesler construction will be delayed if CCD is unable to move to a suitable space on schedule, increasing both direct project costs and costs to maintain current space for DPD.

Also in September 2014, Council adopted leases for DPD offices in the Prefontaine Building (approximately 80 DPD employees) and Watermark Tower (approximately 65 DPD employees) downtown, to keep these new County employees in place until the Yesler redevelopment is complete. These leases were negotiated assuming consolidation of DPD staff in the renovated Yesler Building beginning in 2017.  King County holds an additional lease in the Central Building (through 2021) which houses approximately 74 DPD staff who would be expected to move to the redeveloped Yesler building.

The redevelopment of the Yesler Building was anticipated to begin in March 2015, but the redevelopment schedule is contingent on the County's ability to relocate all of the Yesler Building's current tenants.  As of October 2015, CCD (the building’s largest tenant with the most specialized operations) remains in the building.  In addition, none of the tenants slated for temporary relocation have moved out of the Yesler Building. These include:

- Employee Assistance Program (2 staff)

- Department of Community and Human Services Ombudsman (2 staff)

- Boundary Review Board (2 staff)

- Hearing Examiner (3 staff)

- Sheriff’s Office photography lab (2,459 rentable square feet)

ANALYSIS

The Community Corrections Division has some unique facility needs, which constrain the County’s ability to relocate these successful programs. One key issue has been the need to site the facility close to the downtown criminal justice campus or in an area that is accessable to those with limited transportation options.  As has been recognized by the County for many years, the current situation in Yesler provides a less-than-ideal occupancy for CCD, and has been considered a temporary placement at least since the full implementation of CCD programming in 2004.

Specifically, the Community Center for Alternative Programs (CCAP) requires classroom space and waiting areas which Yesler lacks in sufficient quantity. There is also no place at Yesler to store Community Work Program (work crew) equipment and vehicles. Together with administrative offices and other space supporting the full range of CCD programming, these needs total approximately 18,000 – 20,000 square feet, including 13 classrooms and 33 offices.

As noted in a 2014 review of the first ten years of CCD operations, because of facility constraints, the County’s courts are limited in using many programs.  Additionally, many of the County’s other courts of limited jurisdiction (e.g. city municipal courts) do not have access to the alternatives to secure detention and other treatment programs of the division. CCD currently serves approximately 125 people in CCAP Enhanced (Day Reporting) who must attend classes daily in the CCD facility, and 25 people each weekday in the Community Work Program. Additional programs (including work release) raise the daily total of CCD participants to nearly 600.

The County's most recent space planning policies adopted in 2014 in the Real Property Asset Management Plan (RAMP) state that "over the long-term, County ownership of its office space will be preferred to leasing."  Moving CCD to a leased location would run counter to this principle. A leased location for CCD outside of downtown would also not align with  the long-term plan to pursue the creation of a central downtown campus for the County’s criminal justice and related functions (though it would enable DPD to consolidate in Yesler, which aligns with the campus vision).  However, seeking an appropriate building for purchase to house CCD within the downtown campus area would likely further delay the Yesler redevelopment project and increase costs.

Another critical path issue for the Yesler building redevelopment is the anticipated timing of the Yesler Bridge rehabilitation by the City of Seattle. The current published project schedule contemplates construction beginning in the Spring of 2016. Per FMD, the bridge construction could impact both building construction and especially IT systems (wiring) in the Yesler building redevelopment plans. FMD staff expect to be able to accommodate potential issues related to the bridge project.

FMD believes that the other current tenants of the Yesler building can be accommodated within owned County buildings or existing leases, with the exception of the AFIS photography lab.  Although at this point in time, only the DCHS Ombudsman is schesduled to move and will relocate into space with the DCHS Vets program at 2106 2nd Ave. in mid November.

The Net Present Value (NPV) of the Yesler redevelopment project was estimated in the fall of 2014 as between $5 million and $9 million. FMD’s preliminary estimate at that time was that a one-year delay would reduce this NPV by $1.4 million. This estimate made numerous assumptions related to borrowing, inflation, extended mothball costs for currently empty space in Yesler, and cash flow losses.

Delaying the move of current Yesler tenants may also require the renewal of leases for DPD staff located in the Prefontaine and Watermark Buildings. These leases were negotiated assuming consolidation of DPD staff in the renovated Yesler Building beginning in 2017.

As is noted above, FMD has considered a number of options for the relocation of the CCD.  Options under consideration have included the Pearl Warren Building (606 12th Avenue South) or operating out of temporary structures on County property owned by the Wastewater Treatment Division of DNRP on Elliott Avenue. FMD does not recommend these latter two options due to distance, cost, necessary tenant improvements and environmental issues.  The Department also recently noted that the 420 Fourth Avenue Building is not a candidate for CCD relocation due to the relatively small size of the building (10,000 square feet).

Today’s presentation will highlight a number of other properties that have been considered or are currently under consideration for the CCD relation.  All of these properties are County owned facilities and include the Administration Building, Yessler Building, King Street Center, Blackriver Building in Renton and the West Wing of the King County Jail.

ATTENDEES:

- Ellisa Benson, Deputy Director, Facilities Management Divison, Department of Executive Services.

- Saudia Abdullah, Director, CCD, Adult & Juvinile Detention

- Lorinda Youngcourt, Director, Department of Public Defense

ATTACHMENTS:

- PowerPoint Presentation, “CCD Relocation/Move Briefing, Law, Justice and Emergency management, December 8, 2015.”

Ordinance 17903. The term of the DPD lease in the Prefontaine Building expires December 31, 2016.

Ordinance 17904.  The term of the DPD lease in the Watermark Building expires June 30, 2017.

2014-B0040,  Briefing on the Status of Community Corrections Programs and Initiatives after Ten Years of Operations.

Ordinance 17839.

http://www.seattle.gov/transportation/YeslerBridge.htm