STAFF REPORT

| Agenda Item: | 7 | Name: | Miranda Leskinen |
| --- | --- | --- | --- |
| Proposed No.: | 2018-B0022 | Date: | February 14, 2018 |

SUBJECT

A briefing on the status of the Puget Sound Emergency Radio Network (PSERN) implementation.

SUMMARY

The Puget Sound Emergency Radio Network (PSERN) project will replace and upgrade the County's current emergency radio network. King County is responsible for leading and implementing the PSERN project through completion, which is currently expected in May 2021.

The PSERN project is a complex project with multiple tasks over the course of the implementation period including radio site design, acquisition and construction, as well as the acquisition of radios, consoles, and data systems.

Today’s briefing provides Regional Policy Committee with a first quarter 2018 update on the status of the implementation of PSERN including recent project schedule and budget re-baselining. Reflective of project re-baselining, both PSERN project schedule and budget have changed since the Regional Policy Committee was last updated on the PSERN project in October 2017.

BACKGROUND

On April 28, 2015, King County voters approved a nine-year, $273 million property tax levy to fund PSERN, the replacement of the King County emergency radio communications system.

In late 2018, the vendor for the current countywide emergency radio network, King County Emergency Radio Communications System (KCERCS), will no longer provide system support.  PSERN will replace and upgrade King County's over 20-years old emergency radio communications system, which is used to dispatch responders to incidents and allow responders to communicate with each other at those incidents. Countywide, the current system consists of more than two dozen transmitter sites and multiple interconnecting microwave and fiber systems, and it supports over 100 agencies and approximately 17,000 radios. The current system is owned by King County, the City of Seattle, Valley Communications Center (ValleyCom), and the Eastside Public Safety Communications Agency (EPSCA).

Once completed, PSERN will replace the current countywide emergency radio network.  PSERN will improve and upgrade the countywide emergency radio network by providing increased system reliability, increasing coverage capacity from 94 percent coverage to 97 percent coverage, providing better security on the network, and nearly doubling the number of radio transmitter sites.

Implementation Interlocal Agreement. Under the terms of the PSERN Implementation Interlocal Agreement, King County will be responsible for leading and implementing the PSERN project on behalf of the four owners of the current emergency radio network through completion of the project. Oversight during that implementation period, currently expected to take approximately 70 months per the re-baselined project schedule (discussed later in this staff report), will be conducted by a Joint Board, composed of one non-voting chair (the Executive or the Executive's designee) and four voting representatives, one representing each of the current system's owners. The four voting members of the Joint Board may appoint two additional non-voting participants: a chief of a police agency and a chief of a fire agency.

The PSERN project team includes a project director, government liaison, information technology project managers, information technology project administrator, budget analyst, contract manager, administrative specialists, construction managers, communications manager, government relations officer, technical support technicians and inspectors. King County Information Technology's Business & Finance Section and the Office of Performance, Strategy and Budget will provide financial support. Under the terms of the approximately $114 million contract between Motorola and the county, Motorola will provide design, development, implementation, testing and ongoing support, maintenance and upgrade services for the PSERN project.

Operations Memorandum of Agreement. Under the terms of the Memorandum of Agreement Regarding Future Operation of the Puget Sound Emergency Radio Network, ownership and operation and maintenance of PSERN after completion would be vested in a new, nonprofit organization governed by a Board of Directors.

Council Committee Oversight. Motion 14437, enacted in October 2015, requires the Executive to brief the Law, Justice and Emergency Management Committee (or its successor) on a quarterly basis on the status of the PSERN project in relation to the project’s identified milestones, as indicated in the report attached to Motion 14437 (2015-RPT0134). The Law and Justice Committee received a combined Q4 2017/Q1 2018 briefing on January 9, 2018. The Regional Policy Committee has also requested quarterly briefings on project implementation.

Project Re-Baselining. As indicated by PSERN project staff, schedule and budget baselines for the PSERN project were set in April and September of 2016, respectively. As further indicated, there have since been several key events affecting the project that have made it necessary for project staff to reevaluate both the original schedule and budget baselines. These events include the system vendor needing more time than originally planned for testing the system once it is built, the addition of new radio tower sites to the site design, some radio tower sites becoming unviable, longer than anticipated lease negotiation processes, and necessary substantive technical changes to the system design.

PSERN project staff anticipated that re-baselining would likely need to occur when final system design was complete. As indicated by PSERN project staff, the project reached agreement with the system vendor on the final system design on September 15, 2017. As further indicated, re-baselining analysis would result in an updated project schedule and budget to be presented to key stakeholders, including committees of the King County Council and the PSERN Joint Board.

Project Schedule. Upon completion of re-baselining, PSERN project staff have indicated the project milestone dates would need to change in order to reflect the re-baselined schedule. Additionally, due to schedule and system design changes, the project is reevaluating each milestone identified in 2015 and is considering renaming or updating them so that they provide a more defined measure of the project’s progress. PSERN project staff have indicated any proposed changes would be presented to the project’s oversight bodies for review and feedback.

The updated project schedule reflective of re-baselining is shown in Figure 1.

Figure 1. PSERN Updated Expected Completion Dates, as of November 2017 Reflective of Project Schedule Re-Baselining

Full System Acceptance. As indicated in Figure 1, Full System Acceptance (Milestone #12 identified in 2015-RPT0134) is expected to be completed in May 2021, five months later than the completion date previously reported to this committee in an October 2017 briefing paper (included as Attachment 1 to this staff report), and eight months later than the original projected milestone completion date identified in 2015-RPT0134.

Project Closeout. As indicated in Figure 1, Project Closeout (Milestone # 13 identified in 2015-RPT0134) is expected to be completed in December 2022, twelve months later than the completion date previously reported to this committee in an October 2017 briefing paper (included as Attachment 1 to this staff report), and fifteen months later than the original projected milestone completion date identified in 2015-RPT0134.

Project Budget. As indicated by PSERN project staff, schedule delays combined with site and system design changes, increased site development costs, additional staffing and increased staff duration and other factors have contributed to increased capital budget and total project budget costs in the re-baselined project budget. Figure 2 shows an updated project budget that is reflective of re-baselining.

Figure 2. Updated PSERN Project Budget, as of November 2017 and Reflective of Project Budget Re-Baselining

As indicated in Figure 2, the re-baselined project budget indicates an increase of approximately $32.7 million in capital budget costs when compared to the original project capital budget, and an increase in the overall project of approximately $8.6 million when compared to the original total project budget. As indicated by PSERN project staff, the capital budget increase is offset by expenditure reductions in debt financing, increases in projected levy revenues and other cost reductions (e.g. decreased non-capital budget costs). As shown in Figure 2, the re-baselined project budget is currently estimated to have a balance of approximately $14.6 million (difference between project expenditures and projected levy revenue, based on August 2017 revenue projections).

In-Building Coverage. The PSERN project’s broad definition of “in-building coverage” refers to the ability of first responders to communicate with each other inside and outside of a building. In-building coverage is not within the current PSERN project scope. As indicated by PSERN project staff, project partner representatives have requested to revisit the topic of in-building coverage requirements and criteria under PSERN. As further indicated, project staff are currently working on two major activities related to in-building coverage, including an in-building task force and building owner outreach.

Building Owner Outreach. PSERN project staff indicate the project has a plan for outreach to building owners throughout King County, which has begun and will continue into 2018, to ensure that they are aware of PSERN and how their in-building systems can connect to PSERN. PSERN project staff further indicate there are several steps that need to occur before the project meets with building owners about PSERN and in-building coverage, including outreach to city officials, fire marshals and building officials who oversee the relevant fire codes as well as building owner and management associations. Additionally, project staff indicate they have received feedback from stakeholder advisory groups that is being incorporated into the building owner outreach plan.

In-Building Task Force. An in-building task force has been formed, as indicated by PSERN project staff, comprised of first responders who will be using the system and the technical staff who run the current emergency radio communications system in King County. This group has also proposed utilizing the assistance of a technical consultant with expertise on in-building coverage, which the Joint Board approved at its October 26, 2017 meeting. This task force will submit recommendations to the PSERN Joint Board. PSERN project staff indicate the task force met with the consultant for the first time in early November and is currently anticipated to submit its recommendations to the Joint Board in Spring 2018. PSERN project staff will keep this committee posted on the task force’s schedule, including when recommendations have been presented to the PSERN Joint Board.

2018 Supplemental Budget Appropriation Request. The PSERN project is subject to Mandatory Phased Appropriation (MPA), meaning appropriation by project phases, as described in King County Code. A supplemental budget appropriation request for funding for the final two phases of the project (Implementation and Close-out) is anticipated for the first quarter of 2018, as indicated by PSERN project staff. Specifically, the request will reflect all costs associated with the completion of the project including labor costs (salaries, wages, and benefits), overhead costs, site development and ongoing vendor payments, including architecture and engineering for radio sites, specialized legal services, quality assurance consulting and construction contractors.

King County Auditor Capital Projects Oversight. In November 2015, the Capital Projects Oversight Program of the King County’s Auditor’s Office released a report on PSERN. The November 2015 report focused on project schedule and cost risks, and it included recommendations for the PSERN project team. The Auditor’s Office presented this report to the Government Accountability and Oversight Committee on November 10, 2015.

The next report on PSERN was released by the Capital Projects Oversight Program of the King County’s Auditor’s Office on February 2, 2017. The February 2017 report focuses on PSERN project scope, schedule, budget and risks. The Auditor’s Office presented the February 2017 report to the Law and Justice Committee on February 28, 2017.

The February 2017 report includes four recommendations for the PSERN project team:

Recommendation 1 – Regarding Building Coverage. The Puget Sound Emergency Radio Network (PSERN) project team should expand its outreach and communications plans to identify detailed, proactive engagement with building owners to allow them time to evaluate their systems and prepare for any needed changes.

Recommendation 2 – Regarding Site Development. The PSERN project team should evaluate and compare the impacts on contract requirements, schedule, and costs for 1) the current plan of simultaneously constructing Primary Bounded Area sites, versus 2) extending the Primary Bounded Area site development schedule to allow construction of sites in sequence.

Recommendation 3 – Regarding Project Reporting. The PSERN project team should complete updated site development cost estimates based on current information, should update the overall projects costs based on this information, and enter the project baseline costs into the County’s Project Information Center.

Recommendation 4 – Regarding Project Reporting. The PSERN project team should refine the schedule to reflect realistic site development milestone achievement dates and should enter the project baseline schedule into the County’s Project Information Center.

Additionally, a briefing entailing an Auditor’s Capital Project Oversight Program status report on the PSERN project was presented at the January 9, 2018 Law and Justice Committee (2017-B0225) and included recommendations relating to close monitoring of the re-baselined project schedule for deviations or delays.

ATTACHMENTS

- Briefing paper on the status of PSERN implementation, dated October 12, 2017

INVITED

- David Mendel, Director, Emergency Radio Communications Division, King County Information Technology (KCIT)

- Kimberly Nuber, Government Relations Officer, PSERN Project, Emergency Radio Communications Division, KCIT

A briefing paper, included as Attachment 1 to this staff report, on the status of the PSERN project was provided to the committee via email on October 12, 2017.

According to PSERN project staff, King County owns just under 50 percent of KCERCS, the city of Seattle and Eastside Public Safety Communications Agency owns approximately 25 percent each and ValleyCom owns approximately 10 percent.

Ordinance 18075.

As of September 2017, the members of the Joint Board are as follows:  Fred Jarrett, non-voting Chair; Sharon Potts, King County voting member; Chief Harold Scoggins, Seattle voting member; Kurt Triplett, EPSCA voting member; Lora Ueland, ValleyCom voting member; Chris Elwell, non-voting fire agency member; and Chief John Vinson, non-voting police agency member.

As of February, 13, 2017, the PSERN project team had sixteen positions in the project staffing plan and project budget. As indicated by PSERN project staff, upon periodic review of staffing positions, the project determined a need for six additional staff positions to manage project work. Funding, in the amount of $2,424,929, for these additional project staff positions (to include a budget analyst, contract manager, governmental liaison, civil site development supervisor, IT Project Manager #1 and IT Project Manager #2) was approved by the Joint Board at its February 23, 2017 meeting.

PSERN project staff indicate that the contract, with respect to duration, includes project implementation through 20 years after project completion. Additionally, PSERN project staff indicate that, due to contract change orders, the current value of the contract is approximately $114 million (increase from $112 million). PSERN project staff further indicate that execution of upcoming contract change orders, subject to Joint Board approval, is projected to increase the contract up to approximately $118 million, which is reflected in the re-baselined project budget.

In addition to the primary contract with Motorola, the Executive has hired consultants to develop the site design and to provide construction management oversight.

Ordinance 18074.

As indicated by PSERN project staff, the project provides a variety of reports and updates to several oversight and advisory groups on at least a monthly basis. Aside from Council committees, Executive Office leadership and KCIT leadership, the project also reports to the King County Auditor’s office, quality assurance consultants, King County Project Review board, PSERN Joint Board, PSERN Operations Board and PSERN Technical Committee.

In 2016, the Law, Justice and Emergency Management Committee was changed to the Law and Justice Committee.

The Joint Board took action on approval of final system design at its October 26, 2017 meeting.

Updated project schedule and budget information reflective of re-baselining was presented to the Joint Board at its October 26th and November 16th meetings, and the Joint Board took action on approval of the re-baselined schedule and budget at its January 4, 2018 meeting.

K.C.C. Chapter 4A.130. Per County Code, for this type of supplemental appropriation request, the implementing agency is required to complete a cost estimate validation process to provide an independent evaluation of the project’s cost estimates. As indicated during the January 9, 2018 Law and Justice Committee quarterly PSERN briefing (2017-B0226), at the request of the King County Project Review Board, CASE Associates Inc. (CAI) has provided an independent review of the revised PSERN schedule and associated budget. As further indicated, CAI currently conducts quality assurance assessment on two King County projects, including PSERN.

An electronic version of the November 2015 report is available at http://www.kingcounty.gov/~/media/depts/auditor/new-web-docs/2015/2015-cpo-psern/cpo-psern-final.ashx?la=en.

2015-B0210: A briefing on the Capital Projects Oversight November 2015 Report regarding PSERN.

An electronic version of the February 2017 report is available at http://www.kingcounty.gov/~/media/depts/auditor/new-web-docs/2015/2015-cpo-psern/cpo-psern-2017.ashx?la=en.

Effective February 11, 2017.