BRIEFING PAPER

| Agenda Item: |  | Name: | Miranda Leskinen |
| --- | --- | --- | --- |
| Proposed No.: |  | Date: | October 12, 2017 |

SUBJECT

A briefing paper on the status of the Puget Sound Emergency Radio Network (PSERN) implementation.

SUMMARY

The Puget Sound Emergency Radio Network (PSERN) project will replace and upgrade the County's current emergency radio network. King County is responsible for leading and implementing the PSERN project through completion, which is expected in late 2020.

The PSERN project is a complex project with multiple tasks over the course of the implementation period including radio site design, acquisition and construction, as well as the acquisition of radios, consoles, and data systems.

This briefing paper provides an update on the status of PSERN project implementation since the last Regional Policy Committee briefing on March 15, 2017.

BACKGROUND

On April 28, 2015, King County voters approved a nine-year, $273 million property tax levy to fund PSERN, the replacement of the King County emergency radio communications system.

In late 2018, the vendor for the current countywide emergency radio network, King County Emergency Radio Communications System (KCERCS), will no longer provide system support.  PSERN will replace and upgrade King County's approximately 20-year old emergency radio communications system, which is used to dispatch responders to incidents and allow responders to communicate with each other at those incidents. Countywide, the current system consists of more than two dozen transmitter sites and multiple interconnecting microwave and fiber systems, and it supports over 100 agencies and approximately 17,000 radio users, each with a portable radio handset and/or installed mobile radio in a vehicle. The current system is owned by King County, the City of Seattle, Valley Communications Center (ValleyCom), and the Eastside Public Safety Communications Agency (EPSCA).

Once completed, PSERN will replace the current countywide emergency radio network.  PSERN will improve and upgrade the countywide emergency radio network by providing increased system reliability, increasing coverage capacity from 94 percent coverage to 97 percent coverage, providing better security on the network, and nearly doubling the number of radio transmitter sites.

Implementation Interlocal Agreement. Under the terms of the PSERN Implementation Interlocal Agreement, King County will be responsible for leading and implementing the PSERN project on behalf of the four owners of the current emergency radio network through completion of the project. Oversight during that implementation period, which is expected to take approximately five years, will be conducted by a Joint Board, composed of one non-voting chair (the Executive or the Executive's designee) and four voting representatives, one representing each of the current system's owners. The four voting members of the Joint Board may appoint two additional non-voting participants: a chief of a police agency and a chief of a fire agency.

The PSERN project management team includes a project director, information technology project managers, project administrator, construction managers, communications manager, government relations officer, technical support technicians and inspectors. King County Information Technology's Business & Finance Section and the Office of Performance, Strategy and Budget will provide financial support. Under the terms of the $114 million contract between Motorola and the county, Motorola will provide design, development, implementation, testing and ongoing support, maintenance and upgrade services for the PSERN project.

Operations Memorandum of Agreement. Under the terms of the Memorandum of Agreement Regarding Future Operation of the Puget Sound Emergency Radio Network, ownership and operation and maintenance of PSERN after completion would be vested in a new, nonprofit organization governed by a Board of Directors.

Council Committee Oversight. Motion 14437, enacted in October 2015, requires the Executive to brief the Law, Justice and Emergency Management Committee (or its successor) on a quarterly basis on the status of the PSERN project in relation to the project’s identified milestones, as indicated in the attached report to Motion 14437 (2015-RPT0134). The Law and Justice Committee had its third quarter briefing on September 12, 2017. The Regional Policy Committee has also requested quarterly briefings on the project implementation.

Table 1 below shows the 13 major project milestones identified in the 2015 transmitted report (2015-RPT0134) that remain to be completed during the PSERN implementation process, along with the original expected date of completion and the revised expected dates of completion. The “site construction mid-point” and the “group 2 site leasing” milestones have been eliminated since the Executive’s initial transmittal of the 2015 report. PSERN project staff indicate that the two milestones are no longer applicable to the PSERN project. Of note, project schedule and budget are currently in the process of re-baselining, as discussed later in this staff report. As indicated by PSERN project staff, it is possible the current identified project milestones described in Table 1 below may be updated upon completion of re-baselining.

Table 1: PSERN Implementation Milestones, as Identified in 2015

Original Expected Completion Dates and Revised Expected Completion Dates

| Milestone | Original Completion Date | Revised Completion Date (as of 11/15/16) | Revised Completion Date (as of 2/7/17) | Revised Completion Date (as of 6/13/17) | Revised Completion Date (as of 9/12/17) |
| --- | --- | --- | --- | --- | --- |
| Site Leasing and Final Site Design | March 2016 | May 2017* | January 2018* | No change | May 2018* |
| Construction Permitting | August 2016 | April 2017* | No change | October 2017* | November 2017* |
| Site Construction Mid-Point | September 2016 | Milestone eliminated | Milestone eliminated | Milestone eliminated | Milestone eliminated |
| Group 2 Site Leasing | August 2017 | Milestone eliminated | Milestone eliminated | Milestone eliminated | Milestone eliminated |
| Factory Acceptance Testing | September 2017 | August 2017 | No change | No change | September 2017 |
| Site Construction Complete (all sites) | October 2017 | May 2019 (including U.S. Forest Service Sites) | No change | No change | July 2019 |
| Backhaul System Implementation | November 2017 | November 2018* | No change | No change | April 2019* |
| Land Mobile Radio System Implementation | September 2018 | November 2018* | No change | No change | April 2019* |
| System Optimization and Testing | May 2019 | No change | No change | No change | September 2019 |
| PSERN Non-profit Operator Formation | September 2019 | No change | No change | No change | No change |
| Transition Users to PSERN System | March 2020 | No change | No change | No change | May 2020 |
| Full System Acceptance | September 2020 | No change | No change | No change | December 2020 |
| Project Closeout | September 2021 | No change | No change | No change | December 2021 |

*Expected completion date majority King County Metropolitan areas and Highway SR410

Project Re-Baselining. As indicated by PSERN project staff, schedule and budget baselines for the PSERN project were set in April and September of 2016, respectively. As further indicated, there have since been several key events affecting the project that have made it necessary for project staff to reevaluate both the original schedule and budget baselines. These events include the system vendor needing more time than originally planned for testing the system once it is built, the addition of new radio tower sites to the site design, some radio tower sites becoming unviable, longer than anticipated lease negotiation processes, and necessary substantive technical changes to the system design.

PSERN project staff anticipated that re-baselining would likely need to occur when final system design was complete. As indicated by PSERN project staff, the project reached agreement with the system vendor on the final system design on September 15, 2017. As further indicated, re-baselining analysis is underway and will result in an updated project schedule and budget that will be presented to key stakeholders, including committees of the King County Council and the PSERN Joint Board.

Upon completion of re-baselining, PSERN project staff indicate the project milestone dates will need to change in order to reflect the re-baselined schedule. Additionally, due to schedule and system design changes, the project is reevaluating each  milestone identified in 2015 and is considering renaming or updating them so that they provide a more  defined measure of the project’s progress. PSERN project staff indicate any proposed changes would be presented to the project’s oversight bodies for review and feedback.

In-Building Coverage. The PSERN project’s broad definition of “in-building coverage” refers to the ability of first responders to communicate with each other inside and outside of a building. In-building coverage is not within the current PSERN project scope. As indicated by PSERN project staff, project partner representatives have requested to revisit the topic of in-building coverage requirements and criteria under PSERN. As further indicated, project staff are currently working on two major activities related to in-building coverage, including building owner outreach and development of an in-building task force.

Building Owner Outreach. PSERN project staff indicate the project has a plan in place for outreach to building owners throughout King County, which has begun and will continue into 2018, to ensure that they are aware of PSERN and how their in-building systems can connect to PSERN. PSERN project staff further indicate there are several steps that need to occur before the project meets with building owners about PSERN and in-building coverage, including outreach to fire marshals and building officials who oversee the relevant fire codes as well as building owner and management associations. Additionally, project staff are in ongoing discussions with project stakeholder advisory groups and have received feedback that will be incorporated into the building owner outreach plan.

In-Building Task Force. An in-building task force has been formed, as indicated by PSERN project staff, comprised of first responders who will be using the system and the technical staff who run the current emergency radio communications system in King County. This group will submit recommendations to the PSERN Joint Board. PSERN project staff indicate the task force is aiming to complete its work in November of 2017, and that PSERN project staff will keep the committee (RPC) posted on the task force’s schedule, including when recommendations have been presented to the PSERN Joint Board.

Summary of Project Updates and Upcoming Activities. Major bodies of work for the project for the remainder of 2017, as summarized by PSERN project staff, include:

- Finalization of re-baselining activities

- Execution of a large contract change order with Motorola

- Radio site lease negotiations

- Construction of radio sites

- Begin construction of a fiber optic cable network

- Factory Acceptance of microwave radio equipment

- Transition from the final design stage to the equipment implementation stage

- Begin installation of equipment at radio sites

- Address stakeholder concerns related to in-building coverage

2018 Supplemental Budget Appropriation Request. The PSERN project is subject to Mandatory Phased Appropriation (MPA), meaning appropriation by project phases, as described in King County Code. A supplemental budget appropriation request for funding for the final two phases of the project (Implementation and Close-out) is anticipated for the first quarter of 2018, as indicated by PSERN project staff. Specifically, the request will reflect all costs associated with the completion of the project including labor costs (salaries, wages, and benefits), overhead costs, site development and ongoing vendor payments, including architecture and engineering for radio sites, specialized legal services, quality assurance consulting and construction contractors.

King County Auditor Capital Projects Oversight. In November 2015, the Capital Projects Oversight Program of the King County’s Auditor’s Office released a report on PSERN. The November 2015 report focused on project schedule and cost risks, and it included recommendations for the PSERN project team. The Auditor’s Office presented this report to the Government Accountability and Oversight Committee on November 10, 2015.

The next report on PSERN was released by the Capital Projects Oversight Program of the King County’s Auditor’s Office on February 2, 2017. The February 2017 report focuses on PSERN project scope, schedule, budget and risks. The Auditor’s Office presented the February 2017 report to the Law and Justice Committee on February 28, 2017.

The February 2017 report includes four recommendations for the PSERN project team:

Recommendation 1 – Regarding Building Coverage. The Puget Sound Emergency Radio Network (PSERN) project team should expand its outreach and communications plans to identify detailed, proactive engagement with building owners to allow them time to evaluate their systems and prepare for any needed changes.

Recommendation 2 – Regarding Site Development. The PSERN project team should evaluate and compare the impacts on contract requirements, schedule, and costs for 1) the current plan of simultaneously constructing Primary Bounded Area sites, versus 2) extending the Primary Bounded Area site development schedule to allow construction of sites in sequence.

Recommendation 3 – Regarding Project Reporting. The PSERN project team should complete updated site development cost estimates based on current information, should update the overall projects costs based on this information, and enter the project baseline costs into the County’s Project Information Center.

Recommendation 4 – Regarding Project Reporting. The PSERN project team should refine the schedule to reflect realistic site development milestone achievement dates and should enter the project baseline schedule into the County’s Project Information Center.

According to PSERN project staff, King County owns just under 50 percent of KCERCS, the city of Seattle and Eastside Public Safety Communications Agency owns approximately 25 percent each and ValleyCom owns approximately 10 percent.

Ordinance 18075.

As of September 2017, the members of the Joint Board are as follows:  Fred Jarrett, non-voting Chair; Sharon Potts, King County voting member; Chief Harold Scoggins, Seattle voting member; Kurt Triplett, EPSCA voting member; Lora Ueland, ValleyCom voting member; Chris Elwell, non-voting fire agency member; and Chief John Vinson, non-voting police agency member.

As of February, 13, 2017, the PSERN project team had sixteen positions in the project staffing plan and project budget. As indicated by PSERN project staff, upon periodic review of staffing positions, the project determined a need for six additional staff positions to manage project work. Funding, in the amount of $2,424,929, for these additional project staff positions (to include a budget analyst, contract manager, governmental liaison, civil site development supervisor, IT Project Manager #1 and IT Project Manager #2) was approved by the Joint Board at its February 23, 2017 meeting.

PSERN project staff indicate that the contract, with respect to duration, includes project implementation through 20 years after project completion. Additionally, PSERN project staff indicate that, due to contract change orders, the current value of the contract is $114 million (increase from $112 million).

In addition to the primary contract with Motorola, the Executive has hired consultants to develop the site design and to provide construction management oversight.

Ordinance 18074.

As indicated by PSERN project staff, the project provides a variety of reports and updates to several oversight and advisory groups on at least a monthly basis. Aside from Council committees, Executive Office leadership and KCIT leadership, the project also reports to the King County Auditor’s office, quality assurance consultants, King County Project Review board, PSERN Joint Board, PSERN Operations Board and PSERN Technical Committee.

In 2016, the Law, Justice and Emergency Management Committee was changed to the Law and Justice Committee.

As described in the report attached to Motion 14437 (2015-RPT0134), one year before the anticipated date of full system acceptance, the joint board will establish the PSERN non-profit as agreed to by interlocal agreement (ILA). Establishing the PSERN non-profit will require the filing of incorporation documents with the Washington Secretary of State, the designation of board members by the parties to the ILA, and agreement on and filing of other documents such as by-laws. Once it is established and staffed, the non-profit will take over PSERN including operations, ownership, and governance functions from the project, County, and joint board.  The board must hire an executive director to run the PSERN organization’s day-to-day business, including hiring staff to operate, maintain, monitor, repair, update, and upgrade the PSERN system. The board will also convene an operations board.  As further described in the report, the goal is to have the non-profit ready to assume these functions upon full system acceptance.

K.C.C. Chapter 4A.130

An electronic version of the November 2015 report is available at http://www.kingcounty.gov/~/media/depts/auditor/new-web-docs/2015/2015-cpo-psern/cpo-psern-final.ashx?la=en.

2015-B0210: A briefing on the Capital Projects Oversight November 2015 Report regarding PSERN.

An electronic version of the February 2017 report is available at http://www.kingcounty.gov/~/media/depts/auditor/new-web-docs/2015/2015-cpo-psern/cpo-psern-2017.ashx?la=en.