Proposed Ordinance 2018-0153 and Proposed Motion 2018-0154

Current and proposed comprehensive and subarea planning structures

| CURRENT | PROPOSED |
| --- | --- |
| I. Comprehensive planning cycle |
| Major King County Comprehensive Plan (KCCP) Updates |
| Four-year update cycle | Eight-year update cycle |
| Major KCCP update scope: UGA amendments Substantive policy changes Anything allowed during annual updates | Same as current |
| Midpoint KCCP Updates |
| Allows for a “midpoint” KCCP update if there is a demonstrated need; requires adoption of a motion initiating the update | Same as current |
| Midpoint is in Year Two of four-year cycle | Midpoint is in Year Four of 8-year cycle |
| Midpoint KCCP update scope: Substantive policy changes Anything allowed during annual updates | Same as current |
| Annual KCCP Updates |
| Allows for annual KCCP updates | Same as current |
| Annual update scope: Technical and non-substantive changes Adoption of subarea plans Approval of Four-to-One proposals Approval of other zoning/land use designation changes that do not require substantive policy changes | Same as current, plus adoption of substantive changes to the KCCP update schedule in response to ordinances |
| II. Comprehensive planning timelines |
| Annual KCCP Docket: June 30 docket request submittal deadline December 1 deadline for Executive response to docket proponents December 1 transmittal of Docket Report to Council | Annual KCCP Docket: December 31 docket request submittal deadline April 30 deadline for Executive response to docket proponents April 30 transmittal of Docket Report to Council |
| December 31 transmittal of KCCP Performance Measures Report the year prior to Scoping Motion for major KCCP updates | March 1 transmittal of KCCP Performance Measures Report during year of Scoping Motion for major KCCP updates |
| Scoping Motion for major KCCP updates: March 1 transmittal the year prior to transmittal of major KCCP update April 30 deadline for adoption the year prior to transmittal of major KCCP update (two months) | Scoping Motion for major KCCP updates: June 30 transmittal the year prior to transmittal of major KCCP update August 31 deadline for adoption the year prior to transmittal of major KCCP update (two months, but overlaps with Council’s summer recess) |
| March 1 plan transmittal | June 30 plan transmittal |
| Plan review and adoption by Council: 9 months No explicit deadline for adoption for major, midpoint, or annual KCCP updates, but updates are typically adopted before the Councils December recess later that year Cannot adopt major, midpoint, or annual updates and/or subarea plans more than once per calendar year | Plan review and adoption by Council: 12 months Adoption of major KCCP updates no later than June 30 the following year No explicit deadline for adoption of midpoint or annual KCCP updates plans Cannot adopt major, midpoint, or annual updates and/or subarea plans more than once per calendar year |
| Plan review and adoption by Council overlaps with Council review and adoption of the Biennial Budget | Same as current |
| 2020 adoption of next major KCCP update | 2023 adoption of next major KCCP update |
| Does not align with GMA schedule | Aligns with GMA schedule |
| III. Subarea planning cycle |
| 12 months for plan development and community outreach by Executive March 1 to March 1 | 12 months for plan development and community outreach by Executive June 30 to June 30 |
| 9 months for plan review/adoption by Council March 1 to December (no deadline for adoption, but cannot adopt subarea plans and/or KCCP updates more than once per year) | 12 months for plan review/adoption by Council June 30 to June 30 (no deadline for adoption, but cannot adopt subarea plans and/or KCCP updates more than once per year) |
| Subarea plans are developed/adopted while major KCCP updates are developed by the Executive and reviewed/adopted by the Council | Subarea plans are not developed/adopted while major KCCP updates are developed/adopted (extends the planning cycle) |

| CURRENT | PROPOSED |
| --- | --- |
| IV. Subarea planning geographies |
| All six “rural” Community Service Areas (CSAs) will receive planning each subarea planning cycle | Same as current |
| Three out of the five major Potential Annexation Areas (PAAs) in the West King County CSA will receive planning each subarea planning cycle | All five major PAAs in the West King County CSA will receive planning each subarea planning cycle |
| Planning for Skyway-West Hill PAA and North Highline PAA occurs at the same time (transmittal of both subarea plans in 2018 and adoption of both subarea plans in 2018) | Planning for Skyway-West Hill PAA and North Highline PAA occurs at different times: Skyway-West Hill PAA subarea plan transmittal in 2019 and adoption in 2020; and North Highline PAA subarea plan transmittal in 2020 and adoption in 2021 |
| Order of subarea plan development and adoption: Vashon-Maury Island CSA Skyway-West Hill PAA North Highline PAA Snoqualmie Valley/NE King County CSA Greater Maple Valley/Cedar River CSA Fairwood PAA Bear Creek/Sammamish CSA Southeast King County CSA Four Creeks/Tiger Mountain CSA | Same as current, plus East Renton PAA Federal Way PAA |

| CURRENT | PROPOSED |
| --- | --- |
| V. Subarea planning timelines |
| Geography Devel-opment Adopt-ion Skyway-West Hill PAA 2017-18 2018 North Highline PAA 2017-18 2018 Snoqualmie Valley/NE King County CSA 2018-19 2019 Greater Maple Valley/Cedar River CSA 2019-20 2020 Fairwood PAA 2020-21 2021 Bear Creek/Sammamish CSA 2021-22 2022 Southeast King County CSA 2022-23 2023 Four Creeks/Tiger Mountain CSA 2023-24 2024 | Geography Devel-opment Adopt-ion Skyway-West Hill PAA 2018-19 2019-20 North Highline PAA 2019-20 2020-21 Snoqualmie Valley/NE King County CSA 2020-21 2021-22 Greater Maple Valley/Cedar River CSA 2022-23 2023-24 Fairwood PAA 2023-24 2024-25 Bear Creek/Sammamish CSA 2024-25 2025-26 Southeast King County CSA 2025-26 2026-27 Four Creeks/Tiger Mountain CSA 2026-27 2027-28 East Renton PAA 2027-28 2028-29 Federal Way PAA 2028-29 2029-30 |
| VI. Scope of subarea plans |
| Broad Is a more robust plan specific to the subarea, which creates new policy direction Addresses local issues across all comprehensive planning policy areas Potential for many new, subarea-specific policies Implementation matrix primarily driven by policies in subarea plan | Limited Primarily an implementation plan of existing KCCP policy direction Local land use focus Limited new, subarea-specific policies Implementation matrix reflects prioritized community goals within the context of the KCCP and King County Budget |

| CURRENT | PROPOSED |
| --- | --- |
| VII. Executive staffing |
| Code requires the Office of Performance, Strategy and Budget (PSB) to develop comprehensive plans in coordination with Department of Permitting and Environmental Review (DPER) | Same as current |
| Code and Motion 14341 requires DPER to develop subarea plans in coordination and collaboration with PSB | Same as current |
| In practice, comprehensive planning by PSB and subarea planning by DPER primarily siloed in separate departments | Creation of an integrated work program Developing standard work processes and templates Weekly joint team meetings at DPER Weekly meetings between DPER Director and Regional Planning Director Using digital platforms for communication, scheduling, planning, and document sharing Establishing work space at PSB for DPER staff when they are downtown |
| One subarea planner in DPER | Three subarea planners in DPER |
| One comprehensive planning manager in PSB | Same as current |
| Use of interdepartmental staff team to support development of comprehensive and subarea plans | Same as current, plus documenting departmental leadership support for proposed policies and actions within the purview of their respective departments |
| VIII. Workplan impacts |
| 2016 KCCP Workplan |
| Action 1: Initiation of the CSA Subarea Planning program Transmit subarea plans by March 1 the year following the CSA’s planning year | Transmit subarea plans at a time consistent with the King County Code |

| CURRENT | PROPOSED |
| --- | --- |
| Action 2: Develop a Performance Measures Program for the Comprehensive Plan Transmit initial Performance Measures Report by December 1, 2018 so as to inform 2019 Scope of Work for the 2020 major KCCP update | Transmit initial Performance Measures Report by March 1, 2021 so as to inform 2021 Scope of Work for the 2023 major KCCP update |
| Action 3: Implement a Transfer of Development Rights (TDR) Unincorporated Urban Receiving Area Amenity Funding Pilot Project Transmit report on results of the pilot project by June 1, 2018 so as to inform the 2019-2020 Biennial Budget Transmit any recommended KCCP and/or Code changes as part of 2020 major KCCP update | Transmit report on results of the pilot project by June 1, 2018 so as to inform the 2019-2020 Biennial Budget Transmit any recommended KCCP and/or Code changes as part of 2023 major KCCP update The Executive will work with the Council to determine whether any KCCP amendments are appropriate for inclusion in an annual KCCP update prior to the 2023 major KCCP update |
| Action 4: TDR Program Review Transmit annual TDR activity report by December 1 Transmit study results and KCCP and/or Code changes by December 1, 2018 | Transmit annual TDR activity report by December 1 Transmit study results and KCCP and/or Code changes by December 1, 2018 The Executive will work with the Council to determine whether any KCCP amendments are appropriate for inclusion in an annual KCCP update prior to the 2023 major KCCP update |
| Action 5: Review 2016 King County Comprehensive Plan Implementation Needs Transmit implementation report by July 31, 2017 Transmit Code changes by December 31, 2019 | Same as current |

| CURRENT | PROPOSED |
| --- | --- |
| Action 6: Alternative Housing Demonstration Project Transmit demonstration project ordinance by December 31, 2018 Transmit report and KCCP and/or Code changes by December 31, 2020 | Transmit demonstration project ordinance by December 31, 2018 Transmit report and KCCP and/or Code changes by December 31, 2020 The Executive will work with the Council to determine whether any KCCP amendments are appropriate for inclusion in an annual KCCP update prior to the 2023 major KCCP update |
| Action 7: Agricultural Related Uses Zoning Code Updates Transmit report and Code changes by September 30, 2017 | Same as current (completed) |
| Action 8: Cottage Housing Regulations Review Transmit report and KCCP and/or Code changes by December 31, 2018 | Transmit report and KCCP and/or Code changes by December 31, 2018 The Executive will work with the Council to determine whether any KCCP amendments are appropriate for inclusion in an annual KCCP update prior to the 2023 major KCCP update |
| Action 9: Carbon Neutral King County Plan Transmit progress report on plan development by December 31, 2017 Transmit plan and motion adopting the plan by February 28, 2019 | Same as current |
| Action 10: Green Building Handbook Review Transmit handbook and motion approving the handbook by March 1, 2017 | Same as current (completed) |
| Action 11: Bicycle Network Planning Report Transmit report and motion approving report by December 31, 2017 | Same as current (completed) |
| Action 12: Update Plat Ingress/Egress Requirements Transmit amendments to Code and Road Standards by December 31, 2018 | Same as current |

| CURRENT | PROPOSED |
| --- | --- |
| Action 13: Water Availability and Permitting Study Transmit initial report by December 1, 2017 Transmit final report and KCCP and/or Code amendments by July 1, 2018 | Transmit initial report by December 1, 2017 Transmit final report and KCCP and/or Code amendments by July 1, 2018 The Executive will work with the Council to determine whether any KCCP amendments are appropriate for inclusion in an annual KCCP update prior to the 2023 major KCCP update |
| 2016 KCCP Workplan Actions Related to the Growth Management Planning Council (GMPC) |
| Action 14: Develop a Countywide Plan to Move Remaining Unincorporated Urban PAAs Toward Annexation Complete GMPC review and recommendations by December 1, 2018 | Complete GMPC review and recommendations by December 1, 2018 With due consideration regarding the outcomes of the work of the GMPC, the Executive will work with the Council to determine whether any KCCP amendments are appropriate for inclusion in an annual KCCP update prior to the 2023 major KCCP update |
| Action 15: Review the Four-to-One Program Complete GMPC review and recommendations by December 1, 2018 | Complete GMPC review and recommendations by December 1, 2018 With due consideration regarding the outcomes of the work of the GMPC, the Executive will work with the Council to determine whether any KCCP amendments are appropriate for inclusion in an annual KCCP update prior to the 2023 major KCCP update |

| CURRENT | PROPOSED |
| --- | --- |
| Action 16: Buildable Lands Program Methodology Review Complete GMPC review and recommendations by December 1, 2018 | Complete GMPC review and recommendations by December 1, 2018 With due consideration regarding the outcomes of the work of the GMPC, the Executive will work with the Council to determine whether any KCCP amendments are appropriate for inclusion in an annual KCCP update prior to the 2023 major KCCP update |
| 2017 Vashon-Maury Island (VMI) CSA Subarea Plan Workplan |
| VMI Action 1: P-suffix Conditions Transmittal by December 31, 2018 | Transmittal by June 30, 2021 |

Defined in K.C.C. 20.18.030.C as a determination that is made that the purposes of the Comprehensive Plan are “not being achieved as evidenced by official population growth forecasts, benchmarks, trends and other relevant data…”.  The motion must also identify available resources necessary to accomplish the work

As required by RCW 36.70A.470 and K.C.C. 20.18.140, the docket is a formal means for interested parties to submit comments on or to propose consideration of changes to the KCCP and development regulations.

RCW 36.70A.130. Jurisdictions must review and update comprehensive plans by June 30, 2015 and every eight years thereafter.  The next GMA required update deadline is June 30, 2023.

Bear Creek/Sammamish, Snoqualmie Valley/Northeast King County, Four Creeks/Tiger Mountain, Greater Maple Valley/Cedar River, Southeast King County, Vashon-Maury Island

East Federal Way PAA, East Renton Plateau PAA, Fairwood PAA, North Highline PAA, and Skyway-West Hill PAA

Due to delays in the development and transmittal of the 2017 Vashon-Maury Island CSA Subarea Plan, as well as due to the adoption of a budget proviso that does not allow funds to be expended on subarea planning until Council approval of the restructure plan in PM 2018-0154, development of the Skyway West Hill PAA and North Highline PAA subarea plans has not yet begun.

Initial adoption of the Vashon-Maury Island CSA Subarea Plan occurred in 2017 via Ordinance 18623.

The Executive plans to transmit a proposal later in 2018 to establish a new Department of Local Services (DLS).  The proposed subarea planning restructure plan notes that it is anticipated that the Executive will include reorganizing DPER, along with its subarea planning functions and staff, within the new DLS.

Please note that the transmittal includes a “June 30, 2021” date in Attachment A to PM 2018-0154 and Attachment B to PO 2018-0153.  However, Executive staff have since noted that year 2021 is incorrect, and that “June 30, 2022” was the intended proposed date for this Workplan item.