STAFF REPORT

| Agenda Item: | 8 | Name: | Miranda Leskinen |
| --- | --- | --- | --- |
| Proposed No.: | 2018-B0093 | Date: | May 8, 2018 |

SUBJECT

A briefing on the status of the Puget Sound Emergency Radio Network (PSERN) implementation.

SUMMARY

The Puget Sound Emergency Radio Network (PSERN) project will replace and upgrade the County's current emergency radio network. King County is responsible for leading and implementing the PSERN project through completion, which is currently expected in May 2021.

The PSERN project is a complex project with multiple tasks over the course of the implementation period including radio site design, acquisition and construction, as well as the acquisition of radios, consoles, and data systems.

Today’s briefing provides the Law and Justice Committee with a second quarter 2018 update on the status of the implementation of PSERN. The current expected completion dates for project substantial completion (May 2021) and project closeout (December 2022) are the same as previously reported during the last quarterly briefing on January 9, 2018.

BACKGROUND

On April 28, 2015, King County voters approved a nine-year, $273 million property tax levy to fund PSERN, the replacement of the King County emergency radio communications system.

In late 2018, the vendor for the current countywide emergency radio network, King County Emergency Radio Communications System (KCERCS), will no longer provide system support.  PSERN will replace and upgrade King County's over 20-years old emergency radio communications system, which is used to dispatch responders to incidents and allow responders to communicate with each other at those incidents. Countywide, the current system consists of more than two dozen transmitter sites and multiple interconnecting microwave and fiber systems, and it supports over 100 agencies and approximately 17,000 radios. The current system is owned by King County, the City of Seattle, Valley Communications Center (ValleyCom), and the Eastside Public Safety Communications Agency (EPSCA).

Once completed, PSERN will replace the current countywide emergency radio network.  PSERN will improve and upgrade the countywide emergency radio network by providing increased system reliability, increasing coverage capacity from 94 percent coverage to 97 percent coverage, providing better security on the network, and nearly doubling the number of radio transmitter sites.

Implementation Interlocal Agreement. Under the terms of the PSERN Implementation Interlocal Agreement, King County is responsible for leading and implementing the PSERN project. Oversight during that implementation period is being conducted by a Joint Board, composed of one non-voting chair (the Executive or the Executive's designee) and four voting representatives, one representing each of the current system's owners. The four voting members of the Joint Board may appoint two additional non-voting participants: a chief of a police agency and a chief of a fire agency.

Under the terms of the contract between Motorola and the county, currently valued at approximately $117.4 million, Motorola will provide design, development, implementation, testing and ongoing support, maintenance and upgrade services for the PSERN project.

Operations Memorandum of Agreement. Under the terms of the Memorandum of Agreement Regarding Future Operation of the Puget Sound Emergency Radio Network, ownership and operation and maintenance of PSERN after completion would be vested in a new, nonprofit organization governed by a Board of Directors.

Council Committee Oversight. Motion 14437, enacted in October 2015, requires the Executive to brief the Law, Justice and Emergency Management Committee (or its successor) on a quarterly basis on the status of the PSERN project in relation to the project’s identified milestones, as indicated in the report attached to Motion 14437 (2015-RPT0134). The Law and Justice Committee received a combined 2017 Q4/2018 Q1 PSERN briefing on January 9, 2018. The Regional Policy Committee is scheduled to receive a Q2 2018 briefing on May 9, 2018.

Project Budget and Schedule. As indicated by PSERN project staff, there have been several key events affecting the project that made it necessary for project staff to reevaluate both the original schedule and budget baselines, such as the system vendor needing more time than originally planned for testing the system once it is built, the addition of new radio tower sites to the site design, some radio tower sites becoming unviable, longer than anticipated lease negotiation processes, and necessary substantive technical changes to the system design. These issues have resulted in the need for the project to redo their project budget and schedule. The PSERN Joint Board approved the new (re-baselined) PSERN project budget and schedule in January 2018. The Law and Justice Committee and Regional Policy Committee were each briefed on the new budget and schedule in early 2018. The new (re-baselined) project budget, as compared to the original budget, is shown in Table 1.

Project Schedule - Update. The current project schedule, as of May 2018, is shown in Table 2. Table 2 shows how the new schedule has impacted the major project milestones. As previously reported to this committee, upon completion of re-baselining, project staff indicated that the identified project milestones would be reevaluated and potentially updated to provide a more defined measure of the project’s progress. As identified in Table 2, the expected completion dates relating to project substantial completion and project closeout have not changed since the last quarterly PSERN briefing to the Law and Justice Committee in January 2018.

Table 2: PSERN Implementation Milestones, as of May 2018

Original Expected Completion Dates and Revised Expected Completion Dates

| PSERN PROJECT MILESTONES, As of May 2018 |  | Original Project Completion Date (As of December 2014 (40% design) | Revised Completion Date (As of September 2017, Reflective of Re Baselining) (99% design) | Revised Completion Date (As of May 2018) |
| --- | --- | --- | --- | --- |
| Project Planning |  | Aug/2012 | Aug/2012 | Aug/2012 |
| Preliminary System Design |  | Dec/2014 | Dec/2014 | Dec/2014 |
| Final System Design |  | Jul/2017 | Sep/2017 | Sep/2017 |
| Motorola Site Construction Includes 2015-RPT0134- Identified Milestone #6 (Site Construction Complete) |  | Oct/2017 | Oct/2018 | Dec/2018* |
| Radio System Core and Initial Dispatch Console Transition |  | n/a | Jan/2019 | Nov/2018*** |
| PSERN (King County) Site Construction Includes 2015-RPT0134- Identified Milestones #1(Site leasing & final site design); #2 (Construction Permitting); and #6 (Site Construction Complete) |  | Oct/2017 | Aug/2019 | Jun/2019** |
| PSERN Non-Profit Operator Formation Includes 2015-RPT0134- Identified Milestone #10 (PSERN Non-profit Operator Formation) |  | Sep/2019 | May/2020 | May/2020*** |
| Radio Site Equipment Installations (Motorola) Includes 2015-RPT0134- Identified Milestone #7 (Backhaul System Implementation) and #8 (Land Mobile Radio System Implementation) |  | Sep/2018 | Jul/2020 | Jul/2020*** |
| System Optimization and Coverage Testing Includes 2015-RPT0134- Identified Milestone #9 (System Optimization and Testing) |  | May/2019 | Aug/2020 | Jul/2020*** |
| Deploy & Transition End User Radios Includes 2015-RPT0134- Identified Milestone #11 (Transition Users to PSERN System) |  | Mar/2020 | Dec/2020 | Dec/2020*** |
| Project Substantially Complete/ Transfer to PSERN Operator Includes 2015-RPT0134- Identified Milestone #12 (Full System Acceptance) |  | Sep/2020 | May/2021 | May/2021*** |
| PSERN Project Closeout Includes 2015-RPT0134- Identified Milestone #13 (Project Closeout) |  | Sep/2021 | Dec/2022 | Dec/2022*** |
| *behind schedule **= at risk ***= on schedule |

2018 Supplemental Appropriation Request - Update. The PSERN project is subject to mandatory phased appropriations, meaning appropriation by project phases, as described in King County Code. A supplemental budget appropriation request for funding for the final two phases of the project (Implementation and Close-out) was transmitted to Council in April 2018. As indicated by project staff, the supplemental appropriation request to the PSERN Capital Fund of approximately $205 million includes all costs associated with the completion of the project including labor costs (salaries, wages, and benefits), overhead costs, site development and ongoing vendor payments, including architecture and engineering for radio sites, specialized legal services, quality assurance consulting and construction contractors. This supplemental appropriation request, Proposed Ordinance 2018-0197, was first briefed at the April 25, 2018 meeting of the Budget and Fiscal Committee (BFM). The next hearing for this item is scheduled for the May 9, 2018 BFM Committee meeting.

Project Scope & In-Building Coverage. The PSERN project’s broad definition of “in-building coverage” refers to the ability of first responders to communicate with each other inside and outside of a building. In-building coverage is not within the current PSERN project scope. As indicated by PSERN project staff, project partner representatives have requested to revisit the topic of in-building coverage requirements and criteria under PSERN. Project staff are working on two major activities related to in-building coverage, including an in-building task force and outreach to building owners throughout the county to ensure that they are aware of PSERN and how their in-building systems can connect to PSERN.

In-Building Task Force - Update. An in-building task force has been formed, as indicated by PSERN project staff, comprised of first responders who will be using the system and the technical staff who run the current emergency radio communications system in King County. This group proposed utilizing the assistance of a technical consultant with expertise on in-building coverage, which the Joint Board approved at its October 26, 2017 meeting. The preliminary in-building coverage analysis report was presented at the April 26, 2018 Joint Board meeting. The report identified the three main goals of the task force as follows:

- Define a set of in-building coverage requirements and compare with predicted PSERN coverage maps and data.

- Identify areas of the county where in-building coverage is a major concern.

- Determine if predicted PSERN coverage is adequate in these areas based on the identified requirements.

The task force reviewed multiple options for addressing in-building coverage concerns in King County and evaluated the options based on operational, technical and financial implications. These options are summarized in Table 3.

Table 3. In-Building Task Force Preliminary Report – Options Summary

| Approach | Capital Investments | Operational Costs | Pros | Cons |
| --- | --- | --- | --- | --- |
| Task Force Recommended Option: Hybrid 13 New Radio Towers 2 DAS/BDA 16 vehicular repeaters Total | $23.4M $150K $209K $23.7M | $1.2M $1K $8K $1.2M | Cost effective solution. Technically balanced approach Minimal impact on operations | Towers may still not provide full coverage in buildings Does not provide additional towers in low-density areas |
| Option B: New Towers Only 21 New Radio Towers 0 DAS/BDA 0 vehicular repeaters Total | $37.7M $0 $0 $37.7M | $1.9M $0 $0 $1.9M | Provides added highly reliable PSERN radio coverage in buildings throughout most developed areas of the county Minimal impact on operations | Expensive solution with lots of risk to existing PSERN network design. Towers may still not provide full coverage in buildings |
| Option C: Hybrid 2 New Radio Towers 28 DAS/BDA 76 vehicular repeaters Total | $3.6M $6.3M $992K $10.9M | $182K $14K $38K $234K | Low cost solution Provides added highly reliable PSERN radio coverage in highest density areas of the county | New radio sites only in downtown areas of Bellevue and Seattle. Major impact on operations with deployment of multiple vehicular repeaters Towers may still not provide full coverage in buildings |
| Option D: DAS Only 0 New Radio Towers 52 DAS/BDA 0 vehicular repeaters Total | $0 $22.8M $0 $22.8M | $0 $26K $0 $234K | Provides good coverage throughout buildings with DAS systems installed Below grade levels covered. Low initial capital investment. Little impact to operations. | Existing buildings difficult to target for DAS system, and will require retrofit which is expensive. Government agencies will need to retrofit BDAs in critical buildings that do not have desired level of in-building coverage. Risk for adverse interference from excessive number of BDAs in the area. |
| Option E: Vehicular Repeaters Only 0 New Radio Towers 0 DAS/BDA 3000 vehicular repeaters Total | $0 $0 $39.2M $39.2M | $0 $0 $1.5M $1.5M | Portability Provides good communications during a sustained incident | Operationally complex Requires user training Expensive when deployed for each emergency response vehicle in the county. Capacity limited to a single talk path per unit. |

As noted in Table 3, of the identified options, the task force-recommended option entails a three-layered approach for addressing in-building coverage concerns in King County, including addressing in-building coverage in high and medium density areas with additional radio tower sites; bringing the exterior PSERN radio system coverage inside of building with distributed antenna systems; and utilizing vehicular repeaters for sustained incidents where coverage is challenging. The estimated cost associated with this option entails approximately $23.7M in one-time capital expenses and $1.2M in annual operating costs. Joint Board discussion of the task force’s preliminary report and in-building coverage is ongoing, including possible considerations and implications of the options included in the report in relation to project scope and system design, budget and schedule.

King County Auditor Capital Projects Oversight. The Capital Projects Oversight Program of the King County’s Auditor’s Office have released two reports on PSERN, one in November 2015 and another in February 2017. Both reports focused on project scope, schedule, budget and risks, and included recommendations for the PSERN project team. Additionally, a briefing entailing an Auditor’s Capital Project Oversight Program status report on the PSERN project was presented at the January 9, 2018 Law and Justice Committee (2017-B0225) and included recommendations to closely monitor the re-baselined project schedule for deviations or delays.

The next report, not yet released as of the writing of this staff report, is scheduled to be presented by Auditor’s Office Capital Project Oversight Program staff as part of a briefing at the May 8, 2018 Law and Justice Committee meeting (today’s meeting) and the May 9, 2018 Budget and Fiscal Committee meeting.

ATTACHMENTS

PowerPoint Presentation “Puget Sound Emergency Radio Network (PSERN) Project Update, Law and Justice Committee, dated May 8, 2018”

INVITED

- David Mendel, Director, Emergency Radio Communications Division, King County Information Technology (KCIT)

- Kimberly Nuber, Deputy Division Director – PSERN Project, KCIT

According to PSERN project staff, King County owns just under 50 percent of KCERCS, the city of Seattle and Eastside Public Safety Communications Agency owns approximately 25 percent each and ValleyCom owns approximately 10 percent.

Ordinance 18075.

As of September 2017, the members of the Joint Board are as follows:  Fred Jarrett, non-voting Chair; Sharon Potts, King County voting member; Chief Harold Scoggins, Seattle voting member; Kurt Triplett, EPSCA voting member; Lora Ueland, ValleyCom voting member; Chris Elwell, non-voting fire agency member; and Chief John Vinson, non-voting police agency member.

PSERN project staff indicate that the contract, with respect to duration, includes project implementation through 20 years after project completion. Additionally, PSERN project staff indicate that, due to contract change orders, the current value of the contract is approximately $117.4 million (increase from $112 million), which is reflected in the re-baselined project budget that was approved by the PSERN Joint Board in January 2018.

In addition to the primary contract with Motorola, the Executive has hired consultants to develop the site design and to provide construction management oversight.

Ordinance 18074.

As indicated by PSERN project staff, the project provides a variety of reports and updates to several oversight and advisory groups on at least a monthly basis. Aside from Council committees, Executive Office leadership and KCIT leadership, the project also reports to the King County Auditor’s office, quality assurance consultants, King County Project Review board, PSERN Joint Board, PSERN Operations Board and PSERN Technical Committee.

In 2016, the Law, Justice and Emergency Management Committee was changed to the Law and Justice Committee.

2017-B0226, presented at the January 9, 2018 Law & Justice Committee meeting, and 2018-B0022, presented at the February 14, 2018 Regional Policy Committee meeting.

Levy revenue projections in Table 1 are based on the August 2017 OEFA forecast. March 2018 forecast levy revenue projections for PSERN indicate a net change (increase) of approximately $2.7 million from the August 2017 forecast (https://www.kingcounty.gov/independent/forecasting.aspx).

Three milestones identified in 2015-RPT0134 are not reported in Table 2, including Factory Acceptance Testing (milestone # 5), Site Construction Mid-point milestone (#3) and the Group 2 Site Leasing milestone (#4). Milestones #3 and #4 were eliminated, as previously reported and indicated by project staff, due to no longer being applicable to the project.

Current Completion dates, as indicated by project staff, assume that WSDNR meets proposed deadline for final agreement on leases.

"n/a" for original schedule because this is a new milestone.

As indicated in the preliminary report, the task force began the process of evaluating in-building coverage for King County with several key assumptions, intended to provide a baseline for the task force to begin the analysis and clearly identify the known state of in-building coverage as currently designed. Included in these assumptions are the following:

PSERN system is designed to high public safety standard and will provide high reliability portable radio coverage on-street throughout the county, and within each incorporated city.

Existing PSERN design will provide some level of in-building coverage throughout the county without any modifications.

In-building coverage should not be expected in 100% of each building

In-building coverage should not be expected in 100% of each area

The task force is primarily concerned with in-building coverage in densely developed areas and where building construction materials cause excessive attenuation.

Residential areas are not a major concern for in-building coverage.

Below grade areas should not be expected to be covered from the external radio network.

2015-B0210: A briefing on the Capital Projects Oversight November 2015 Report regarding PSERN, presented to the Government Accountability and Oversight Committee on 11/10/15. An electronic version of the November 2015 report is available at http://www.kingcounty.gov/~/media/depts/auditor/new-web-docs/2015/2015-cpo-psern/cpo-psern-final.ashx?la=en. The November 2015 report included five recommendations for the PSERN project:

- The PSERN project team should revise the project schedule and communicate it to stakeholders before the end of 2015 to include reasonable time to accomplish the remaining tasks necessary to finish tower site construction. The schedule should be based on progress to date and identify the impact on the remainder of the project schedule.

- The PSERN project team should improve reporting to clearly demonstrate to stakeholders the progress on leasing and constructing radio tower sites. Reporting should show how current cost and schedule forecasts compare to the assumptions used in the preliminary project estimate.

- The PSERN project team should establish and document a project baseline prior to signing any construction contract. The baseline should use the certainties from the Motorola contract, best available information for tower site costs and schedule, and refined estimates of other costs.

- The Finance and Business Operations Division (FBOD) should provide ongoing technical assistance to the PSERN project team to help manage the cost risks of any construction work order contracts for this project.

- Before seeking bids on a work order construction contract for the radio tower sites, the PSERN project team and FBOD should evaluate the relative benefits, costs, and risks specific to each site of inclusion in a work order contract or a traditional design-bid-build contract. This evaluation should be documented and result in a recommended approach for each individual site for consideration and approval by the project sponsor.

2017-B0038: Auditor’s Capital Project Oversight Status Report on PSERN, presented to the Law and Justice Committee on 2/28/17. An electronic version of the February 2017 report is available at http://www.kingcounty.gov/~/media/depts/auditor/new-web-docs/2015/2015-cpo-psern/cpo-psern-2017.ashx?la=en. The February 2017 report included four recommendations for the PSERN project:

- The Puget Sound Emergency Radio Network (PSERN) project team should expand its outreach and communications plans to identify detailed, proactive engagement with building owners to allow them time to evaluate their systems and prepare for any needed changes.

- The PSERN project team should evaluate and compare the impacts on contract requirements, schedule, and costs for 1) the current plan of simultaneously constructing Primary Bounded Area sites, versus 2) extending the Primary Bounded Area site development schedule to allow construction of sites in sequence.

- The PSERN project team should complete updated site development cost estimates based on current information, should update the overall projects costs based on this information, and enter the project baseline costs into the County’s Project Information Center.

- The PSERN project team should refine the schedule to reflect realistic site development milestone achievement dates and should enter the project baseline schedule into the County’s Project Information Center.