## Sheet1
Coverage Area | Site Name | Site Owner | Description of work | 2017 Baseline Budget Estimate | Current Cost Estimate | Status | Est. completion date
PBA | Cambridge | City of Kent | Tower Extension, Shelter, Generator | 95000 | 273986 | Under Construction | 2019-05-14
PBA | Valley Communications Center (VCC) | VCC | Floor reinforcement | 0 | 37000 | Under Construction | 2018-05-31
PBA | Skyway | Skyway Water District | Tower Extension and Minor Retrofitting | 35000 | 93305 | Under Construction | 2019-05-16
PBA | View Park | Private Owner | New Tower, Shelter, Generator | 756092.05 | 756092.05 | Under Construction | 2019-04-22
PBA | Capitol Hill | KCTS | Tower upgrade, Generator, Minor Retrofitting | 425000 | 1200000 | Under Construction | 2019-08-13
PBA | Bellevue Station 9 | City of Bellevue | New Tower, Shelter, Generator | 310000 | 571362 | Under Construction | 2019-05-20
PBA | Preston | WA DNR | New Tower, Shelter, Generator | 276000 | 306507 | Under Construction | 2019-05-30
PBA | Rattlesnake Mtn. | WA DNR | Shelter, Generator | 162000 | 416107 | Under Construction | 2019-06-06
PBA | East Tiger | WA DNR | New Tower, Shelter, Generator | 260000 | 589000 | Under Construction | 2019-06-04
PBA | West Tiger | WA DNR | New Tower, Shelter, Generator | 340000 | 640158 | Under Construction | 2019-07-19
PBA | Tacoma (INDHL) | City of Tacoma | Tower Extension and Minor Retrofitting | 185000 | 185000 | Awaiting Lease | 2019-09-13
PBA | McDonald Mtn. | Land - WA DNR, Shelter/Tower - VCC | Minor Retrofitting | 60000 | 104216 | Awaiting Lease | 2019-08-12
PBA | King Lake | Private Owner | Shelter, Generator | 448000 | 448000 | Awaiting Lease | 2019-10-03
PBA | Cougar Mtn. | U. S. Army Corps of Engineers | Tower upgrade, Shelter, Generator | 155000 | 363529 | Construction start Est. 5/1 | 2019-07-22
PBA | West Seattle | City of Seattle | New Tower, Shelter, Generator | 153028 | 451396 | Construction start Est 4/29 | 2019-09-13
PBA | 3 Sisters | Private Owner | New Tower, Shelter, Generator | 2159641.68 | 2159641.68 | Awaiting Permit | 2019-09-16
PBA | Tolt | Private Owner | New Tower, Shelter, Generator | 1299232.71 | 1299232.71 | Awaiting Permit | 2019-09-26
S.R. 410 | Greenwater | Muckleshoot Tribe | New Tower, Shelter, Generator | 732591.52 | 732591.52 | Under Construction | 2019-05-09
I-90 | Tinkham | WA DOT | New Tower, Shelter, Generator | 300000 | 436696 | Under Construction | 2019-06-19
I-90 | Iron Horse | Private Owner | Shelter, Generator | 786451.83 | 786451.83 | Under Construction | 2019-06-25
I-90 | Olallie | WA DOT | New Tower, Shelter, Generator | 350000 | 460000 | Under Construction | 2019-06-20
I-90 | Snoqualmie Pass | USFS | New Tower, Shelter, Generator | 750000 | 2600122 | Construction Start Est. June | 2019-10-03
U.S. 2 | Sobieski | USFS | New Tower, Shelter, Generator | 650000 | 1030230 | Under Construction | 2019-10-31
U.S. 2 | Three Lakes | Snohomish PUD | Minor Retrofitting | 250000 | 30000 | Awaiting Lease | 2019-11-04
U.S. 2 | Cowboy | USFS | New Tower, Shelter, Generator | 400000 | 2460184 | Awaiting Lease | 2019-10-22
U.S. 2 | Stevens Pass Ski Resort | USFS | New Tower, Shelter, Generator | 250000 | 1750000 | Awaiting Lease | 2019-10-08
U.S. 2 | Wellington | USFS | New Tower, Shelter, Generator | 2900000 | 3080446 | Awaiting Lease | 2019-11-05
U.S. 2 | Scenic | USFS | New Tower, Shelter, Generator | 1000000 | 2839107 | Awaiting Lease | 2020-05-19
U.S. 2 | Deception Creek | USFS | New Tower, Shelter, Generator | 3000000 | 3352264 | Awaiting lease | 2019-11-07
PBA | Vashon Island | Private Owner | New Tower, Shelter, Generator | TBD | TBD | Awaiting lease/Permits | 2019-09-11
PBA | Auburn | Private Owner | New Tower, Shelter, Generator | TBD | TBD | Awaiting Permit | 2019-09-23
S.R. 410 | Grass Mtn. | WA DNR | New Tower, Generator and Minor Retrofitting | 400000 | 509000 | Awaiting Lease/Permit | 2020-09-28
I-90 | Hyak | WA DOT | New Tower, Shelter, Generator | 200000 | 350000 | Construction Start Est. June | 2019-07-15
I-90 | Stampede | Land - USFS, Tower/Shelter - KITCOMM | Minor Retrofitting | 150000 | 150000 | Awaiting Lease | 2019-10-09
I-90 | I-90 Repeater | USFS | New Tower | 650000 | 3400000 | Awaiting Lease | 2019-11-19
I-90 | Bandera | WA Parks | New Tower | 650000 | 1800000 | Awaiting Lease/Permit | 2020-04-23
U.S. 2 | Maloney | USFS | New Tower, Shelter, Generator | 3500000 | 4200000 | Construction Start Est. August | 2019-10-29
U.S. 2 | Deer Creek | WA DNR | New Tower, Shelter, Generator | 300000 | 1400000 | Awaiting Lease | 2019-10-14
U.S. 2 | Hwy2 West | USFS | New Tower | 650000 | 1800000 | Awaiting Lease | 2019-09-30
|  |  |  | 18488037.79 | 29452624.79
Notes:
Sites above the heavy black line are under contract for constrcution at the specified "Current Cost Estimate" amount. Sites below the heavy black line are pending construction contracts.
All sites generally also have electrical upgrades and/or electrical retrofitting.
Sites listed as having a "Private Owner" are Motorola developed sites
Due to viability issues, Vashon and Auburn Site Construction values will be reset and covered in a Change Order with Motorola
The Sobieski site has a contract for the New Tower, but does not have a contract for the shelter and generator.