King County Mental Health, Chemical Abuse and Dependency Services

Mental Illness and Drug Dependency Implementation Plan

VERSION 7

REVISED October 8, 2008

Table of Contents

|  | Page # |
| --- | --- |
| Introduction | 2 |
| Community Based Care |  |
| 1a-1 Increase access to community mental health treatment…………………………………………. | 13 |
| 1a-2 Increase access to community substance abuse treatment……………..…………………......... | 16 |
| 1b Outreach and engagement to individuals leaving hospitals, jails, or crisis facilities……………. | 20 |
| 1c Emergency room substance abuse early intervention program………………………..………… | 24 |
| 1d Mental health crisis next day appointments and stabilization services…………………………… | 28 |
| 1e Chemical dependency professional education and training……………………………………….. | 31 |
| 1f Parent partner and youth peer support assistance program………………………………...…….. | 35 |
| 1g Prevention and early intervention mental health and substance abuse services for adults age 55+………………………………………………………………………………………….……………. | 39 |
| 1h Expand availability of crisis intervention and linkage to on-going services for older adults…… | 42 |
| 2a Caseload reduction for mental health………………………………………………………………… | 46 |
| 2b Employment services for individuals with mental illness and chemical dependency…………… | 50 |
| 3a Supportive housing services………………………………………………………………………… | 54 |
| Programs Targeted to Help Youth |  |
| 4a Services for parents in substance abuse outpatient treatment……………………………………. | 59 |
| 4b Prevention services to children of substance abusers…………………………………...………… | 63 |
| 4c School district based mental health and substance abuse services……………………………… | 67 |
| 4d School based suicide prevention………………………………………...…………………………… | 71 |
| 5a Expand assessments for youth in the juvenile justice system…………………………………….. | 75 |
| 6a High fidelity wraparound initiative……………………………...……………………………….......... | 78 |
| 7a Reception center for youth in crisis………………………….……………………………………….. | 83 |
| 7b Expansion of children’s crisis outreach response service system………………………………… | 87 |
| 8a Expand family treatment court services and support to parents………………………………….. | 91 |
| 9a Expand juvenile drug court treatment………………………………………………………………… | 95 |
| Jail and Hospital Diversion Programs |  |
| 10a Crisis intervention training program……………………………………………………………...…… | 100 |
| 10b Adult crisis diversion center, respite beds, and mobile behavioral health crisis team………….. | 104 |
| 11a Increase capacity for jail liaison program……………………...…………………………………….. | 108 |
| 11b Increase services available for new or existing mental health court programs………………….. | 112 |
| 12a Increase jail re-entry program capacity………………………………………………………………. | 116 |
| 12b Hospital re-entry respite beds…………………………………………………………………………. | 122 |
| 12c Increase Harborview’s Psychiatric Emergency Services capacity to link individuals to community services upon discharge from ER……………………………………………………… | 126 |
| 12d Urinalysis supervision for Community Center for Alternative Programs clients………...……….. | 129 |
| Domestic Violence, Sexual Assault, and Expansion of Adult Drug Court |  |
| 13a Domestic violence and mental health services……………………………………………………… | 133 |
| 13b Domestic violence prevention…………………………………………………………………………. | 138 |
| 14a Sexual assault and mental health services………………………………………………………….. | 142 |
| 15a Adult drug court expansion………………………………...………………………………………….. | 147 |
| Housing Development |  |
| 16a New housing units and rental subsidies……………………………………………………………… | 155 |
| New Strategies | 160 |
| 17a | 161 |
| 17b | 164 |
| Appendices |  |
| Appendix A – Oversight Committee………………………………………………………………………... | 176 |
| Appendix B – Strategy Implementation Process………………………………………………………….. | 179 |
| Appendix C – Implementation Timeline……………………………………………………………………. | 183 |
| Appendix D – Spending Plan……………………………………………………………………………….. | 184 |
| Appendix E – RFP Decision Model…………………………………………………………………. | 187 |

Introduction

1.	Overview

In July 2006 the King County Council, recognizing the unmet needs of people disabled by mental illness and chemical dependency and the ongoing public costs of serving them in hospitals and jails, passed Council Motion 12320, calling for the development of a three-phase action plan:

“… to prevent and reduce chronic homelessness and unnecessary involvement in the criminal justice and emergency medical systems and promote recovery for persons with disabling mental illness and chemical dependency by implementing a full continuum of treatment, housing and case management services”.

The three-phase action that was developed, called “The Mental Illness and Drug Dependency (MIDD) Plan”, was accepted by Council in October 2007.  In November 2007 Council passed Ordinance 15949, authorizing the collection of a one-tenth of one-percent sales and use tax to provide funding for the programs outlined in the MIDD, and requiring the submission of a three-part Oversight, Implementation, and Evaluation Plan for Council approval prior to funds being spent on the MIDD.  The Oversight Plan, describing the representation, roles and responsibilities of the Oversight Committee, was approved by Council on April 28, 2008.  The attached Implementation Plan describes in detail the services that will be provided, the resources needed for implementation, the timeline and milestones for implementation, how drug diversion court and programs that support victims of domestic violence and sexual assault, and how housing will be included in the MIDD continuum of mental health and substance abuse services, and the revised spending plan for the MIDD fund. This Implementation Plan provides a detailed framework for a comprehensive system of programs and strategies that will fulfill the Council mandate to create a full continuum of treatment, housing, and case management services that will lead to a significant reduction in the human and public costs of mental illness and chemical dependency in King County.

The MIDD Implementation Plan will provide an integrated system of:

- Prevention and early intervention services

- Community-based treatment

- Expanded therapeutic court programs

- Jail and hospital diversion programs

- Housing and housing supportive services.

The plan includes new programs as well as expansion of existing programs and services.  These new and expanded services will address the unmet needs of approximately 33,000 individuals in King County each year.

- Development of the MIDD Implementation Plan

The MIDD Implementation Plan represents the collaborative efforts over a two-year period of a wide range of community and governmental stakeholders, including representatives of mental health and substance abuse treatment agencies, courts, law enforcement, public health, the prosecuting attorney, public defense, juvenile and adult justice systems, children’s services, juvenile rehabilitation, and many others.  The product of this work is a comprehensive, multi-jurisdictional plan to help youth and adults who are at risk for or suffer from mental illness and/or substance abuse.

The strategies that make up the MIDD Plan were first developed by several community workgroups that met from the spring of 2006 through the spring of 2007.  These groups used the Sequential Intercept Model as a framework to determine what services need to be provided for which people at what locations in order to help prevent incarceration, hospitalization, and homelessness.  This model has been adopted by a number of communities across the nation as an action blueprint for planning system change in the way that communities address the problem of people with mental illness in their criminal justice systems.

King County has adapted the organizing principles of this model to include people who may have no mental illness but who are at risk for criminal justice involvement due to substance abuse, and to include diversion from emergency medical services as another priority.  The work group also expanded on the model’s definition of core services to put more emphasis on youth and on prevention services.

The workgroups that developed the strategies for the MIDD recognized that the greatest opportunities for diversion exist when individuals are still in the community, and that diversion options decrease as individuals move through the criminal justice system.  Understanding the importance of prevention services, early assessment and intervention, and comprehensive and integrated community-based services, the MIDD plan has devoted considerable resources to build and support a community services system that will serve to divert many individuals from the criminal justice and emergency medical systems while also providing the infrastructure needed to help people who have entered these systems rejoin the community in a safe and effective manner.

Following the acceptance by the King County Council of the MIDD plan and the passage of Ordinance 15949 authorizing the collection of the one-tenth of one-percent sales and use tax, additional work was done to refine the original strategies, and to add new strategies to the Plan to serve individuals in adult drug court as well as victims of domestic violence and sexual assault.  This new work was done by in collaboration with a number of community and government stakeholders, and with the newly formed Interim Oversight Committee.

The MIDD Oversight Committee was convened first as an interim group in April, 2008 while legislation adopting the Oversight Plan was being processed, and subsequently seated as a formal committee in May 2008 after members were appointed by the King County Executive and confirmed by the King County Council.  The Committee is comprised of representatives from a broad spectrum of county, community and city entities (a list of committee members is provided in Appendix A).  Committee members and their staff generously contributed their time, insight and knowledge to review and provide input on the draft Implementation Plan.  Members attended and participated in multiple committee meetings as well as in workgroup meetings at which each strategy in the plan was discussed in detail.  Public comment was also received by the committee through testimony at meetings, written comments, website comments, and presentations by members of their own stakeholder groups.  In addition, the members of the Oversight Committee reviewed and provided input on the revised 2008 spending plan.  Completion of the MIDD Implementation Plan would not have been possible without the thoughtful collaboration of the Oversight Committee members.

Through the MIDD programs, individuals with mental illness and chemical dependency will be linked to effective services designed to help them to become stable and productive, and prevent unnecessary incarceration and hospitalization.  These services include:

- Prevention and early intervention strategies for high-risk youth that will reduce substance abuse and youth suicide, help more youth to stay in school, and prevent their involvement in the juvenile justice system.

- Community-based treatment will provide mental health and chemical dependency services for people who have not previously been able to access them.

- Crisis intervention training for police and other first responders, a crisis diversion facility for adults, and a reception center for youth that will provide effective alternatives to jails and hospitals for individuals in crisis.

- Therapeutic court program that will divert juveniles and adults from detention and jail.

- Early intervention and prevention services for adult and child survivors of domestic violence and sexual assault that will help prevent the onset of more severe mental illness and substance abuse, and help to interrupt the intergenerational cycle of violence.

- Housing with supportive services that will ensure that individuals who are homeless will be able to receive the maximum benefit from treatment services.

Together, all of these strategies will result in an improved quality of life for people with mental illness and chemical dependency and their families throughout King County.

3.	The MIDD Implementation Plan Strategies

The MIDD Implementation Plan strategies are grouped into five service areas.  The first three were included in the MIDD Action Plan that was accepted by the King County Council in October 2007.  The fourth service area includes new programs incorporated into the MIDD plan in response to King County Ordinance 15949 and a change in State law which clarified the use of sales tax collections for housing. The Council, recognizing the unmet mental health and substance abuse treatment needs of individuals involved in adult drug diversion court and of victims of domestic violence and sexual assault, directed the Implementation Plan to include services for these individuals. The final service area addresses the housing needs of individuals with serious mental illness and chemical dependency.

1.	Community-Based Care includes strategies to:

- Increase access to community mental health and substance abuse treatment for uninsured children, adults, and older adults

- Improve the quality of care by decreasing mental health caseloads and providing specialized employment services

- Provide supportive services for housing projects serving people with mental illness and chemical dependency treatment needs.

2.	Programs Targeted to Help Youth includes strategies to:

- Expand prevention and early intervention programs

- Expand assessments for youth in the juvenile justice system

- Provide comprehensive team-based, intensive “wraparound” services

- Expand services for youth in crisis

- Maintain and expand Family Treatment Court and Juvenile Drug Court.

3.	Jail and Hospital Diversion includes strategies to:

- Divert people who do not need to be in jail or hospital through crisis intervention training for police and other first responders and by creating a crisis diversion facility

- Expand mental health courts and other post-booking services to get people out of jail and into services faster

- Expand programs that help individuals re-enter the community from jails and hospitals.

4.	Domestic Violence and Sexual Assault Intervention and Prevention and Adult Drug Court includes strategies to:

- Address the mental health needs of children who have been exposed to domestic violence

- Increase access to coordinated, early intervention mental health and substance abuse services for survivors of domestic violence

- Increase  access to treatment services for victims of sexual assault

- Enhance services available through the King County Adult Drug Diversion Court.

- Housing Development includes strategies to:

  - Support capital projects and rental subsidies for people with mental illness and chemical dependency.

(Note: This strategy was enabled by legislation passed into law in March 2008 (SSB 6791) that clarified that moneys collected under the county-authorized sales and use tax for mental health and chemical dependency services and therapeutic courts could be used for housing that is a component of a coordinated chemical dependency or mental health treatment program or service.  This new housing development strategy will use unspent funds resulting from the delayed start-up of programs in 2008, and will not take away funding that could be used for the service strategies listed above.)

Each individual strategy contains:

- A needs statement

- A description of services

- A discussion of needed resources, including staff, information and provider contracts

- Milestones for implementation of the programs.

A table showing what type of services will be provided (mental health, substance abuse, or both), age groups served, whether the service is an expansion of an existing service or a new service, whether a request for proposal process is required, and estimated service start dates is provided in Appendix B.

A schedule for the implementation of programs is included in Appendix C.  A revised 2008 spending plan and financial plan for the mental illness and drug dependency fund is included in Appendix D and discussed below.  In addition, each of the strategies includes a list of linkages to other programs and planning and coordinating efforts, highlighting the fact that collaboration and coordination are critical to the successful implementation of the MIDD Plan.

4.	MIDD Management and Implementation

The King County Department of Community and Human Services’ (DCHS) Mental Health, Chemical Abuse and Dependency Services Division (MHCADSD) has overall responsibility for the management of the implementation of the MIDD, including managing the budget, program development, issuing requests for proposals (RFPs), writing and monitoring contracts, quality management, and program evaluation.

The MIDD Oversight Committee is an advisory body to the Executive and Council, whose purpose is to ensure that the implementation and evaluation of the strategies and programs funded by the MIDD tax revenue are transparent, accountable, collaborative and effective.  The Oversight Committee will review, make recommendations, and provide comments to the Executive and Council on emerging and evolving priorities for the use of the MIDD revenue, and on the implementation and evaluation components of the MIDD Plan.  The Oversight Committee is staffed collaboratively by MHCADSD and the King County Office of Management and Budget (OMB).

A.	Timeline for implementation

The timeline for implementation of the strategies was determined by MHCADSD staff in consultation with stakeholders and partners identified for each strategy.  Variables considered in developing timelines included whether or not the plan was complete or needed additional development, whether an RFP was required or not, and the time needed for staff recruitment and training.  In addition, MHCADSD considered the work required by community providers to respond to RFPs, and, when possible, spread out the RFP response dates so that providers would not have to respond to multiple RFPs at the same time.

B.	Procurement for services

King County policies regarding procurements were followed in determining whether a competitive RFP was required for each strategy.   See Appendix E for the King County procurement requirements.  The decision tree below shows how decisions were made regarding the need for RFPs.

There have also been differences in perspective among Oversight Committee members regarding whether Strategy 11b, to increase services available for new or existing mental health courts, requires an RFP process.

C.	Provision of services

The great majority of services that will be provided through the MIDD will be contracted out to community agencies.  When fully implemented, an estimated 438 full-time equivalent staff must be hired to provide the services and administrative responsibilities of the MIDD Plan.

D.	Fiscal management

The .1% sales tax to support Mental Illness and Drug Dependency (MIDD) is collected by the State and transmitted to King County within two to three months of its receipt.  King County then deposits the proceeds into the MIDD fund which is managed by the MHCADSD. Once the funds are available, and all other necessary conditions have been met, contracts of memoranda of agreement with providers for MIDD services will be written and negotiated and services can begin.  Providers will be paid in the same manner as for other services contracted by MHCADSD:  by either check or wire transfer.

MHCADSD has the infrastructure in place to contract with providers and to manage and measure the services they provide before releasing payments.   All of the current funding sources for MHCADSD, including the State Mental Health Division and the Division of Alcoholism and Substance Abuse, the City of Seattle and others, require evidence that services are being performed in conformance with their contracts or agreements as a condition of payment.  The same infrastructure and fiscal management methodology will be used to manage MIDD funds and services, as are

used to manage MHCADSD’s other books of business.  No lump sum payments will be issued prospectively in anticipation of services.

E.	Revised spending plan

The original 2008 spending plan for the MIDD was first developed in mid-2007. This 2008 spending plan was revised recently to incorporate information that became available this year regarding when funds would be available for spending.  Because we now know that MIDD services can not start until late September/early October of 2008, the spending plan reflects spending on provider services that start no earlier than when funds become available.  Other factors have also been taken into account as appropriate in developing the spending plan including the ability to hire staff, ramp up services, and accommodate organizational and facility growth needs.  The revised 2008 spending plan is included in Appendix D.

6.	Challenges

A.	Need for Additional Planning

Several of the strategies in the MIDD plan can be implemented immediately after approval of the Implementation and Evaluation Plans by the King County Council.  Some of the new strategies involve multiple systems and will require additional planning.  These include:

- Adult Crisis Diversion Facility  (10b)

- Youth Reception Center  (7a)

- Outreach and Engagement to Individuals Leaving Hospitals, Jails or Crisis Facilities (1b)

- School District-Based Mental Health and Substance Abuse Services (4c)

- Increased Capacity for Harborview Psychiatric Emergency Services to provide linkage to community services (12c).

B.	Staffing

The MIDD strategies will require over 400 new staff at community-based agencies, including mental health professionals, chemical dependency professionals, case managers, administrative staff and others.  To address the complex and urgent needs of the people who will be served through the MIDD programs, staff for these programs should be highly qualified, experienced, and trained in the policies and procedures of the relevant agency.  Agencies implementing MIDD programs may be challenged to find qualified staff to fill all the new positions in a timely fashion.  To increase the number of qualified professionals available in King County, the MIDD Implementation Plan includes a strategy for training chemical dependency professionals in King County, resulting in up to 125 new certified chemical dependency professionals annually.

C.	Stability of King County Funding to Foundation Programs

In the current climate of King County budget reductions, questions have been raised at the MIDD Oversight Committee and in public comments as to the potential impact of budget cuts on existing programs that will be expanded or enhanced with MIDD

funding.  It is the intent of MHCADSD to move forward with implementation and planning in accordance with the timelines outlined in the MIDD Plan, and in Appendix C.  If necessary, these questions will be revisited after the adoption of the 2009 budget in November, 2008.

D.	MIDD Housing Development Strategy

MIDD Oversight Committee members expressed unanimous support for use of unspent 2008 funds for housing development and rental subsidies.  However, there is a difference in perspective among committee members and stakeholders who have submitted public comments regarding the use of funds for housing development in subsequent years.  One perspective is that services must be prioritized because the MIDD as originally presented to and approved by the King County Council was intended to fill large gaps in the mental health and chemical dependency treatment systems, and did not include housing.  A counter view is that housing needs to be a higher funding priority in order for services to be successful.  There is agreement that a balance is needed and this topic will be an area for continued discussion by the Oversight Committee.

E.	Use of MIDD Funds for Medication

In the process of reviewing the individual strategies in the MIDD Implementation Plan, some members of the Oversight Committee identified the need for funding for medication for many individuals receiving services through the MIDD programs.  MHCADSD recognizes this need, but has determined that medications are the responsibility of the State of Washington, and that service provision is the priority for MIDD funds. Community providers have worked with pharmaceutical companies and used other funding sources to provide for the medication needs of clients who are not able to access state funding to pay for medications.

F.	Supplantation issues

The state legislation (E2SSB 5763) that allowed counties to impose the sales and use tax that will provide the funding for the MIDD required that funds from the sales tax be used for new or expanded services and not be used to supplant existing funding for these services, with the exception of lapsed Federal funding previously used for the operation or delivery of services and programs as defined by the legislation.  Any services that were funded by King County at the time the County enacted the one-tenth of one-percent sales and use tax may not be subsequently funded by the sales tax in the event that county funding is lost.  This plan reflects adherence to the non-supplantation intent.

7.	Conclusion

As noted above, this Implementation Plan is the second part of a three-part plan required by Council as part of Ordinance 15949.  The third and final part, the Evaluation Plan, will be submitted to Council by August 1, 2008.  Once Council has approved all three plans, many of the programs in the Implementation Plan will begin to receive funds and provide services.  Other programs will be phased in as program

designs and procurements for services are completed and as staff are hired and trained by providers.  By the end of 2008, hundreds of children adults and older adults across King County will have begun to receive the services and supports needed to stabilize and improve their lives.  All the citizens of King County will benefit in the coming years as the public and human costs of mental illness and substance abuse are reduced.

Community Based Care

Strategies 1a – 3a

Strategy Title:	Increase Access to Community Mental Health and Substance Abuse Treatment

Strategy No:	1a (1) – Increased Access to Mental Health Outpatient Services for People Not on Medicaid

County Policy Goals Addressed:

- A reduction of the incidence and severity of chemical dependency and mental and emotional disorders in youth and adults.

- A reduction of the number of people with mental illness and chemical dependency using costly interventions like jail, emergency rooms and hospitals.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

The public mental health system has long been driven by Medicaid funding.  Medicaid regulations require that funds be expended only for persons on Medicaid.  These regulations and funding restrictions prevent King County from serving a large population of individuals who need mental health treatment but are not on Medicaid and are financially unable to pay for services.  Individuals with severe mental illness may not be covered by Medicaid due to their citizenship status, their inability to provide documentation needed for eligibility, their income intermittently exceeding the income limit for Medicaid eligibility, or other technical barriers to eligibility.  When they don’t receive needed outpatient services, they often end up in psychiatric hospitals and jails.  Over half the individuals with mental illness who are admitted to psychiatric hospitals do not have Medicaid coverage.  This strategy will serve people of all ages and who reside in all parts of King County.

- B.	Reason for Inclusion of the Strategy

Currently, when individuals lose their Medicaid coverage they also lose their mental health services, or are intermittently eligible.  This disrupts continuity of care and threatens the individual’s clinical stability.  Additionally, there is a large unserved population of people who are not on Medicaid, or do not qualify for Medicaid, whose mental health needs are only addressed when their need reaches crisis proportions - either in hospital emergency departments, inpatient care, or jails.  Expanded access to services could be put into place immediately upon receipt of expenditure authority, and would immediately open up access to services for individuals who are leaving hospitals and jails, and who previously would not have been able to receive services.

- C.	Service Components/Design

Provide expanded access to outpatient mental health services for individuals who do not qualify for, or lose their Medicaid coverage, yet meet the income and clinical eligibility  standards (medical necessity) for public mental health services.  Services offered will include assistance to individuals to establish Medicaid eligibility.

- D.	Target Population

Children, youth, adults, and older adults who have been served by the mental health system under Medicaid but have lost their eligibility; and individuals who have a mental illness, do not receive or do not qualify for Medicaid, or are waiting for approval for Medicaid, but meet clinical and financial eligibility criteria.  The priority will be for those who are most in need of services, particularly individuals exiting the justice system, being discharged from hospitals, court-ordered to treatment, and those at risk for homelessness, incarceration, or hospitalization.

- E.	Program Goals

Increase access to services and service provision for individuals who are currently ineligible; decrease the number who are re-incarcerated or re-hospitalized, and reduce jail and inpatient utilization, and homelessness.

- F.	Outputs/Outcomes

An additional 2400 non-Medicaid clients served per year.

A reduction in use of jail, hospital, and emergency services.

2.	Funding Resources Needed and Spending Plan

| Dates | Activity | Funding |
| --- | --- | --- |
| September 2008 | Implement revised policies for non-Medicaid back fill and access |  |
| Sept - December | Ramp up of non-Medicaid clients served | $2,130,000 |
|  | Total Funds 2008 | $2,130,000 |
| Jan – Dec 2009 | Target of 2400 non-Medicaid clients served annually | $8,520,000 |
|  | Total Funds 2009 | $8,520, 000 |
| Ongoing Annual | Total Funds | $8,520, 000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and Type of Providers (and where possible FTE capacity added via this strategy)

Current Regional Support Network (RSN) outpatient providers will be able to provide service as soon as funding is available and access is opened up.  Current work force capacity will need to be expanded to meet projected target. It is estimated that necessary recruitment and training would occur over approximately 16 months following the receipt of expenditure authority on or around September 15, 2008.

Approximately 70 - 75 additional FTEs may be required to deliver additional non-Medicaid services across the 16-member outpatient provider network.  This network

also includes youth-serving agencies that provide services under subcontracts with RSN providers.

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

| Dates: | Activity: |
| --- | --- |
| Sept 2008 | Training for provider network on new policies and access criteria |
| Sept – Dec 2008 | Training for inpatient units, civil commitment and mental health courts, and jail liaison |

- C.	Partnership/Linkages

King County Mental Health, Chemical Abuse and Dependency Services Division will continue to maintain close partnerships with its outpatient provider network, hospital inpatient units, jails, and community health clinics for referral of appropriate persons from the identified target populations who are not on Medicaid and in need of services.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

Development of revised policies and procedures: 	June 1 - July 15, 2008

Policies released for review and comment: 		July 15

End of review and comment period: 			August 6

Final policies released for implementation in 30 days: 	August 15

Providers implement new policies and increase

access for non-Medicaid population:			September 15, 2008

- B.	Procurement of Providers

The mental health providers are currently under contract with the County.  No RFP is required.

- C.	Contracting of Services

Increases can be accommodated within current contract structure.

- D.	Services Start Date(s)

Services to consumers will begin September 15, 2008, or as soon as spending authority is approved by King County Council.

Strategy Title:	Increased Access to Community Mental Health and Substance Abuse Treatment

Strategy No:	1a(2) – Increased Access to Substance Abuse Outpatient Services for People Not On Medicaid

County Policy Goals Addressed:

- A reduction of the incidence and severity of substance abuse and mental and emotional disorders in youth and adults.

- A reduction of the number of people with mental illness and substance abuse using costly interventions like jail, emergency rooms and hospitals.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

The present substance abuse treatment system provides treatment based on financial eligibility.  Many individuals are unable pay for treatment because they do not qualify for Medicaid or other public funding.  As of March 31, 2008 there are 219 unduplicated individuals on the waiting list to receive treatment that fall into this category.  Wait lists for substance abuse services for this population can be as long as 8 months. This strategy will provide access to treatment for individuals not eligible for or covered by Medicaid, the Alcohol and Drug Abuse Treatment and Support Act (ADATSA), or General Assistance Unemployable (GAU) benefits, or waiting for acceptance into a medical benefits program.

- B.	Reason for Inclusion of the Strategy

Providing opiate substitution treatment and non-opiate substitution substance abuse treatment lowers health care costs and reduces arrests and convictions.  Current funding for non-Medicaid clients is insufficient to meet the need.  Funds will be used to provide opiate substitution treatment (OST) and outpatient treatment for individuals who do not meet the financial eligibility requirements of the substance abuse treatment system in Washington State.

- C.	Service Components/Design

Funding will be increased to County contracted outpatient treatment agencies and OST programs to provide treatment services for low-income individuals from King County.  Low-income individuals are defined as having income of 80% of the state median income or less, adjusted for family size.  Specific service components include intensive outpatient treatment and outpatient treatment as well as daily doses of methadone or an alternate OST such as suboxone.

- D.	Target Population

Individuals who abuse substances or are chemically dependent leaving jails and inpatient treatment, undocumented residents, individuals on current wait lists, individuals who are not able to continue treatment due to loss of funding, individuals living with HIV/AIDS, intravenous drug users, and older adults and youth will be prioritized.

- E.	Program Goals

Increase the number of individuals with substance abuse problems admitted to substance abuse treatment and OST.  Numerous studies have shown that individuals who receive substance abuse treatment have reduced medical and criminal justice costs.

- F.	Outputs/Outcomes

An additional 461 individuals needing OST and 400 individuals needing outpatient substance abuse disorder treatment will receive services annually.  Providing access to needed substance abuse treatment will reduce the severity of chemical dependency as well as the medical and criminal justice costs for the individuals served.

2.	Funding Resources Needed and Spending Plan

The project needs $2,623,225 to increase substance abuse treatment services capacity within the provider community.

| Dates | Activity | Funding |
| --- | --- | --- |
| Sept – Dec 2008 | Start-up: OST Outpatient Treatment | $435,806 $220,000 |
|  | Total Funds 2008 | $635,806 |
| 2009 and onward | Ongoing Treatment Services OST Outpatient Treatment | $1,743,225 $880,000 |
| Ongoing Annual | Total Funds | $2,623,225 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers (and where possible FTE capacity added via this

strategy)

This funding level provides for additional treatment at two OST providers; and

this funding level provides for additional treatment capacity at 30 outpatient substance abuse treatment providers.

At the direction of the County, OST providers have begun to increase admissions and staff.  The agencies will hire a mix of Chemical Dependency Counselors and Trainees.  Trainees will receive training funds under MIDD strategy 1e.  Caseloads for OST average 75 clients per clinician.  An additional 6.5 FTE’s will be necessary.

Non-OST outpatient providers will need to increase staff capacity to take on new clients.  Agencies will hire a mix of Chemical Dependency Counselors and Trainees.  Trainees will receive training funds under MIDD strategy 1e.  Caseloads for non-OST outpatient counselors vary widely depending on the specific population that agency is targeting.  An additional 10.0 FTE’s will be necessary.

Because of recent treatment expansion in the area of Medicaid clients in recent years – provider agencies have been in a process of growth for over two years.  They are experienced in recruiting counseling staff.  In addition, new resources dedicated to workforce development will assist agencies in recruiting for these positions.

- B.	Staff Resource Develop Plan and Timeline (e.g. training needs, etc.)

| Dates: | Activity: |
| --- | --- |
| Sept – Dec 2008 | Treatment providers hire additional staff as needed; |
| Sept 2008 | Services start in those Agencies where capacity is developed and ready. |
| March 2009 | Assess capacity of treatment programs. |

- C.	Partnership/Linkages

King County Mental Health, Chemical Abuse and Dependency Services Division (MHCADSD) and the providers will need to continue to maintain significant partnerships with the local Community Services Organizations (CSO) that manage financial benefits and entitlements.  Although treatment services are available, other needed services such as housing, medical needs and cross system collaboration between mental health and substance abuse will need to continue.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

- Program design planning will be substantially completed by April 30, 2008.

- Draft contract exhibits for mental health and chemical dependency agencies will be developed by May 31, 2008 and routed internally for review.

- Contract amendment language for the chemical dependency agencies will be developed and transmitted to the providers by July 31, 2008.

- Treatment programs will start-up during the 4th calendar quarter of 2008.

- B.	Procurement of Providers

The chemical dependency providers are currently under contract with the County and no RFP is required for this expansion of services.

- C.	Contracting of Services

Contracts with the additional eligibility categories for chemical dependency providers will start on September 15, 2008

- D.	Services Start date(s)

Services to consumers will begin September 15, 2008 and increase throughout the first quarter and each subsequent year until reaching full capacity.

Strategy Title:	Increase Access to Community Mental Health and Substance Abuse Treatment

Strategy No:	1b – Outreach and Engagement to Individuals Leaving Hospitals, Jails, or Crisis Facilities

County Policy Goals Addressed:

- Diversion of youth and adults with mental illness and chemical dependency from initial or further justice system involvement.

- A reduction of the number of people with mental illness and chemical dependency using costly interventions like jail, emergency rooms and hospitals.

- Explicit linkage with, and furthering of, other council directed efforts including the Adult and Juvenile Justice Operational Master Plans, the Ten-Year Plan to End Homelessness in King County, the Veterans and Human Services Levy Service Improvement Plan and the Recovery Plan for Mental Health Services.

- A reduction of the number of people who cycle through the jail, returning repeatedly as a result of their mental illness or chemical dependency.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

The One Night Count, conducted on January 25, 2007, estimated that there are 6000 individuals using emergency shelter and transitional housing on any given night in King  County.  This strategy was proposed during the original development of the Mental Illness and Drug Dependency Action Plan (MIDD) as a way of addressing the needs for ongoing case management for homeless individuals being discharged to shelters from jails and hospitals, as well as for those who would be discharged from the new crisis diversion facility that is being planned as part of the MIDD.  The original concept was to build upon the success of Healthcare for the Homeless in engaging and assisting individuals at several shelters in King County with mental health, chemical dependency, and primary health needs.

- B.	Reason for Inclusion of the Strategy

Shelters do not have the resources to provide the mental health and chemical dependency assessments and case management needed to help individuals access treatment and permanent supported housing.  Providing these services will help individuals access housing and escape the cycle of chronic homelessness and repeated involvement in the criminal justice and emergency medical systems.

- C.	Service Components/Design

There are several strategies being considered, but a final service design is not being proposed at this time.  There are a number of programs targeting this homeless population that are being developed in the next year, and it is critical that these efforts be well-coordinated in order to reduce duplication of effort and to achieve the most efficient and effective results.  A major effort that is underway to serve homeless individuals who are frequently involved with the criminal justice and hospital emergency systems is the High Utilizer Referral System, with funding provided by the Veterans and Human Services Levy and the United Way Campaign to End Chronic Homelessness.  The Service Improvement Plan that is being developed this year includes a redesign of the Emergency Services Patrol and Dutch Shisler Sobering Center, increased outreach and service engagement for individuals with chemical dependency and improved coordination among key stakeholders to identify high utilizers of criminal justice and emergency medical services in order to facilitate placement into dedicated supported housing.  Below is an excerpt from the Veterans & Human Services Levy Service Improvement Plan 2.1 (a-2) that describes the intent of the plan:

“This procurement plan is the third in a series of three that address this objective. The first, a procurement plan to enhance outreach and engagement of homeless people in South King County was approved in 2007 (SIP 2.1(b)). The second procurement plan, approved in March 2008, calls for development of a county-wide database that will identify high utilizers of public safety and emergency medical systems. The database will ultimately facilitate coordinated entry into existing and new housing, services and supports, and is a tool that will be used by the staff and programs to implement the strategies described in this procurement plan.

This third plan describes a set of proposed investments that will improve coordination of homeless outreach, engagement, and entry into treatment and housing for a subset of homeless single adults in Seattle, as described on page 19 of the Service Improvement Plan.

In this Procurement Plan, we first describe a group of current services that target homeless people with substance abuse problems – the King County Emergency Service Patrol or ESP, which picks up intoxicated people off the streets; the Dutch Shisler Sobering Support Center, which provides a safe place to sleep off the effects of intoxication; REACH Case Management, an intensive case management service provided to the most frequent users of the Sobering service; and the High Utilizer Group or HUG, that meets to conduct individual case planning for the most challenging clients.

While this redesign is somewhat complex, the Levy’s SIP called for strategies to “challenge existing fragmentation,” to “fill existing gaps in services and continuums of care” and to “build on existing successful programs or structures.”  This redesign meets all of these criteria.”

Since the final design for the high utilizer system has not yet been fully developed, we propose to use the funding dedicated to this strategy to fill any gaps identified in the high utilizer service system, once other programs dedicated to this target population are implemented.

- D.	Target Population

Homeless adults being discharged from jails, hospital emergency departments, crisis facilities and in-patient psychiatric and chemical dependency facilities.

- E.	Program Goal

Increase availability of outreach, engagement, and case management services for homeless individuals.

- F.	Outputs/Outcomes

1.	Linkage of individuals to needed community treatment and housing.

2.	Expected outcomes include reduced use of emergency medical services, reduced jail bookings, and increased number of people in shelters being placed in services and permanent supported housing.

2.	Funding Resources Needed and Spending Plan

To be determined

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers

To be determined

- B.	Staff Resource Develop Plan and Timeline

Still to be developed

Will depend on the model developed through the planning process

- C.	Partnership/Linkages

Stakeholders include The Committee to End Homelessness in King County, The Veterans and Human Services Levy Boards, United Way of King County, shelter providers, jails, and hospitals throughout King County, the King County Department of Community and Human Services, and Public Health – Seattle and King County.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

To be determined

- B.	Procurement of Providers

Exact timeline to be determined

- C.	Contracting of Services

Exact timeline to be determined

- D.	Services Start Date(s)

To be determined

Strategy Title:	Increase Access to Community Mental Health and Substance Abuse Treatment

Strategy Title:	1c - Emergency Room Substance Abuse and Early Intervention Program

County Policy Goals Addressed:

- A reduction of the number of people with mental illness and chemical dependency using costly interventions like jail, emergency rooms and hospitals.

- A reduction of the incidence and severity of chemical dependency and mental and emotional disorders in youth and adults.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

Individuals who have abused alcohol and/or other drugs have an increased risk of being involved in automobile and other accidents, as well as a heightened risk for other health problems, which may lead to emergency room admissions.  Admissions to hospital emergency services may provide an opportunity to engage individuals who have abused substances into accepting the need for intervention and brief treatment, and prevent future alcohol and drug-related hospitalizations.  This strategy provides delivery of early intervention and treatment services to hospital emergency room patients who have substance use disorders or are at risk of developing these disorders.

- B.	Reason for Inclusion of the Strategy

The existing substance abuse intervention program at Harborview Medical Center already has a record of success and has demonstrated cost effectiveness with regard to reducing substance abuse and other health problems associated with drug use and reducing utilization of medical services. Patients who received services in this program at Harborview have altered their substance use patterns significantly.  Among substance abuses who received at lease a brief intervention, use reported in the six month follow-up interview declined significantly compared to use reported at screening.  The current program is funded by a federal grant which began in 2003 and will end in September 2008.  Implementation of this strategy will allow the continuation of the program at Harborview and expansion of the service to additional hospitals in south King County.  The program will reduce the number of individuals with substance abuse and dependency issues in hospital emergency rooms and increase access and referral to treatment.

- C.	Service Components/Design

The program is delivered by integrating chemical dependency professionals into the multidisciplinary team within emergency rooms.  Service design includes the following:

- Maximize the number of emergency room patients who are identified through screening to have substance abuse problems.

- Deliver brief counseling, or “brief interventions,” to patients who screen positive for substance use disorders.

- Increase referrals of chemically dependent people from the generalist medical setting to CD community treatment agencies.

- Reduce subsequent emergency room use rates, medical costs, criminal behavior, disability, and death for patients with alcohol and drug problems of all severity levels.

- Improve the links between the medical and chemical dependency treatment communities so that providing screenings and interventions for substance use disorders become routine.

- D.	Target Population

The program provides early intervention for at-risk substance users before more severe consequences occur, as well as intervention and referral for high utilizers of hospital emergecy room services.

Expansion to south King County hospital emergency departments was made at the request of the Washington State Hospital Association and as a result of an increase in low income and indigent clients in south King County.

- E.	Program Goals

Provide early intervention and referral to treatment for those with less severe addiction issues who are admitted to hospital emergency rooms in order to reduce the risk of more serious chemical dependency.

- F.	Outputs/Outcomes

3,488 new clients would be served each year in addition to the current number of clients served for a total capacity of 7,680 served annually.

Expected outcomes include reductions in emergency room visits, other medical costs, accidents, criminal behavior, and death.

2.	Funding Resources Needed and Spending Plan

The emergency room substance abuse and early intervention program will have an annual cost of $796,500.

| Dates | Activity | Funding |
| --- | --- | --- |
| Sept – Dec 2008 | Continue Harborview contract | $120,000 |
|  | Total Funds 2008 | $120,000 |
| Jan – Dec 2009 | Harborview | $442,500 |
| Jan – Dec 2009 | Expansion to south King County | $354,000 |
|  | Total Funds 2009 | $796,500 |
| 2010 and onward | Ongoing program cost | $796,500 |
| Ongoing Annual | Total Funds | $796,500 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers (and where possible FTE capacity added via this strategy)

This strategy will provide support for nine FTE Chemical Dependency Professionals (CDPs); five at Harborview Medical Center (existing staff) and four new FTE CDPs in south King County.

Although there is a statewide shortage of substance abuse professionals and recruiting can be a challenge, selected provider will have access to Chemical Dependency Professional Education and Training under MIDD strategy 1e.

- B.	Staff Resource Develop Plan and Timeline (e.g. training needs, etc.)

| Dates: | Activity: |
| --- | --- |
| Oct 1 – Dec 31,2008 | Funding to Harborview for existing program staff. |
| Oct 1– Dec 31, 2008 | Recruitment for south King County positions |
| January 1, 2009 | Services start in south King County |
| January 1, 2009 | Fully operating programs at all facilities |

- C.	Partnership/Linkages

MHCADSD will partner with Harborview Medical Center and south King County hospitals on this project.  South King County hospital locations will be identified in collaboration with the Washington State Association of Hospitals.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

The current contract with Harborview will be extended without interruption, pending final approval for spending authority by the King County Council prior to the end of federal funding on September 30, 2008.

Services in south King County will begin in January 2009.

- B.	Procurement of Providers

There is a current contract with Harborview for services, so an RFP is not required to continue services.  State law allows sales tax funds to be used to replace lost federal funding.

Procurement of providers for south King County will be determined in collaboration with the Washington State Association of Hospitals.  Procurement will occur Oct-Dec 2008.

- C.	Contracting of Services

Contract with Harborview will be amended effective October 1, 2008.

Contracts for south King County will be effective January 1, 2008.

- D.	Service Start Date(s)

Services at Harborview will start October 1, 2008.

Services at south King County hospitals will start January 2, 2009.

Strategy Title:	Increase Access to Community Mental Health and Substance Abuse Treatment

Strategy Title:	1d – Mental Health Crisis Next Day Appointments

County Policy Goal Addressed:

- A reduction of the number of people with mental illness and chemical dependency using costly interventions like jail, emergency rooms, and hospitals.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

Next day appointment (NDA) services are an existing service that provides follow up to a face-to-face crisis service with timely direct crisis intervention, resolution, referral, and follow-up services. This help is available for individuals who are in crisis but may not be eligible for or need ongoing services.  For those who do need ongoing services this can be a point of entry as long as the outpatient system has capacity [see strategy 1a (1)].  This service is used to divert costly inappropriate inpatient admissions.  Current funding provides only a limited amount of follow up stabilization service.

- B.	Reason for Inclusion of the Strategy

Expanded services will provide for increased stabilization and decreased inpatient utilization.  Services that reduce emergency room visits and inpatient admissions constitute better care and will result in savings to the system.  Access to ongoing mental health services following a crisis can result in more effective intervention with a person’s illness, more successful stabilizaton, and prevention of further deterioration of the person’s condition.  Crisis services contracts are already in place and expanded services could be provided immediately without a Request for Proposal (RFP) process.

- C.	Service Components/Design

Consumers in crisis will be seen for additional treatment and stabilization beyond the next day appointment.  Potential additional services could include:

  - Linkage to ongoing services as access is made more available through MIDD funding.

  - Completion of Medicaid application process.

  - Medication plan developed and linkage to primary care provider for those who are not enrolled for ongoing services.

  - Referrals to chemical dependency treatment.

The specific service components will be developed as part of a stakeholder process.

- D.	Target Population

Adults aged 18 years or older who are at risk for voluntary or involuntary inpatient psychiatric admission, are not enrolled in RSN outpatient services, and who are referred by the Crisis Clinic or the Designated Mental Health Professionals (DMHPs).  Crisis Clinic referrals include those persons seen in local emergency departments and it is determined that they can be safely stabilized in the community with appropriate and timely services, thereby averting an inpatient admission.

- E.	Program Goals

- Increase access to crisis stabilization services in order to reduce inpatient admissions.

- Provide early and timely intervention into a person’s mental illness in order to prevent further deterioration in the person’s condition.

- F.	Outputs/Outcomes

- 750 persons will receive expanded crisis stabilization services.

- An expected outcome is reduced admissions to hospital emergency rooms and inpatient units.

2.	Funding Resources Needed and Spending Plan

Detailed spending plan to be determined based on review of data submitted by current providers.

| Dates | Activity | Funding |
| --- | --- | --- |
| Sept - Dec 2008 | Implement expanded crisis services | $73,000 |
|  | Total Funds 2008 | $73,000 |
| Jan – Dec 2009 | Target of 750 NDA referrals to receive expanded services | $250,000 |
|  | Total Funds 2009 | $250,000 |
| Ongoing Annual | Total Funds | $250,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers (and where possible FTE capacity added via this strategy)

Five existing Adult Crisis Services providers serving all regions of King County.

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

| Dates: | Activity: |
| --- | --- |
| September – December 2008 | Staff retrained to new model |
| September 2008 – December 2009 | Increased prescriber capacity |
| September – December 2008 | Training for Crisis Clinic, Hospital ED Staff, DMHPs |

- C.	Partnership/Linkages

      - Stakeholders to develop service model details: Crisis and Commitment Services, Crisis Clinic/ hospital authorization staff, Harborview Psychiatric Emergency Services staff, mental health crisis providers, chemical dependency providers, Mental Health, Chemical Abuse and Dependency (MHCADSD) staff.

      - Partnerships with the five adult crisis services providers.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

Stakeholder process to develop program details: 	May-July 2008

Development of contract amendments: 			August 2008

Contract amendments in place:				September 15, 2008

- B.	Procurement of Providers

The mental health providers are currently under contract with the County, and no RFP is required under this expansion of services.

- C.	Contracting of Services

Contracts with current providers will be amended effective September 15, 2008.

- D.	Services Start date(s)

Services will begin September 15, 2008 or as soon as spending authority is approved by King County Council.

Strategy Title:	Increase Access to Community Mental Health and Substance Abuse Treatment

Strategy No:	1e – Chemical Dependency Professional Education and Training

County Policy Goals Addressed:

- A reduction of the number of people with mental illness and chemical dependency using costly interventions like jail, emergency rooms and hospitals.

- A reduction of the incidence and severity of chemical dependency and mental and emotional disorders in youth and adults.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

There is a significant shortage of chemical dependency professionals.  By 2010, the demand for addiction professionals and licensed treatment staff with graduate-level degrees is projected to increase by 35 percent.  This shortage limits access to treatment. The lack of certified chemical dependency professionals (CDPs) makes it challenging for King County substance abuse providers to meet their treatment expansion goals and to increase the number of clients admitted to and receiving needed substance abuse services.

- B.	Reason for Inclusion of the Strategy

A well trained and sufficient supply of substance abuse counselors means better access to and higher quality substance abuse treatment.  This funding will provide stipends to treatment agencies and additional workforce development activities to help support staff with the education and training needed to become CDPs.  Increasing the supply of CDPs will ensure that we have a sufficient and properly trained workforce in King County to increase the number of clients served.

- C.	Service Components/Design

Treatment agencies will be able to offer chemical dependency professional trainees (CDPTs) reimbursement for tuition and books for course work meeting the educational requirements to become a chemical dependency professional.  The requirements are 45 quarter hours or semester hours of course work specific to the assessment, treatment and case management of individuals with substance use disorders.  Courses may be taken at accredited community colleges, universities,

National Association of Alcoholism and Drug Abuse Counselors (NAADAC), and/or at all Association for Addiction Professionals approved education providers.  Individuals taking advantage of the tuition and books reimbursement will be asked to commit to staying at the treatment agency for one year post graduation.  Funds will also be used to pay for training needs of the workforce, cultural competency consultation, clinical supervision and additional workforce development activities.  Reimbursement for staff time to attend trainings and/or classes is not included in phase one implementation.  Reimbursement for this time may be considered in future workforce development strategies funded through this initiative.

- D.	Target Population

Individuals working at any King County contracted treatment agency who are in the process of becoming certified CDPs.

- E.	Program Goal

Increase the number of Chemical Dependency Professionals in King County, and increase their access to professional development and cultural competence consultation.

- F.	Outputs/Outcomes

- 45 CDPTs testing at each test cycle offered by the Washington State Department of Health;

- Up to 125 new certified chemical dependency professionals annually.

- An expected outcome of increasing the number of CDPs is that individuals will be able to access treatment sooner and more readily, and this will, in turn, reduce criminal justice involvement and admissions to emergency rooms and inpatient units.

2.	Funding Resources Needed and Spending Plan

| Dates | Activity | Funding |
| --- | --- | --- |
| July – Dec 2008 | Start-up (initial tuition reimbursement will begin after completion of first courses) | $160,000 |
|  | Total Funds 2008 | $160,000 |
| Jan – Dec 2009 | Continuing Tuition Reimbursement | $615,625 |
|  | Total Funds 2009 | $615,625 |
| 2010 and onward | Ongoing Continuing Tuition Reimbursement and additional workforce development activities |  |
| Ongoing Annual | Total Funds | $615,625 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers (and where possible FTE capacity added via this strategy)

| Dates: | Number of Treatment Providers: | Activity/Number of CDPTs enrolled: |
| --- | --- | --- |
| September 1 – December 31, 2008 | 32 | Tuition and books reimbursement begins/125 CPDTs enrolled for tuition reimbursement |
| 2009 and continuing | 32 | Tuition and books reimbursement continues/150 CPDTs enrolled for tuition reimbursement/ tests and CDP status awarded for 45 CDPTs |

- B.	Staff Resource Develop Plan and Timeline (e.g. training needs, etc.)

Current County contracted outpatient providers would be able access funding immediately and increase their pool of qualified CDPs.

- C.	Partnership/Linkages

Linkage with local community colleges, interested universities, and other appropriate entities, including Seattle Central Community College, Edmonds Community College, Highline Community College, Bellevue Community College, Tacoma Community College, University of Washington Extension, and National Association of Alcoholism and Drug Abuse Counselors (NAADAC) The Association of Addiction Professionals Approved Education Providers.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

| Dates: | Activity: |
| --- | --- |
| April – June 2008 | Meeting with local community colleges, universities and development of a list of other approved education providers who are able to meet the educational requirements to become a CDP. |
| May – June 2008 | Development of Contract Exhibit outlining tuition and books reimbursement for agencies. List of education resources provided to the agencies. |
| July – Sept 30 2008 | Contract Exhibits are signed by all parties and agencies are aware of how to bill for tuition and books reimbursement for staff who qualify. |
| August 1, 2008 | Training for Agencies related to contractual expectations for tuition and books reimbursement. |
| Oct – Dec 31, 2008 | Tuition and books reimbursement is made available for all CDPTs at King County contracted agencies. |
| 2009 and continuing | Contract Exhibit included in all contracts. Portions of the funds will be carved out for a Request for Proposals to interested community colleges, universities, and other appropriate entities to develop an institute of condensed classes for advanced degree clinicians. Additional workforce development activities will be added. |

- B.	Procurement of Providers

Providers are currently under contract with King County and contracts are managed by the Mental Health, Chemical Abuse and Dependency Services Division.  No additional procurement or recruitment of providers is planned.

- C.	Contracting of Services

May 2008 -- Contract Exhibit developed, reviewed and made available to review by contracted treatment agencies

June 2008 -- Contract Exhibit amended into current contracts

September 2008 – December 2008 -- Tuition reimbursement begins prior to the end of 2008.

January 1, 2009 -- Contract Exhibit included in all 2009 agency treatment agency contracts.

- D.	Services Start Date(s)

September 2008

Strategy Title:	Increased Access to Community Mental Health and Substance Abuse Treatment

Strategy No:	1f - Peer Support and Parent Partner Family Assistance

County Policy Goals Addressed:

- Diversion of youth and adults with mental illness and chemical dependency from initial or further justice system involvement.

- Explicit linkage with, and furthering the work of, other council directed efforts (the Recovery Plan for Mental Health Services).

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

Parents, family members and youth consumers of the public mental health, substance abuse and other service systems benefit from the unique mentoring, guidance and expertise offered by someone who has had similar experiences.  Navigating complex service systems can be a frustrating, confusing and challenging experience for consumers. Traditionally, systems fail to help consumers mitigate against these experiences. Parent partners/peers help families and youth to identify their needs, focus on strengths, develop and implement services and supports, and successfully partner with system professionals.  This type of support is currently only available to a limited number of families in King County; the vast majority of families who would benefit do not have access.

- B.	Reason for Inclusion of the Strategy

Parent partners/peers are an essential component of any progressive public system.  National research suggests that this approach is highly effective—both for the consumer and for the system.  Capacity to provide these supports is extremely limited in King County. Although the King County Mental Health, Chemical Abuse and Dependency Services Division (MHCADSD) developed some capacity to offer this type of assistance as a result of a federal System of Care grant, the grant funding ended in 2005, curtailing further growth and development.  MIDD funds will help to significantly expand the availability of this critical resource to consumers throughout the county.

- C.	Service Components/Design

MHCADSD will employ a full time Parent Partner Specialist to provide leadership in the development and coordination of a network of parent partner/youth peer support organizations.  In coordination with MHCADS, the organizations will provide peer support, technical assistance, mentoring, training, networking opportunities and resources to families and youth in the target population.

- D.	Target Population

1.	Families whose children and/or youth currently receive services from the public mental health and substance abuse treatment systems, the child welfare system, the juvenile justice system and/or special education programs, and who have requested assistance to successfully access services and supports for their children/youth.

2.	Youth who currently receive services from the public mental health and substance abuse treatment systems, the child welfare system, the juvenile justice system and/or special education programs, and who have requested assistance to successfully access services and supports.

- E.	Program Goals

To empower families and youth by assisting them to:

1.	Increase their knowledge and expertise.

2.	Utilize effective coping skills and strategies to support children/youth.

3.	Effectively navigate complex service system(s).

- F.	Outputs/Outcomes

1.	Parent Partner Specialist is hired; permanent fulltime staff resource is available at MHCADSD.

2.	Increase in the number of families and youth receiving parent partner/peer support services (up to 4000/year).

3.	Increase in the number of parent partner/peer support services provided.

4.	Increase in the number of parent/youth engaged in networks of support.

5.	Increase in the number of training/education services available annually.

2.	Funding Resources Needed and Spending Plan

This program needs $450,000 per year to develop and sustain the MHCADS leadership position and to contract with and sustain a network of parent and youth peer organizations to serve all of King County.

| Dates | Activity | Funding |
| --- | --- | --- |
| July – Dec 2008 | Start-up (Hire and train MHCADS staff; development of program design, including recruitment strategies; RFP development) | $75,000 |
|  | Total Funds 2008 | $75,000 |
| Jan – Dec 2009 | Phased in procurement, selection, contracting, recruitment and training of parent partner and youth peer organizations | $450,000 |
|  | Total Funds 2009 | $450,000 |
| 2010 and onward | County-wide network of parent partner and youth peer organizations is in place; ongoing training, support and program evaluation | $450,000 |
| Ongoing Annual | Total Funds | $450,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers (and where possible FTE capacity added via this strategy)

This funding level supports a full-time Parent Partner Specialist at MHCADS ($50,000 at 2008 county rates) and up to 40 part-time parent partners/youth peers in several organizations at a total projected cost of $400,000 per year.  Parent partners/youth peer support services may be provided by free standing parent/peer run organizations and/or by community mental health centers. The number of parent partners and youth peers ultimately needed to fully implement this program county-wide is not currently available, therefore a phased-in implementation plan is required.  Potential providers may be new or existing family organizations; including freestanding organizations or those attached to community mental health agencies.

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

| Dates: | Activity: |
| --- | --- |
| Sept 1– Dec 30, 2008 | Hire and train MHCADS Parent Partner Specialist. Research & evaluate existing program models and best practices in King County, Washington State and nationally to inform program design. |
| Jan – Dec 2009 | Development and implementation of training and technical assistance plan to support parent partner and youth peer organizational development and sustainability. Services will be initiated in a phased manner as capacity is developed and ready. |
| 2010 and ongoing | Program evaluation and modifications will help determine ongoing training and technical assistance needs. Ongoing training and technical assistance is implemented to assure program achieves goal(s). |

- C.	Partnership/Linkages

MHCADS and its contracted parent partner and youth peer organizations will maintain close partnerships with national and state parent and youth peer organizations, and with local systems, including mental health and substance abuse treatment providers, child welfare, juvenile justice, schools and other stakeholders.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

- MHCADS staff person recruited and hired by September 1, 2008.

- Program design planning will be substantially completed by December 31, 2008.

- The Request for Proposals (RFP) for the procurement of parent and youth organizations will be developed by January 30, 2009.

- First organizations will start-up no later than July 1, 2009.

- B.	Procurement of Providers

- The RFP for parent and youth organizations will be released by February 15, 2009.

- The response date will be March 31, 2009.

- The awards for accepted bids will be made April 15, 2009.

- C.	Contracting of Services

Contracts for parent and youth organizations will start on May 15, 2009.

- D.	Services Start date(s)

Services to families and youth will begin July 1, 2009.

Strategy Title:	Increase Access to Community Mental Health and Substance Abuse Treatment

Strategy No:	1g – Prevention and Early Intervention Mental Health and Substance Abuse Services for Older Adults

County Policy Goals Addressed:

- A reduction in the incidence and severity of chemical dependency and mental and emotional disorders in youth and adults.

  - A reduction of the number of people with mental illness and chemical dependency using costly interventions such as jail, emergency rooms and hospitals.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

Undiagnosed and untreated depression and drug and alcohol abuse are contributing factors to high suicide rates for older men and women.  A recent report of the Surgeon General cites depression symptom prevalence estimates of 17% to 35% in older adult primary care patients.

- B.	Reason for Inclusion of the Strategy

In 2007, King County Health Centers served an estimated 20,000 low income adults over 55 years of age.  In recent studies among those 55 years and older who have completed suicide, 77% had contact with a primary care provider within a year of their suicide and 58% had contact with the primary care provider within a month of their suicide.  These studies suggest that identifying and treating high risk older adults in health centers is an effective strategy.

- C.	Service Components/Design

Mental health/chemical dependency staff will be integrated into the staffing of primary care teams in the safety net clinics.  (Safety net clinics include community health centers, public health centers, and Harborview primary care clinics.  These clinics work closely with community centers and senior centers in many suburban communities, and a number of clinics are piloting new outreach and integrated service strategies to serve older adults under a state grant to King County Care Partners through Senior Services.)

Mental health/chemical dependency staff will screen older adults for depression and/or drug or alcohol abuse.  Brief interventions and treatment will be initiated in primary care. Adults with more severe or complex needs that cannot be adequately treated in primary care will be referred to mental health and chemical dependency treatment agencies already under contract with Mental Health, Chemical Abuse and Dependency Services Division.

Mental health and chemical dependency providers integrated in primary care will also be responsible for coordinating referrals to MHCADSD contracting agencies, facilitating communication between primary care teams and mental health/chemical dependency treatment providers, and assuring that treatment plans are coordinated.

- D.	Target Population

Adults age 55 years and older seen in primary care clinics who are low income and/or otherwise have no medical health insurance.

- E.	Program Goal

Provide screening and treatment for depression and for prescription or illegal drug or alcohol abuse in older adults who are seen in primary care clinics.

- F.	Outputs/Outcomes

A reduction of the number of people with mental illness and chemical dependency using costly interventions such as jail, emergency rooms and hospitals.  Screening and appropriate interventions will occur for 2,500 to 4,000 individuals annually.

Expected outcomes include reductions in suicides, alcohol and drug abuse among older low income adults in King County.  Additionally reductions are expected in health care costs because older adult patients with depression visit doctors and emergency rooms more often, use more medications, and incur higher inpatient charges than those who are not depressed.

2.	Funding Resources Needed and Spending Plan

The mental health and substance abuse service enhancement for safety net primary care clinics will have an annual cost of $500,000.

| Dates | Activity | Funding |
| --- | --- | --- |
| Sept – Dec 2008 | Start-up (staff hiring and training) | $150,000 |
|  | Total Funds 2008 | $150,000 |
| Jan – Mar 2009 | Continued start-up | $250,000 |
| Jan – Dec 2009 | Phasing in ongoing services | $250,000 |
|  | Total Funds 2009 | $500,000 |
| 2010 and onward | Ongoing safety net clinic Services with enhanced mental health and substance abuse services | $500,000 |
| Ongoing Annual | Total Funds | $500,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number Type of Providers

Mental health providers in safety net clinics include psychologists, MSWs, and RNs or ARNPs with specialized psychiatric training.  Many clinics would like to include chemical dependency providers on their primary care team, but the shortage in trained chemical dependency providers has generally not made that feasible.

The equivalent of 10.0 FTE mental health providers will be added to clinic staff. Resources will be spread among 15 or more clinics so as to include those clinics that serve significant populations of older low income adults.

- B.	Staff Resource Develop Plan and Timeline (e.g. training needs, etc.)

| Dates: | Activity: |
| --- | --- |
| Sept 15 – Nov 30, 2008 | Treatment providers hire staff |
| Sept 15, 2008 – Mar 30, 2009 | Start up activities |
| Oct 1, 2008 | Training for primary care related to ongoing services |
| Nov 1, 2008 | Services start in those clinics where capacity is developed and ready |
| June 1, 2009 | Fully operating programs |

- C.	Partnership/Linkages

The clinics will need to develop and maintain referral relationships with mental health and drug and alcohol treatment providers to assure appropriate treatment for those individuals whose treatment needs cannot be managed in primary care.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

As this is an addition to existing programs the planning is substantially complete; refinements to the plan will be completed by July 2008.

- B.	Procurement of Providers

The providers are currently under contract with the County.

- C.	Contracting of Services

Contracts amendments will be in place by August 30, 2008.

- D.	Services Start date(s)

Services will begin no later than November 1, 2008.

Strategy Title:	Increase Access to Community Mental Health and Substance Abuse Treatment

Strategy No:	1h – Expand the Availability of Crisis Intervention and Linkage to On-Going Services for Older Adults

County Policy Goal Addressed:

- A reduction of the number of people with mental illness and chemical dependency using costly interventions like jail, emergency rooms and hospitals.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

Home-based age-appropriate outreach and intervention services for older adults with mental health and/or substance abuse issues are insufficient to meet the need.  Older adults are under represented in the mental health and substance abuse treatment systems in King County.  While the number of those 55 and older is 22% of the King County population, only 7% of clients in substance abuse treatment and 15% of those in mental health programs receive services.  The Geriatric Crisis Services program currently has three FTE that serve 200 clients per year.  The program turns away at least three referrals a week.  Additionally, the Seattle Police indicated that they would likely refer 1-3 individuals per week to this program from the Crisis and Hostage Negotiation team.

- B.	Reason for Inclusion of the Strategy

As our population ages, the number of older adults who experience a crisis in which mental health and/or alcohol and other drugs is a contributing factor is increasing.  Family members, unsure of who to contact, resort to calling the police or other first responders.  This team will provide relief to police and other emergency responders and divert unnecessary jail bookings and hospitalizations.

- C.	Service Components/Design

Geriatric Crisis Services is a specialized outreach crisis intervention and stabilization service available to older adults in King County. A multidisciplinary team of geriatric specialists will respond to police and other first responders, professionals, relatives and others in the community for outreach and assessments of older adults who are experiencing crises related to mental illness and substance abuse.  Services provided include comprehensive assessments at the client’s residence as well as crisis intervention and stabilization with prompt referral and linkage to mental health, chemical dependency, aging, and health care providers in the community.  The team also provides consultation, care planning, and education for professionals, families, and other care providers.

The program is not designed as a 24 hour per day service.  The team works during typical business hours and the Crisis Clinic provides after hours telephone coverage.  The crisis team staff doesn’t carry caseloads because they are specialty crisis workers.  They assess and link people to follow-up services.  The average length of stay in the program is 23 days.  The staff’s job is to perform a comprehensive assessment (mental health, substance use, physical assessment, social, environmental, etc.) of the client, stabilize the client and link the client to mental health, substance abuse, aging, and health care providers.  The amount of time spent in each episode of intervention can be quite variable depending on the client’s situation and level of cooperation.  The clinicians intensely work on stabilizing multiple clients at one time.

Currently the team’s response time is up to three working days.  The MIDD funding will allow the program to decrease the response time and expand the services for first responders (police, fire, EMTs) and the Designated Mental Health Professionals (DMHP).  The program will be able to respond within 24 working hours.  In addition the program will be available to provide on demand telephone consultation.

One of the primary tasks of the program is the linkage of clients to medical care.  It is not uncommon for a client to not have seen a physician in many years.  In addition, there is a psychiatrist on the team who consults in person with the staff weekly, is available for phone for consultation and is also available to perform weekly home visits.  Our proposal also adds a .6 RN to perform medical assessments.

- D.	Target Population

Individuals age 55+ residing in King County at risk of or experiencing a crisis in which mental health or alcohol and/or other drugs are a likely contributing factor and/or exacerbating the situation.

- E.	Program Goal

Build capacity in the community to provide prevention and treatment services to the older adult population, establish a solid evidenced-based crisis team, and increase the number of older adults accessing treatment services.

- F.	Outputs/Outcomes

The program currently serves 200 people per year.  With the additional staff resources the program will serve an additional 340 new clients served each year for a total of 540 people per year served.  Expected outcomes will include an increase in engagement of older adults in ongoing mental health and chemical dependency treatment and a reduction in the use of emergency medical services by these individuals.

2.	Funding Resources Needed and Spending Plan

| Dates | Activity | Funding |
| --- | --- | --- |
| Sept-Dec 2008 | Start-up (hire and train staff) | $87,500 |
| Jan-Dec 2009 | Full implementation | $350,000 |
| 2010 Onward | Ongoing program cost | $350,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers (and where possible FTE capacity added via this strategy)

1 FTE Master’s level social worker/mental health therapist

1 FTE Chemical Dependency Professional

1 FTE Chemical Dependency Professional Trainee

.6 FTE Nurse

- B.	Staff Resource Develop Plan and Timeline (e.g. training needs, etc.)

Two-day agency orientation and six weeks of team orientation.  Team orientation includes policy and procedure manual orientation, office procedures, developing knowledge of the services of other teams.  New team members function independently after six weeks.

Timeline:

| Dates: | Activity: |
| --- | --- |
| Sept – Oct 2008 | Provider hires program staff. |
| Sept 2008 – Dec. 15, 2008 | Training of new staff. Training takes about six weeks. |
| Oct 1, 2008 – Dec 1, 2008 | Training and networking with community stakeholders such as the police department and community emergency rooms and other first responders. |
| Dec 1, 2008 | Services start. |
| Feb 1, 2009 | Agency has reached full operating capacity. |

- C.	Partnership/Linkages

Ongoing partnerships with the substance abuse and mental health provider network.  Partnership with jails, police, Crisis Clinic, 24-Hour Helpline, National Alliance on Mental Illness (NAMI), and others who refer and/or work with the target population.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

- Program planning will be completed by June 2008.

- Contract amendment language will be completed for Evergreen Health Services by July 30, 2008.

- Program will start on December 1, 2008.

- B.	Procurement of Providers

Evergreen Community Health Care will provide the service, no Requests For Proposals will be issued. Services will be amended as an exhibit to the provider’s existing contract.

- C.	Contracting of Services

The contract will start September 2008.

- D.	Services Start date(s)

Services to consumers will start December 1, 2008

Strategy Title:	Improve Quality of Care

Strategy No:	2a - Caseload Reduction for Mental Health

County Policy Goal Addressed:

- A reduction of the number of people with mental illness and chemical dependency using costly interventions like jail, emergency rooms and hospitals.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

As a result of state mental health funding allocation decisions,  the funding King County Regional Support Network  (RSNs are counties and groups of counties that manage publicly funded mental health services through contracts with the state) receives for mental health services have not kept up with the increased costs of providing those services.  This has led to increases in the size of community mental health center case loads over the years, compromising quality of care and negatively impacting the system’s ability to hire and retain staff.

Large case load sizes negatively impact a case manager’s ability to maintain regular contact with consumers.  Regular contact allows the case manager to: assist consumers in developing their own illness management strategies; provide

psycho-education; provide motivational interviewing for pursuing supported employment services; monitor fluctuations in symptoms so that medication adjustments can be recommended; and provide other treatment services that contribute to consumers’ stability and recovery.  With very large case loads, case managers are limited in their ability to provide routine rehabilitation services and instead primarily respond to crises.

- B.	Reason for Inclusion of the Strategy

Dedicated funding to enable agencies to add additional staff and reduce case load sizes would have a substantial benefit for those being being served as well as for those providing the services.  Decreased case loads would enable case managers to respond more quickly when their clients are in crisis.  Clients could be seen sooner after being discharged from jails or hospitals.  More time could be spent with clients to meet their goals and to provide the supports they need.  This strategy is consistent with the goal of reducing the number of people with mental illness who use more costly interventions such as jails, emergency rooms, and inpatient care.

- C.	Service Components/Design

Case management services may be provided in different ways and by varied staff across the network of RSN contracted mental health providers.  Services such as money management, helping individuals shop for food or take care of their

apartments, medication management, vocational services, and education may be provided by mental health case managers, peer counselors, vocational specialists, or financial workers, depending on the agency.  Additional funding will be provided to decrease outpatient caseloads at community mental health agencies, across the system.  Planning is still taking place to determine how to take into account the variation across the system in how, and by whom, case management services are provided.  Among the variables are the following:

- Variation in case load sizes that are reported to be from 20 or 25 to as large as 80 clients per case load

- Case mix-- the relative severity of consumers’ illnesses within and across caseloads

- Different models for providing services (for example, if one agency has a vocational specialist providing vocational services and another has the case manager provide that service, the responsibilities and workloads for the case managers are different, and case load size could be adjusted accordingly)

- Some agencies pay higher salaries and may have higher caseloads, while others have kept lower caseloads, but pay lower salaries.

There will need to be ongoing discussions with stakeholders to determine the best way to achieve the goals of this strategy, including determining how case management caseloads will be measured, and which staff providing which services should be considered in determining case loads.

- D.	Target Population

Children, youth, adults, and older adults receiving outpatient services through the King County Regional Support Network.

- E.	Program  Goals

  - Lower outpatient mental health case loads to allow case managers to see consumers more regularly to assist them to achieve greater stability and recovery, and to be more responsive to consumers who are in crisis, particularly those who are in, and exiting from, jails and hospitals.

  - Decreased case manager turnover due to high caseloads, which will lead to a more stable and effective work force as well as savings related to training and orientation of new staff.

- F.	Outputs/ Outcomes

- Addition of up to 110 new staff, including peer counselors, mental health professionals, and supervisors.

- Reduction of system-average case loads by a percentage yet to be determined.  (Original calculations on the estimated percentage decrease did not include some variables identified in discussions with mental health providers, such as supervisory positions needed to support new case managers and additional space requirements).

- The expected outcomes of lower caseloads are reductions in emergency room utilization, hospital admissions, criminal and juvenile justice involvement, and prevention of out of home placement for children.

2.	Funding Resources Needed and Spending Plan

| Dates | Activity | Funding |
| --- | --- | --- |
| Sept- Dec 2008 | Provide funds to contracted mental health agencies to begin hiring additional case managers. | $1,750,000 |
|  | Total Funds 2008 | $1,750,000 |
| Jan – Dec 2009 | Continue ramp-up of staff, complete by end of year. $3,500,000 will be MIDD funds and $1,500,000 will be additional federal matching funds. | $5,000,000 |
|  | Total Funds 2009 | $5,000,000 |
| Ongoing Annual | Total Funds | $7,000,000 |

Ongoing total funding assumes additional federal matching funds.  MIDD Action Plan funds will be $4 million, and federal match will be $3 million.

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers (and where possible FTE capacity added via this strategy)

- 16 RSN mental health outpatient providers and subcontracted youth service providers.

- As many as 110 new case managers and supervisors added.

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

Supervisor training for staff moving into new role:  Ongoing while staffing increases are underway.

- C.	Partnership/Linkages

RSN Mental Health Provider agencies and subcontracted agencies.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

- Stakeholder Process to develop implementation strategy:	May-July 2008

- Contracts amended:						August 2008

- Agencies begin hiring process:				September 2008

- Case load reduction completed:				December 2009

- B.	Procurement of Providers

Proposed timelines	Not Applicable

- C.	Contracting of Services

Existing contracts amended:	August, 2008

- D.	Services State Date(s)	September 15, 2008

Strategy Title:	Improve Quality of Care

Strategy No:	2b – Employment Services for Individuals with Mental Illness and Chemical Dependency

County Policy Goal Addressed:

- Explicit linkage with, and furthering the work of, other council directed efforts including the Adult and Juvenile Operational Master Plans, the Ten Year Plan to End Homelessness in King County, the Veterans and Human Services Levy Service Improvement Plan and the Recovery Plan for Mental Health Services.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

Employment is an essential element in recovery-based systems of care and moving individuals towards self-sufficiency.  Currently less than ten percent of individuals enrolled in outpatient mental health services are employed.  In the chemical dependency treatment system only 25% of the individuals in statewide treatment programs are employed.  For the individuals in King County treatment programs only 16% are employed.

- B.	Reason for Inclusion of the Strategy

Currently there are no specialized vocational resources in the chemical dependency treatment provider community and very limited resources in the mental health treatment community to address the needs of individuals receiving treatment services who need assistance and support to find and retain a competitive job.

- C.	Service Components/Design

The mental health and chemical dependency treatment provider community will provide fidelity-based (adheres to an evidenced-based service model)  supported employment services including: trial work experiences, job placement, on the job intensive training supports, and job retention services for individuals who are receiving treatment services for mental health and/or chemical dependency.  Additionally, consumers will receive benefits counseling and extended supports to foster long-term job retention.  Outreach and education to participants concerned about how getting a job will affect eligibility for public resources will also occur.

- D.	Target Population

Persons who are currently receiving services under the public mental health or the public chemical dependency treatment system in King County who need supported employment services to obtain competitive employment.

- E.	Program Goal

Provide evidence-based supported employment services to individuals in King County who are in mental health and/or chemical dependency treatment programs in order to help individuals obtain jobs and further their recovery and self-sufficiency.

- F.	Outputs/Outcomes

- The program is projected to serve 920 individuals annually.

- Individuals will receive, on average, six months of ongoing employment placement and retention services.

- The expected outcomes of providing employment services include an increase in the employment rates, improved housing stability, and decreased reliance on public assistance for those individuals receiving services.

2.	Funding Resources Needed and Spending Plan

The original proposal for the project indicated a need $1.5 million to increase the employment services staffing capacity within the treatment provider community.  There is a need for an additional $600,000 to support the existing employment programs in the mental health system due to a budget cut in federal Medicaid related directly to employment services that is occurring in July 2008.  The total funds needed for this strategy are $2.1 million.

The spending plan is as follows:

| Dates | Activity | Funding |
| --- | --- | --- |
| Sept – Dec 2008 | Start-up (staff hiring and training) All FTEs will be contracted out to providers | $350,000 |
|  | Total Funds 2008 | $350,000 |
| Jan – Mar 2009 | Continued Start-up | $250,000 |
| Jan – Dec 2009 | Phasing in Ongoing Supported Employment Services | $1,350,000 |
|  | Total Funds 2009 | $1,600,000 |
| 2010 and onward | Ongoing Supported Employment Services | $2,100,000 |
| Ongoing Annual | Total Funds | $2,100,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers (and where possible FTE capacity added via this strategy)

This funding level provides for the addition of up to 23 vocational specialists within the contracted King County mental health and substance abuse treatment provider community.

- B.	Staff Resource Develop Plan and Timeline (e.g. training needs, etc.)

| Dates: | Activity: |
| --- | --- |
| Sept 15 – Nov 30, 2008 | Treatment providers begin to hire vocational staff. It may take over one year for providers to recruit and train the full complement of vocational staff called for in this strategy. |
| Sept 15, 2008 – Mar 30, 2009 | Vocational specialists require training that occurs both on the job and through university based programs. The training can take from 3 – 6 months. |
| Oct 1, 2008 | Training for Agencies related to contractual expectations for ongoing services and any expectations for the partnership with the Division of Vocational Rehabilitation. |
| Nov 1, 2008 | Services start in those Agencies where capacity is developed and ready. |
| June 1, 2009 | Fidelity measurement of the fully operating Supported Employment Programs. |

- C.	Partnership/Linkages

King County MHCADSD and the providers will need to continue to maintain significant partnerships with the Division of Vocational Rehabilitation (DVR) and the local Community Service Offices (CSO) that manage financial benefits and entitlements.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

Program design planning will be substantially completed by June 30, 2008.

The mental health treatment system already has a cadre of treatment providers that provide employment services.  Therefore the County is able to amend existing contracts to expand service capacity in existing employment services programs.  Currently the chemical dependency treatment system does not have employment services operating in any of its treatment programs.  The County will develop a Request for Proposal process to recruit for treatment providers who are willing and able to add employment services to their treatment programs.

The Request for Proposals (RFP) for the procurement of the Chemical Dependency providers will be developed by July 2008.

Contract amendment language for the mental health vocational provider agencies will be developed and transmitted to the providers by July 31, 2008.

Vocational programs will start-up during the 4th calendar quarter of 2008.

- B.	Procurement of Providers

The RFP for CD providers will be released August 2008.

The response date will be September 2008.

The awards for accepted bids will be in September 2008.

- C.	Contracting of Services

Contracts for MH providers and CD providers will start in October 2008.

- D.	Services Start date(s)

Limited services to consumers will begin November 1, 2008.

Strategy Title:	Increase Access to Housing

Strategy No:	3a - Supportive Services for Housing Projects

County Policy Goals Addressed:

- A reduction of the number of people with mental illness and chemical dependency using costly interventions like jail, emergency rooms and hospitals.

- Explicit linkage with, and furthering of, other council directed efforts, including the Adult and Juvenile Justice Operational Master Plans, the Ten-Year Plan to End Homelessness in King County, the Veterans and Human Services Levy Service Improvement Plan and the Recovery Plan for Mental Health Services.

- A reduction of the number of people who cycle through the jail, returning repeatedly as a result of their mental illness or chemical dependency.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

Housing providers often do not have adequate on-site staff resources to provide hands on assistance to homeless persons to help them transition to housing stability. Many housing projects are under funded for supportive housing services. Persons who are homeless need to relearn the skills needed to maintain a residence and meet the obligations of tenancy.

- B.	Reason for Inclusion of the Strategy

With on-site supportive housing services, individuals will receive the assistance they need to be successful in their housing environment and will be less likely to return to homelessness.  Housing providers will be able to accept homeless individuals that they had previously turned down due to inadequate available housing supports/services.  Lack of on-site services and responsiveness by case management staff	when a tenant has a crisis are often cited by landlords as the primary reasons for not dedicating housing to persons who are homeless and have a disability.

- C.	Service Components/Design

The treatment provider community will provide supportive housing services to assist individuals to transition from homelessness to housing stability.  Services will be provided primarily at the individual’s housing site and in the surrounding community by housing support specialists.

Services will include assistance to help the individual meet the obligations of his/her tenancy, i.e. rent payments, abide by landlord rules, cooperate with neighbors, keep

apartment clean and safe; assistance with learning the daily living skills to live independently, i.e. shopping, cooking, budgeting, cleaning; coordination with mental health and/or chemical dependency treatment providers and healthcare providers; and helping individuals get to medical appointments.

- D.	Target Population

Persons in the public mental health treatment system and chemical dependency treatment system who are homeless; have not been able to attain housing stability; are exiting jails and hospitals; or have been seen at a crisis diversion facility.

- E.	Program Goals

Increase the number of housed individuals with mental illness and chemical dependency who are receiving supportive housing services, leading to increased housing tenure and housing stability.  Housing stability has been shown to be a key determinant in increasing treatment participation and in reduced use of criminal justice and emergency medical systems.

- F.	Outputs/Outcomes

An estimated 400 individuals will be served.  The number of housing providers is yet to be determined.  Expected outcomes include increased housing stability and reduced use of criminal justice and emergency medical services.

2.	Funding Resources Needed and Spending Plan

| Dates | Activity | Funding |
| --- | --- | --- |
| July 2008 | Request For Proposal (RFP) issued |  |
| Aug 2008 | RFP selection process completed |  |
| Sept 2008 | Funds awarded to providers |  |
| Sept – Oct 2008 | Start-up (staff hiring and training) | $2,000,000 |
| Nov 2008 | Begin services to target population |  |
|  | Total Funds 2008 | $2,000,000 |
| Ongoing Annual | Total Funds | $2,000,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and Type of Providers (and where possible FTE capacity added via this strategy)

The number of providers is yet to be determined.  Those selected will be mental health treatment providers, chemical dependency treatment providers and affordable housing providers that currently serve the target population.

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

Current providers serving the target population and housing providers that will be applying for new capital projects will be identified through an RFP procurement process.

  - Housing support specialists will be added to mental health treatment providers and chemical dependency treatment providers in the Mental Health Chemical Abuse and Dependency Services Division (MHCADSD) network and to affordable housing providers (private non-profit) that house the target population.

  - A housing support specialist will have a caseload of 15 clients. The specialist will work with individuals primarily at the housing site, teaching daily living skills and helping the client achieve the obligations of tenancy and housing stability. The housing support specialist will also coordinate with the client’s treatment team and regularly communicate with the landlord.

  - Adding housing support specialists will allow providers to house individuals who have previously been turned down or have been unsuccessful in housing due to lack of stability and/or lack of daily living skills.

- C.	Partnership/Linkages

Mental health treatment providers, chemical dependency treatment providers and affordable housing providers that serve the target population, funders of housing development and services, and the Committee to End Homelessness in King County.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

Program design planning will be substantially completed by April 30, 2008

RFPs for the procurement of the MHCADSD providers and affordable housing providers will be developed by June 30, 2008.

New contracts with MHCADSD network providers and affordable housing providers will be developed and transmitted to the providers in September 2008.

Supportive housing teams/ programs will start-up during the 4th calendar quarter of 2008.

- B.	Procurement of Providers

The RFP for providers will be released July 1, 2008.

The response date will be July 30, 2008.

The awards of accepted bids will be in September 2008.

- C.	Contracting of Services

Contracts for MHCADSD providers and affordable housing providers will start in September 2008.

- D.	Services Start Date(s)

Services to consumers will begin in November 2008.

Programs Targeted to Help Youth

Strategies 4a – 9a

Strategy Title:	Invest in Prevention and Early Intervention

Strategy No:	4a - Comprehensive Chemical Dependency Outpatient Services to Parents In Recovery (Will be renamed: Services to Parents Participating in Substance Abuse Outpatient Treatment Programs)

County Policy Goal Addressed:

- A reduction of the incidence and severity of chemical dependency and mental and emotional disorders in youth and adults.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

Nationally, in 2001, ten percent of children aged five or younger have one or more parents abusing or dependent on alcohol or other drugs.   The nature of the addictive process focuses parental attention on the procurement, the use, and the experience of the alcohol/drugs.  This involvement interferes with and diminishes their ability to be attentive and appropriately responsive to their children’s emotional and physical needs. It also increases family isolation, and there is a tendency for children to assume the vacancy in the position of parent.  Because of the lack of appropriate parental behavior, observation and monitoring, children of substance abusers are more likely to exhibit developmental and behavioral challenges and are at higher risk of later developing problems with alcohol and other drugs as well as mental health problems.

While substance abuse treatment addresses the parent’s recovery from addiction, it does not directly address the impact of addiction on the children and family, nor deal with parenting as a specific issue with skill building, guided skill practice and targeted support.

- B.	Reason for Inclusion of the Strategy

In King County, in 2007, 25% of adults enrolled in outpatient substance abuse treatment had children under age 18 living with them.  By increasing their ability to attend to and care for their children’s health and well-being, effectively communicating with and actively structuring their children, and reducing family isolation, recovering parents will decrease risk factors while increasing protective factors and resiliency in their children.  Recovering parents who increase their skills and ability in parenting positively affect their children’s lives and assist their children in overcoming developmental issues.

- C.	Service Components/Design

These services will be provided to parents participating in county-funded outpatient substance abuse treatment programs that are selected in the Request For Qualifications (RFQ) process to be the contracted providers of this service.  The overall services include assessment of individual parent and family functioning and development of a service plan, parent education, parent support and supervised skill practice.

Once the assessment of parent/family functioning review is completed, a service plan is developed specific to this parent and family which includes group and individual parent education and support, and observed skill practice with their children so the parent(s) receives immediate in-the-moment coaching alternatives and affirmation.

The Family Coordinator will actively link parents and children as needed to developmental testing and treatment as well as therapeutic child care and other social services for children and youth of the parents in the treatment program. The children and family will be included in the services and/or events provided in MIDD Strategy 4b Prevention Services to Children of Substance Abusers.

- D.	Target Population

Custodial parents participating in outpatient substance abuse treatment programs selected in the RFQ process.

- E.	Program Goal

Increased family functioning and reduced potential for child neglect; reduced drug use by children of recovering parents.

- F.	Outputs/Outcomes

- 400 parents served annually

(Current data available does not tell us how many adults admitted to outpatient treatment have children living with them, but extrapolations from other data sets gives us an estimate of 700 parents with children at home who could benefit from this program.)

- Increased parent services at outpatient substance abuse treatment programs

- Increased family communication

- Increased positive family structure

- Increased parent skill in developmentally appropriate interactions with child

- Reduced substance abuse by children of recovering parents

2.	Funding Resources Needed and Spending Plan

The program needs $500,000 of MIDD funding per year to sustain.

| Dates | Activity | Funding |
| --- | --- | --- |
| April – October 2008 | Planning |  |
| October – December 2008 | Procurement; RFQ |  |
|  | Total Funds 2008 | $ 0 |
| January – March 2009 | Contracting |  |
| April – June 2009 | Staff hiring and training | $ 375,000 |
|  | Total Funds 2009 | $ 375,000 |
| Ongoing Annual | Total Funds | $ 500,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers (and where possible FTE capacity added via this strategy)

Opiate substitution treatment providers

Outpatient substance abuse treatment providers

2 FTE Family Coordinators

2 FTE Family Support Workers

3 FTE Families Facing the Future staff

- B.	Staff Resource Develop Plan and Timeline (e.g. training needs, etc.)

Training in the Family Support Model

Staff trained in Facing the Future curriculum and parent services model

- C.	Partnership/Linkages

Opiate substitution treatment providers

Outpatient substance abuse treatment providers

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

Project planning and RFQ development:  April – October 2008

- B.	Procurement of Providers

RFA released:  by October 1, 2008

RFA awarded:  by December 15, 2008

- C.	Contracting of Services

Contract signed by March 30, 2009

- D.	Services Start Date(s)

Services to parents start by June 30, 2009

Strategy Title:	Invest in Prevention and Early Intervention

Strategy No:	4b – Prevention Services to Children of Substance Abusers

County Policy Goals Addressed:

- A reduction of the incidence and severity of chemical dependency and mental and emotional disorders in youth and adults.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

Children of substance abusers (COSA) are more likely to exhibit problem behaviors and are at higher risk of later developing problems with alcohol and other drugs.  To decrease these risks and increase protective factors for healthy youth development, COSAs need coping skills and support from caring, trusting adults.  It is estimated that one in four children under the age of 18 lives in a home where alcoholism or alcohol abuse is prevalent.  Countless other children are exposed to illegal drug use in their families.  In King County, in 2007, 25% of adults enrolled in outpatient substance abuse treatment had children under age 18 living with them.

- B.	Reason for Inclusion of the Strategy

Evidence-based prevention programs have the potential to reduce future costs by preventing youth from becoming involved with the criminal justice system as well as the substance abuse treatment system.  Because they target youth and intervene prior to the development of substance use problems, alcohol and other drug prevention programs have the potential to create long-term cost savings including the prevention of long-term health issues.

- C.	Service Components/Design

This strategy expands upon evidenced based initiatives proven to work with this high risk population.  It is based upon principles of effectiveness for substance abuse prevention and is a proactive, family-based approach.

A major service component is the provision of educational/support groups for COSAs, using evidence-based programming such as the Celebrating Families!™ curriculum.  The National Association for Children of Alcoholics (NACoA) recently acquired Celebrating Families!™ and is disseminating the curriculum.  Celebrating Families!™ is a cognitive behavioral, support group model which has the goal: “ to

foster the development of whole, fulfilled, and addiction-free individuals and families by increasing resiliency factors and decreasing risk factors.”

Specifically, each series of the Celebrating Families!™ curriculum is comprised of 16 two-hour sessions.  A family meal precedes each session and then family members are separated by age group for the main, educational portion of the program.  Toward the end of each session, all the family members are brought back together to interact in healthy ways.

The Celebrating Families!™ curriculum builds a strong foundation; however, to adapt the program to local needs and to make the services more comprehensive, other components may be added including life-skills training, mentoring services, parent educational/support groups, and special drug prevention awareness events.

Through services contracted to a local provider(s) (which may include school organizations, community-based youth and family service agencies, and outpatient chemical dependency treatment agencies), activities would be presented multiple times in all five geographic regions of King County (east, south, north, central, and Vashon Island).

- D.	Target Population

The target populations are COSAs and their parents/guardians/kinship caregivers. Children will be identified from various referral sources including schools, community-based organizations, recreation and after-school programs, child welfare and the foster care system, juvenile justice as well as self-referrals.

- E.	Program Goal

Provide an evidence-based prevention program to children of substance abusers to reduce the risk of their developing substance abuse problems or chemical dependency.

- F.	Outputs/Outcomes

400 individuals served annually

Reduced substance abuse by COSAs

Improvement in health outcomes

Improvement in school attendance and performance

Reduction in juvenile justice involvement by COSAs

Improvement in individual and family functioning

2.	Funding Resources Needed and Spending Plan

| Dates | Activity | Funding |
| --- | --- | --- |
| Sept- December 2008 | Planning, procurement, and contracting |  |
|  | Total Funds 2008 | $ 0 |
| Jan – March 2009 | Hiring and training of Project Coordinator and Staff by provider(s) awarded under the RFQ process | $100,000 |
| April – December 2009 | Service provision | $300,000 |
|  | Total Funds 2009 | $ 400,000 |
| Ongoing Annual | Total Funds | $ 400,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and Type of Providers

One 0.75 FTE Contracted Project Coordinator

Five 0.5 FTE Contracted Project Staff

Provider(s) may include school organizations, community-based youth and family service agencies, alcohol and other drug prevention agencies, and outpatient chemical dependency treatment agencies

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

Project staff will need training and support in various curricula/programs, such as Celebrating Families!™, parenting, life skills, and mentoring.

Initial training of project staff shall be provided within two months of hire.  Ongoing training will be scheduled, as needed.

- C.	Partnership/Linkages

Partnerships and linkages will be between local, county, and state agencies and organizations which have access to COSAs and their families.  This may include but not be limited to:  King County Alcohol and Other Drug Prevention Program, King County Community Organizing Program, King County Youth and Family Services, King County Superior Court/Juvenile Services, local chemical dependency treatment agencies, alcohol and other drug prevention/intervention programs, Washington State Department of Social and Health Services’ Division of Children and Family Services, Treehouse, Casey Family Program, Puget Sound Educational Service District, King County Mentoring Roundtable, mental health treatment agencies.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

March 3, 2008 to May 30, 2008 (three months) -- Project planning

- B.	Procurement of Providers

June 2, 2008 to October 1, 2008 (five months) – Development/approval of competitive bid documents.  Request for Proposals (RFP) process

- C.	Contracting of Services

November 3, 2008 to December 31, 2008 (two months) – Contract development and processing

- D.	Services Start date(s)

April 1, 2009 – Services to youth and caregivers start

Strategy Title:	Invest in Prevention and Early Intervention

Strategy No:	4c – School District Based Mental Health and Substance Abuse Services

County Policy Goal Addressed:

- A reduction of the incidence and severity of chemical dependency and mental and emotional disorders in youth and adults.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

Mental health and substance abuse problems in children and youth interfere with their ability to learn, progress in school, and progress along a normal developmental course. A 2001 U.S. Surgeon General report stated that mental health is critical to a child’s learning and general health, and is as important as immunizations. Approximately 21% of children between the ages 9 and 17 have diagnosable emotional or behavior disorders, but fewer than a third receive help. This group of children have an increased risk for dropping out of school and not becoming fully contributing members of adult society. Their difficulties often are not recognized as mental health and/or substance abuse related.  They get left behind educationally and socially and can be labeled as difficult, which leads to further isolation from accurate problem identification and professional assistance.

Substance abuse can be linked to untreated mental illness as 43% of children who use mental health services also have a substance abuse disorder.    There is an increased risk for co-occurring disorders with students who smoke, drink or use other illicit drugs; substance abuse is associated with depression, anxiety disorder, attention deficit hyperactivity disorder, conduct disorder and eating disorders.  Children with mental disorders, particularly depression, are at a higher risk for suicide; an estimated 90% of children who commit suicide have a mental disorder.

Youth who fail at school are much more likely to end up on public assistance and involved in the criminal justice system. According to one study, 66% of boys and almost 75% of girls in juvenile detention have at least one mental disorder.  A 2005

report from the Civil Rights Project at Harvard University says failure to graduate from high school triples the likelihood of going to jail.

Without proper care their problems and challenges compound so that when professional care is offered the mental illness and substance abuse has progressed to the point that their needs are much more complex.

- B.	Reason for Inclusion of the Strategy

Schools provide an early opportunity to identify children and youth with mental health and substance abuse problems.  School based programs have been shown to improve mental health, and improve educational outcomes and school success.

- C.	Service Components/Design

Due to the complex nature of the project, the number of potential partners and the implementation development timeline, the service design work for this strategy has not been completed.  Services design will be defined with local partners with services delivery to begin with 2009/2010 school year.

- D.	Target Population

Children and youth enrolled in King County schools who are at risk for future school drop out.

- E.	Program Goal

To reduce the risk of students developing mental or emotional illness, or using drugs/alcohol.

- F.	Outputs/Outcomes

Up to 19 competitive grant awards to schools, school districts, or community-based organizations in partnership to provide a continuum of mental health and substance abuse services in schools, with a focus on those youth identified as most at risk for dropping out of school and becoming involved in the juvenile justice system.

Using an existing model of in-school services in the Seattle school-based health centers, it is estimated that each school-based counselor would provide therapeutic interventions with five students per school day, in addition to providing facilitation of group activities and school-wide initiatives including population-based mental health preventive and mental health promotion strategies.  Counselors would coordinate with MIDD Strategy 4d School Based Suicide Prevention activities and programs, therefore counselors may also be deployed to other schools in their district to assist in the event of a significant event or tragedy such as the suicide, death, or serious assault of a student, teacher, or other school staff.

Expected outcomes:

  - Reduced risk of students developing mental and emotional illnesses and abusing drugs and alcohol.

  - Improved school performance and reduced involvement in juvenile justice and emergency medical systems.

2.	Funding Resources Needed and Spending Plan

The program needs $1,235,306 of MIDD fund per year to sustain.

| Dates | Activity | Funding |
| --- | --- | --- |
| April-December 2008 | Stakeholder planning process | $0 |
|  | Total Funds 2008 | $0 |
| January-June 2009 | Complete planning, develop and issue Request for Proposals (RFPs) | $0 |
| June-August 2009 | Select recipients, complete contracts, staff hired | $125,000 |
| September-December 2009 | Services begin | $400,000 |
|  | Total Funds 2009 | $ 525,000 |
| 2010 | Services fully operational | $1,235,000 |
| Ongoing Annual | Total Funds | $1,235,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers (and where possible FTE capacity added via this strategy)

To be determined through the planning process.

- B.	Staff Resource Develop Plan and Timeline (e.g. training needs, etc.)

To be determined through the planning process.

| Dates: | Activity: |
| --- | --- |
| April – December 2008 | Planning Process |
| June – August 2009 | Staff Training |

- C.	Partnership/Linkages

Public Health; Community Services Division; King County Systems Integration Initiative, school-based health clinics; local schools and school districts, education services districts, mental health providers serving children of active duty military

personnel, and other community providers.  Linkage to MIDD strategy 4d School Based Suicide Prevention.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

To be determined in the planning process

- B.	Procurement of Providers

May-June 2009

- C.	Contracting of Services

August 2009

- D.	Services Start Date(s)

School year 2009-2010

Strategy Title:	Invest in Prevention and Early Intervention

Strategy No:	4d – School Based Suicide Prevention

County Policy Goals Addressed:

- A reduction of the incidence and severity of chemical dependency and mental and emotional disorders in youth and adults.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

Suicide is the second leading cause of death for Washington youth ages 15-24.

Between 2000 - 2004, 117 youth in King County died by suicide.  In this same period, there were 1,024 hospitalizations of King County youth because of suicidal attempts.  Among 10th grade students in King County who responded to the 2006 Healthy Youth Survey, 13 percent reported seriously considering suicide and almost 10 percent reported making a plan within the past 12 months for committing suicide.  Between three and four percent reported attempting suicide in the prior year.

- B.	Reason for Inclusion of the Strategy

Currently there is no integrated suicide prevention strategy countywide.  Provision of these services will reduce the number of youth suicides in King County.  This strategy will also increase the ability of parents, as well as school staff and administrators, to identify warning signs of potential suicide and develop appropriate prevention and intervention strategies.

- C.	Service Components/Design

There are four main components to this strategy:

- Suicide awareness presentations for youth 12-19:  These presentations will raise awareness of suicide and help students understand the warning signs of suicide.  They will also explain how to get help for themselves or their friends.  These will focus on increasing “help seeking” behavior and “help giving” behavior as it relates to suicide prevention.

- Teacher training:  This will provide faculty and other staff with information about depression and suicide, including warning signs; differentiates “normal” adolescent behavior from at risk behavior; identifies basic intervention strategies; and reinforces a school’s crisis response policies and procedures.

- Parent education:  This will offer presentations to parents and guardians on childhood depression, suicide, and community crisis resources.  This will also cover tips on how to talk to young people about depression and suicide, as well as how to assist parents in helping their youth deal with stress and depression.

- Assist schools in developing suicide prevention/intervention policies and procedures:  Many schools have no policies or procedures to respond to deal with suicide.  This aspect will help school leadership establish a suicide prevention strategy, to assist staff in identifying students at risk for self-destructive/pre suicide behaviors and to respond to a suicide crisis if needed.  This includes training front line staff such as teachers, nursing staff, coaches and counselors the skills and appropriate steps for intervening with students at risk, engaging families and outside support systems and community resources.

- D.	Target Population

The target populations are King County school students, including alternative schools students, age 12-19 years, school staff and administrators, and the students’ parents and guardians.

- E.	Program Goals

  - Support parents and guardians to increase knowledge and skills of suicide prevention and intervention strategies.

  - Assist schools in developing suicide prevention, suicide intervention and crisis response strategies.

- F.	Outputs/Outcomes

Individuals to be reached

  - 3000 students

  - 1500 parents

  - 500 school staff

The expected outcomes include increased awareness among youth, school personnel, and parents regarding suicide, and a reduction in youth suicides in King County.

2.	Funding Resources Needed and Spending Plan

The program needs $200,000 of MIDD funds per year to be sustainable.

| Dates | Activity | Funding |
| --- | --- | --- |
| March – July 2008 | Develop scope of work and outcomes in conjunction with Crisis Clinic TeenLink and YSPP | 0 |
| August 2008 | Develop exhibit and written contract | 0 |
| October 15, 2008 | Contract effective date | 0 |
| October – December 2008 | New staff hired and trained; services commence | $ 75,000 |
|  | Total Funds 2008 | $ 75,000 |
| January – December 2009 |  | $ 200,000 |
|  | Total Funds 2009 | $ 200,000 |
| Ongoing Annual | Total Funds | $ 200,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of providers (and where possible FTE capacity added via this strategy):

2 FTEs to provide Suicide Awareness training and instruction, 0.75 FTE for parent and teacher training, and 0.25 for school policy development.

This strategy involves one primary provider that will utilize the 3 FTE.  We will negotiate with a provider that we already have a contract with to provide this service.

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

Existing provider staff are trained and seen as experts on youth depression and suicide, however all of the newly hired staff will require training.  A coordinated effort between these agencies is central to the strategy to ensure there is a systematic approach to the implementation of the suicide prevention strategy in schools, and/or school districts (depending on the local need).

- C.	Partnership/Linkages

This strategy will involve a partnership between schools, school districts, Public Health, mental health providers serving children of active duty military personnel, and other King County youth serving agencies.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

March 2008 through July 2008:  develop scope of work and contract.

- B.	Procurement of Providers

August 2008:  King County already contracts with the Crisis Clinic for TeenLink services so MHCADSD will amend this contract to add funding and an exhibit for the additional work and outcomes, including the subcontract for the additional work and hiring of FTEs.

- D.	Contracting of Services

September 15, 2008 effective date

- E.	Services Start Date

October 2008 services provided to youth, parents and schools.

Strategy Title:	Expand Assessments for Youth in the Juvenile Justice System

Strategy No:	5a – Increase Capacity for Social and Psychological Assessments for Juvenile Justice Youth

County Policy Goals Addressed:

- Diversion of youth and adults with mental illness and chemical dependency from initial or further justice system involvement.

- A reduction of the incidence and severity of chemical dependency and mental and emotional disorders in youth and adults.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

The juvenile court processes 4,850 youth per year. National estimates suggest that 65-70% of youth in the juvenile justice system have problems with mental illness.  Of those, approximately 60% had a co-occurring substance abuse problem.  Of the 2300 youth admitted to King County juvenile detention in 2006, approximately half were referred to the mental health clinic due to their response on the Massachusetts Youth Screening Instrument (MAYSI), a standardized screening tool used in justice systems to determine the need for further mental health evaluation.   An estimated 80% of the 1300 King County youth annually placed on probation, who are moderate or high risk to re-offend are chemically dependent or substance abusers.

- B.	Reason for Inclusion of the Strategy

To successfully reduce future involvement in the justice system, the behavioral health issues of youth entering the juvenile justice system need to be effectively and assertively assessed and treated.

- C.	Service Components/Design

Under this strategy, the system will add staff capacity to increase the availability at the juvenile court of screening and assessment to determine if juvenile justice and child welfare system involved youth have substance abuse and/or mental health issues.  Following screening and assessment, this strategy will help assure treatment service linkage for youth identified with substance abuse and/or mental health treatment needs.  The following staffing capacity will be added to the system:  one chemical dependency professional, one mental health treatment liaison, one assessment coordinator, one psychologist, and contracted professionals to perform specialty assessments (psychiatric, medication evaluation, forensic psychiatric, neurological, etc.).

- D.	Target Population

Youth age 12 years or older who have become involved with the juvenile justice and/or child welfare system.

- E.	Program Goal

Increase the appropriate response to youth who have become involved with juvenile justice system due to substance abuse or mental health issues.

- F.	Outputs/Outcomes

- Screening and assessment of up to 1,080 youth per year.

- Linkage to treatment services for those youth identified with a treatment need.

- Reduction in future involvement in the juvenile justice system.

2.	Funding Resources Needed and Spending Plan

The project needs $361,000 to increase assessment staff capacity to address the needs of youth involved in the juvenile justice system.

The spending plan is as follows:

| Dates | Activity | Funding |
| --- | --- | --- |
| Sept – Dec 2008 | Start-up (staff hiring and training and award of the RFP for specialty professional assessment services) | $60,000 |
|  | Total Funds 2008 | $60,000 |
| Jan – Mar 2009 | Continued start-up (training for court staff on how to utilize the specialty assessment services and implementation of CD and MH assessment and linkage services) | $60,000 |
| Jan – Dec 2009 | Phasing in ongoing services | $250,000 |
|  | Total Funds 2009 | $310,000 |
| 2010 and onward | Ongoing assessment and linkage services |  |
| Ongoing Annual | Total Funds | $361,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers (and where possible FTE capacity added via this strategy)

  - One FTE Chemical Dependency Professional (CDP) (contracted)

  - One FTE Mental Health Liaison—Children’s Mental Health Professional (contracted)

  - One FTE King County Superior Court Assessment Coordinator

  - One FTE King County Superior Court Psychologist

  - Consultant contracts for professionals who provide specialty assessments

- B.	Staff Resource Development  Plan and Timeline (e.g. training needs, etc.)

The CDP will need to be qualified to administer the Global Assessment of Need (GAIN) assessment instrument.  Certification to administer this assessment tool can take up to three months if the individual is not qualified at the time of hire.

All other staff and consultants should be hired with appropriate qualifications to perform required assessments.

- C.	Partnership/Linkages

Partnerships with substance abuse and mental health treatment providers for the purpose of assuring quality linkages to needed treatment and/or evidence based programs specifically designed to reduce juvenile justice recidivism.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

Continued planning related to the implementation of this strategy proceeds from May – August 2008.

- B.	Procurement of Providers

The RFP(s) for the specialty assessment professionals will be released no later than August 30, 2008.

- C.	Contracting of Services

Amendments to existing contracts for the CDP and the mental health liaison will be in place by September 1, 2008.

- D.	Services Start Date(s)

CDP Assessments, Assessment Coordinator and MH Liaison services will begin September 15, 2008.

The Psychiatric staffing and specialty assessment services will begin no later than January 1, 2009.

Strategy Title:	Expand Wraparound Services for Youth

Strategy No:	6a – Wraparound Family, Professional and Natural Support Services for Emotionally Disturbed Youth

County Policy Goal Addressed:

- Diversion of youth and adults with mental illness and chemical dependency from initial or further justice system involvement.

- A reduction of the incidence and severity of chemical dependency and mental and emotional disorders in youth and adults.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

Families with children who have serious emotional and behavioral disturbances face numerous challenges. These children often experience profound difficulties with functioning in school, maintaining relationships with family and peers, coping with their emotions, and controlling their behavior. Sometimes these difficulties strain families to the point that they see no other solution than to place their child outside of their home.  When families turn to formal systems for support, they may experience a fragmented process that is driven more by system needs than by the needs of the child/youth and family.

Wraparound is a proven, effective approach to developing and coordinating service plans that build on the strengths of the child/youth and family.  Resulting plans are individualized and are based on the family’s goals. They address the specific cultural needs of the family, with the goal that services and supports occur in the family’s home and community whenever possible.  A team of supportive individuals ‘wraps’ around the family to help them achieve their goals.  Often the team is made up of ‘natural’ supports like relatives, neighbors, coaches, clergy, etc., who continue to be involved for years.

Wraparound reduces reliance on formal systems and increases resilience, self-determination and overall well-being for families.  Families who participate in wraparound often describe it as the only approach that truly worked for them.  Wraparound helps families to stay together and to avoid use of more costly resources such as inpatient care, foster care and/or juvenile justice.

Wraparound approaches have evolved since the early 1990s. ‘High fidelity wraparound’ is a ‘state of the art,’ scientifically supported approach that adheres to the established principles, guidelines and processes which have been shown to produce better outcomes.

- B.	Reason for Inclusion of the Strategy

Capacity to provide high fidelity wraparound is limited in King County.  Although the Regional Support Network developed capacity to offer wraparound as a result of federal Child and Adolescent Service System Project (CAASP) and System of Care grants, all grant funding ended in 2005, curtailing further growth and development.  The Children’s Mental Health Plan developed by MHCADS in 2005 anticipated that high fidelity wraparound would be available in 2006-07 to all children receiving the most intensive level of outpatient services.  However, the system has lacked sufficient resources to even begin to reach this goal.  MIDD funds will help to significantly expand the availability of wraparound to consumers throughout the county.  There is an increasing body of research that demonstrates the effectiveness of high fidelity wraparound.  In addition, the principles, methods and goals underlying wraparound align well with those of the MHCADS Recovery Initiative.

- C.	Service Components/Design

King County Mental Health, Chemical Abuse and Dependency Services Division (MHCADS) will employ a full time Wraparound Initiative Specialist devoted to the development and coordination of the initiative.  The Specialist, other MHCADS staff and partner agencies will design, develop and implement wraparound in King County based upon the ‘Ten Principles of Wraparound’ and the essential conditions defined as necessary to support high fidelity wraparound by the National Wraparound Initiative (NWI) and Portland State University Research and Training Center.

The King County Wraparound Initiative (KCWI) will assure that training, technical assistance, coaching, flexible funds/resources and capacity for system wide quality improvement and program evaluation is available on an ongoing basis.  The KCWI will phase in high fidelity wraparound over several years, building system capacity with a network of providers and assuring linkage to MIDD funded parent organizations (See Strategy 1f).

- D.	Target Population

Emotionally and/or behaviorally disturbed children and/or youth (up to the age of 21) and their families who receive services from two or more of the public mental health and substance abuse treatment systems, the child welfare system, the juvenile justice system, developmental disabilities and/or special education programs, and who would benefit from high fidelity wraparound.

- E.	Program Goal

High fidelity wraparound is available as needed for children/youth and families in the target population throughout King County.

- F.	Outputs/Outcomes

- High fidelity wraparound provided to 920 youth and families per year

- Training and technical assistance regularly available to provider organizations, parent organizations and partner agencies

- Improved school performance for youth served

- Improved high school graduation rates for youth served

- Reduced drug and alcohol use for youth served

- Improvement in functioning at home, school and community for youth served

- Reduced juvenile justice involvement for youth served

- Maintained stability of current placement for youth served

- Increased community connections and utilization of natural supports by youth   and families

2.	Funding Resources Needed and Spending Plan

This program needs $4,692,000 of MIDD funds per year to develop and sustain the MHCADS staff capacity, provide training and flexible funding and to contract with and sustain a network of organizations to serve all of King County.  When allowable, additional resources (including Medicaid and state funds) will be accessed by MHCADS contracted providers and/or our system partners to provide actual services and supports.  MHCADS will assure that funds are expended in accordance with contract expectations and standardized protocols (e.g., flexible funds must be used within established parameters).

| Dates | Activity | Funding |
| --- | --- | --- |
| June – Dec 2008 | Start-up (Hire MHCADS staff; development of program design, including training and evaluation plan, consultation needs; RFP development). | $175,000 |
|  | Total Funds 2008 | $175,000 |
| Jan – Dec 2009 | Phase in development of readiness capacity. Procurement, selection, contracting, recruitment and training of wraparound provider network. | $3,000,000 |
|  | Total Funds 2009 | $3,000,000 |
| 2010 and onward | County-wide network of provider organizations in place; ongoing training, support, quality improvement processes and program evaluation. | $4,692,000 |
| Ongoing Annual | Total Funds | $4,692,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers (and where possible FTE capacity added via this strategy)

This funding level supports a full-time Wraparound Initiative Specialist at MHCADS ($90,000 at 2008 county rates) and the capacity to provide ongoing training, monitoring, quality improvement and program evaluation.  A phased-in

implementation plan is required to develop, train and sustain a network of provider organizations with capacity to offer high fidelity wraparound to the target population (40 facilitators, 5 supervisors to serve 920 families).  Potential provider organizations may include both new and existing providers of wraparound.

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

| Dates: | Activity: |
| --- | --- |
| June– Dec 30, 2008 | Hire and train MHCADS Wraparound Initiative Specialist Develop and begin implementation of training and technical assistance plan |
| Jan – Dec 2009 | Orientation/training offered to develop readiness across the county Services will be initiated in phases as provider network is selected and develops capacity to offer high fidelity wraparound. |
| 2010 and ongoing | Program evaluation and quality improvement processes will help determine ongoing training and technical assistance needs. Ongoing training and technical assistance is implemented to assure KCWI achieves goal(s). |

- C.	Partnership/Linkages

MHCADS and its contracted wraparound provider network will maintain close partnerships with the NWI, with state and local parent organizations and with local partners, including mental health and substance abuse treatment providers, child welfare and juvenile justice systems, schools and other stakeholders.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

- MHCADS staff person recruited and hired by June 1, 2008.

- Program design and training plan will be substantially completed by December 31, 2008.

- First services will be offered by September 2009.

- B.	Procurement of Providers

- The RFP for provider organizations will be released by March 15, 2009.

- The response date will be April 30, 2009.

- The awards for accepted bids will be made May 15, 2009.

- C.	Contracting of Services

- Contracts for provider organizations will start on June 15, 2009.

- Training for provider organizations will begin by July 1, 2009.

- D.	Services Start Dates(s)

First services to families and youth will begin September 1, 2009.

Strategy Title:	Expand Services for Youth in Crisis

Strategy No:	7a – Reception Centers for Youth in Crisis

County Policy Goals Addressed:

- A reduction of the number of people with mental illness and chemical dependency using costly interventions like jail, emergency rooms and hospitals.

- Explicit linkage with, and furthering of, other council directed efforts including the Adult and Juvenile Justice Operational Master Plans, the Ten-Year Plan to End Homelessness in King County, the Veterans and Human Services Levy Service Improvement Plan and the Recovery Plan for Mental Health Services.

- Diversion of youth and adults with mental illness and chemical dependency from initial or further justice system involvement.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

The King County juvenile justice system struggles to respond adequately to the needs of arrested youth who are not eligible for juvenile detention and who do not have a readily available parent or guardian.  Although appropriate services might be available through Harborview’s Emergency Department, the Secure Crisis Residential Center, the Children’s Crisis Outreach Response Team, shelters, and/or Division of Child and Family Services, each of these services has different criteria, phone numbers and intake procedures. There is no coordinated response system to assist police or other professionals who encounter these youth. In addition, the system may need additional services to meet the needs of these youth.

- B.	Reason for Inclusion of the Strategy

It is a King County priority to minimize the use of detention for youth who are not a serious public safety concern and who do not have readily available parents or guardians. Since King County implemented the juvenile detention intake criteria in the late 1990s, law enforcement has experienced difficulty accessing community alternatives for youth who don’t meet those criteria. The Mental Illness and Drug Dependency Action Plan (MIDD) funds will help address these concerns and provide an opportunity to better assess unmet needs, develop additional services and improve coordination. This strategy is consistent with the goals of the King County Systems Integration Initiative.

- C.	Service Components/Design

The recommendation of the original MIDD Action Plan was to meet the needs of the target population through development of a reception center that would provide an

immediate option for law enforcement and serve as a central coordination point. As envisioned, the reception center would help connect youth to their parent/guardian or help them find alternative housing. Reception center staff would assess the youth’s needs for treatment and services and link them to those services.

At this juncture, a needs assessment and planning process is an essential next step to help evaluate the feasibility of the original recommendation.  In particular, the needs assessment will gather information about the projected use of a reception center.  The planning for this strategy will be coordinated with the planning processes for related MIDD strategies (especially Children’s Crisis Outreach Response System (7b), and Crisis Intervention Training for first responders (10a)). The goal of this integrated planning process would be to develop a crisis response system that meets the needs of the target population(s) and comprises a full continuum of service options.

- D.	Target Population

Youth who have been arrested, are ineligible for detention, and do not have a readily available parent or guardian.  Many of these youth have mental health and/or substance abuse needs. The needs assessment and planning process will help determine if a broader population of youth might also qualify for and benefit from this intervention (e.g., youth in crisis referred by schools or community centers).

- E.	Program Goals

Create a coordinated response/entry system for the target population.

Law enforcement and other first responders will be able to link youth to appropriate services in a timely manner.

An enhanced array of services is available to the target population.

- F.	Outputs/Outcomes

Complete a needs assessment in conjunction with Strategy 7b to determine appropriate strategies to meet goals.

Implement strategies identified through needs assessment (e.g., coordinated response system, reception center, additional services).

Reduce admissions to juvenile detention for youth served.

Reduce admissions to hospital emergency rooms and inpatient units for youth served.

Decrease homelessness for youth served.

2.	Funding Resources Needed and Spending Plan

The project needs $75,000 to conduct a needs assessment, design a coordinated response system, and assess the feasibility of and subsequently design a centralized reception center and/or additional services.

| Dates | Activity | Funding |
| --- | --- | --- |
| May – Dec 2008 | Project team (which may include a consultant) conducts needs assessment, evaluates feasibility of reception center, develops program design, budget and RFP if recommended. | $75,000 |
|  | Total Funds 2008 | $75,000 |
| Jan – Mar 2009 | Start-up activities for coordinated response system including training and communication plan (e.g., printing of materials) Project team finalizes recommendation for reception center and additional services. Next steps could include Request for Qualifications (RFQ) or Request for Proposals (RFP). | TBD (Note that one-time funds may be needed for capital improvements) |
|  | Total Funds 2009 | $497,400 |
| 2010 and onward | TBD | TBD |
| Ongoing Annual | Total Funds | $497,4000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers (and where possible FTE capacity added via this strategy) 

If implemented, the reception center would require a community provider, a suitable location, 24/7 capability and staff, including treatment specialists (mental health and substance abuse) and case managers.

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

Needs will be dependent upon the program design.

- C.	Partnership/Linkage

The planning process will occur in partnership with juvenile justice, law enforcement, youth service providers, King County Mental Health Chemical Abuse and Dependency Services Division, families and other involved stakeholders.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

- Needs assessment/Baseline/Feasibility Study and Concept Development:  Conduct a study and planning process; develop recommendations and design for a reception center and coordinated response system.  Develop budget estimates.  (May – Dec 2008)

- Implementation of Coordinated Response System:  Conduct training of staff, law enforcement, and other professionals.  Implement coordinated response system.  (January – Mar 2009)

- Reception Center:  Depending on recommendation from the project team, next steps could include the development of an RFQ or RFP.  Implementation date to be determined.  (2009)

- B.	Procurement of Providers

To be determined, depending on recommendations from the project team.

- C.	Contracting of Services

To be determined, depending on recommendations from the project team.

- D.	Services Start Date(s)

To be determined, depending on recommendations from the project team.

Strategy Title:	Expand Services for Youth in Crisis

Strategy No:	#7b – Expanded Crisis Outreach and Stabilization for Children and Youth

County Policy Goals Addressed:

- Diversion of youth and adults with mental illness and chemical dependency from initial or further justice system involvement.

- A reduction of the incidence and severity of chemical dependency and mental and emotional disorders in youth and adults.

- A reduction of the number of people with mental illness and chemical dependency using costly interventions like jail, emergency rooms and hospitals

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

Children and youth experiencing acute crises because of their emotional and/or behavioral problems may inappropriately enter the most restrictive and costly settings, including inpatient hospitalization, juvenile detention, foster care, and eventually, the Children’s Long-term Inpatient Programs (CLIP) or Juvenile Rehabilitation Administration institutions.  Youth who become involved in the child welfare and juvenile justice systems because of their emotional or behavioral problems face many barriers later in life related to education, employment, and housing.

- B.	Reason for Inclusion of the Strategy

King County holds the value that children and youth are better served when they remain within their home and community.  Research suggests that immediate crisis outreach and stabilization can help to de-escalate the current crisis, stabilize and maintain the current placement, and provide the family with tools and skills to prevent future crises.  Crisis outreach can prevent inappropriate utilization of costly out-of-home services. The current King County crisis system for children and youth has proven to be effective, but current capacity is insufficient; there are gaps in services for certain populations.

- C.	Service Components/Design

The current Children’s Crisis Outreach Response System (CCORS) offers a continuum of crisis outreach, crisis stabilization, and intensive in-home services to children, youth, and families in King County.  MIDD funding will expand capacity to serve additional youth and families, particularly those youth involved in the justice system whose placement is at risk.  Funding will support a comprehensive needs assessment and planning process with the goal of enhancing the continuum of children’s crisis services, incorporating elements of national best practice models (i.e., short-term crisis beds, reception center).  The planning process will be

coordinated with the planning for related MIDD strategies (especially Reception Center (7a), and Crisis Intervention Training for first responders (10a)).

- D.	Target Population

Children and youth age 3-17 who are currently in King County and who are experiencing a mental health crisis.  This includes children, youth, and families where the functioning of the child and/or family is severely impacted due to family conflict and/or severe emotional or behavioral problems, and where the current living situation is at imminent risk of disruption.  The program will also target children and youth being discharged from a psychiatric hospital or juvenile detention center without an appropriate living arrangement.

- E.	Program Goal

King County children’s crisis response system will have sufficient capacity and a range of available services to fully address the needs of the target population.

- F.	Outputs/Outcomes

- Serve an additional 300 children, youth and families each year.

- Conduct needs assessment, in conjunction with strategy 7a to determine additional capacity and resource needed to develop the full continuum of crisis options within the CCORS program

- Increased # of youth in King County receiving crisis stabilization within the home environment

- Maintain current living placement for youth served

- Reduced admissions to hospital emergency rooms and inpatient psychiatric units

- Decreased admissions and detention days in juvenile detention facilities

- Decreased requests for placement in child welfare system

2.	Funding Resources Needed and Spending Plan

| Dates | Activity | Funding |
| --- | --- | --- |
| Sep – Dec 2008 | Stakeholder work group will conduct needs assessment, evaluate alternatives and recommend model for expansion (budget for needs assessment in strategy 7a) |  |
|  | Total Funds 2008 | $ |
| Jan – Dec 2009 | Development of expanded model Contract amendment and/or RFP as needed; services begin Training and technical assistance is provided | $1,000,000 |
|  | Total Funds 2009 | $1,000,000 |
| 2010 and beyond | Comprehensive continuum of crisis interventions available to children and youth; Ongoing training and technical assistance and quality improvement process. | $1,000,000 |
| Ongoing Annual | Total Funds | $1,000,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers (and where possible FTE capacity added via this strategy)

The YMCA of Greater Seattle administers the current CCORS program.  The planning process will help determine the need to expand provider capacity.

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

| Dates: | Activity: |
| --- | --- |
| Jan – Dec 2009 | Implement expanded crisis services, providing orientation and training to providers and stakeholders, depending upon final model |
| 2010 and ongoing | Continuous assessment of staff development needs; ongoing training and technical assistance is offered |

- C.	Partnership/Linkages

Ongoing partnerships with the mental health provider network, the Crisis Clinic, hospitals and Crisis and Commitment/Designated Mental Health Professionals.  Region IV Division of Child and Family Services is a funding partner in the current CCORS program.  As an expanded model is evaluated and implemented, MHCADS will collaborate with juvenile justice, law enforcement agencies and other stakeholders who work with children and youth in crisis.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

Needs assessment and stakeholder planning process -- final recommendations completed by December 2008

Amend current contract as needed, expanding current interventions, and/or develop RFP as needed for new components in the continuum of crisis services – January -July 2009

Program phase-in until operating at full capacity (depending upon model) -- September 2009 - January 2010

Program evaluation and modifications as needed -- ongoing

- B.	Procurement of Providers

Since this is an expansion of an existing program with a contracted provider, an RFP is not required.  See overall timeline above.

- C.	Contracting of Services

See overall timeline above.

- D.	Services Start Dates(s)

To be determined through needs assessment and stakeholder planning process.

Target date range for service enhancements:  September 2009-January 2010.

Strategy Title:	Expand Family Treatment Court

Strategy No:	8a – Expand Family Treatment Court Services and Support to Parents

County Policy Goals Addressed:

- Diversion of youth and adults with mental illness and chemical dependency from initial or further justice system involvement.

- A reduction of the number of people with mental illness and chemical dependency using costly interventions like jail, emergency rooms and hospitals.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

With increasing frequency, children are placed in foster care because their parents are addicted to alcohol or drugs. Many children also are born to mothers who abused alcohol or drugs while pregnant.  Equally concerning is the number of children in foster care whose families are torn apart by substance abuse who subsequently abuse alcohol or drugs themselves.  Two hundred ninety (290) children, or 43% of the 675 annual dependency petitions filed in King County Superior Court (KCSC), are drug related.

Family Treatment Court (FTC) is a special program designed to ensure that children live in safe and drug free homes. This program is designed to serve individuals who have an abuse or neglect case against them with associated alcohol or substance abuse allegations.  Over 50% of the families entering FTC are homeless and in need of transitional and/or permanent housing.  Eighty-five percent are unemployed and the majority of female parent participants have been victims of domestic violence.  The FTC program will help the parents recover from alcohol or substance abuse and work toward reuniting parents with their children.

- B.	Reason for Inclusion of the Strategy

Keeping families whose lives have been devastated as a result of substance abuse together and/or encouraging early reunification is good for families and the community.  The majority of children who enter foster care eventually return to their parents. However, in recent years an increasing number of children leave foster care only to re-enter the system at a later date as a result of parental substance abuse.

- C.	Service Components/Design

FTC is organized around the ten key components that define a drug court:  1) integrated systems (child welfare, substance abuse treatment services and the court); 2) protection and assurance of legal rights, advocacy and confidentiality; 3) early identification and intervention; 4) access to comprehensive services and

individualized case planning; 5) frequent case monitoring and drug testing; 6) graduated responses and rewards; 7) increased judicial supervision; 8) deliberate program evaluation and monitoring; 9) a collaborative, non-adversarial, cross-trained team; and 10)  partnerships with public agencies and community-based organizations.

- D.	Target Population

FTC serves King County parents involved in the child welfare system who are identified as being chemically dependent and who have had their children removed due to their substance use.

- E.	Program Goals

FTC’s goals are: 1) to ensure that children have safe and permanent homes within permanency planning guidelines or sooner; 2) to ensure that families of color have outcomes from dependency cases similar to families not of color; 3) to ensure that parents are better able to care for themselves and their children and seek resources to do so; and 4) to reduce the societal cost of dependency cases involving parental chemical dependency.

- F.	Outputs/Outcomes

45 new children will be served in the program, doubling the current capacity to a total of 90 children.  Expected outcomes include a reduction in the use of substances and in juvenile justice system involvement.

2.	Funding Resources Needed and Spending Plan

The continuation and expansion of Family Treatment Court will have an annual cost of $694,300.

The spending plan is as follows:

| Dates | Activity | Funding |
| --- | --- | --- |
| Sept – Dec 2008 | Provide ongoing funding of existing services and start-up of program expansion (staff hiring and training) | $522,000 |
|  | Total Funds 2008 | $522,000 |
| Jan – Dec 2009 | Continued start-up and program funding | $694,300 |
|  | Total Funds 2009 | $694,300 |
| 2010 and onward | Ongoing Family Treatment Court costs | $694,300 |
| Ongoing Annual | Total Funds | $694,300 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers (and where possible FTE capacity added via this strategy)

| Type of Provider: | Description: |
| --- | --- |
| Treatment Liaison (1.0 FTE) | This position serves as a liaison between FTC and chemical dependency treatment agencies, monitors parent’s progress and compliance, and provides therapeutic case coordination services to FTC families. |
| Recruitment Specialist (1.0 FTE) | This position actively identifies and recruits new participants, provides orientation, conducts chemical dependency and mental health screenings, makes referrals to treatment agencies, serves as a liaison between the court and treatment agency and provides case coordination services to FTC parents. |
| Parent-to-Parent Coordinator (.5 FTE) | Goal of the Parent-to Parent Program is to increase parental engagement in hearings and the dependency process by connecting parents newly involved in the dependency court process with parents who have successfully reunited with their children. Coordinator guides veteran parents in helping new parents, organizes the schedule for shelter care hearings and facilitates “Dependency 101” classes. Will coordinate with FTC Alumni veteran parents to attend court hearings, conduct Dependency 101 classes and identify potential FTC participants. |
| Wraparound Coordinator (Contracted 1.0 FTE) | Coordinates on-going wraparound meetings for families in FTC that include both natural and professional supports involved with the parents and/or children. Facilitates wraparound meetings and leads the team in the development of a unified care plan consisting of strengths, normalized needs, measurable goals, and assigned tasks to complete these goals across ten different life domains. Develops a Strength, Need, & Cultural Discovery with the parent to be used in the development & implementation of the care plan. Assists the team in developing family/professional partnerships. |

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

Recruitment Specialist and Treatment Liaison positions will be recruited, hired and trained by KCSC 7/1/08 – 9/15/08.  Increases in public defense, CASA Supervisor and AG time assigned to FTC will be developed by 12/31/08.  The design and implementation of the parent-to-parent program will be conducted in collaboration with DSHS and MIDD Strategy #1f.  Ongoing FTC team building and training activities will be conducted.

- C.	Partnership/Linkages

Partnerships and linkages have already been developed with the Department of Children and Family Services, Children’s’ Administration, treatment providers and the court system.  Linkages to the Wraparound initiative 6a will occur as well.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

| Phase: | Timeline: | Strategies: | Target # of children: |
| --- | --- | --- | --- |
| Build to current capacity levels | 09/15/08 - 12/31/08 | Referral at 72-hour hearing to observe FTC by judicial officer (started 2/08) Hire Treatment Liaison by 9/15/08 | 45 |
| Phase I | 09/15/08 - 12/31/08 | Hire/Contract for Parent-to-Parent Program Coordinator to start by January 2009 Hire Recruitment Specialist by 9/15/08 Contract for additional Wraparound Coordinators to meet the need of the existing participants so they are in place by January 2009 | 60 |
| Phase II | 01/01/09 - 06/30/09 | Implement Dependency 101/Parent-to-Parent Program Contract for an additional Wraparound Coordinator so they are in place by July 2009 Identify potential space needs | 75 |
| Phase III | 06/30/09 - 12/31/09 | Identify remaining needs to move to full capacity | 90 |

- B.	Procurement of Providers

There is no current plan for procurement of services to accompany program expansion.

- C.	Contracting of Services

Current FTC Wraparound Coordinator contract amended for continuation by 9/1/08.  Additional Wraparound Coordinator positions to accommodate program expansion to be procured and contracted through MIDD Strategy 6a.

- D.	Services State Date(s)

Services to clients will begin to increase September 2008.

Strategy Title:	Programs Targeted for Youth

Strategy No:	9a – Expand Juvenile Drug Court

County Policy Goals Addressed:

- Diversion of youth and adults with mental illness and chemical dependency from initial or further justice system involvement.

- Explicit linkage with, and furthering of, other council directed efforts including the Adult and Juvenile Justice Operational Master Plans, the Ten-Year Plan to End Homelessness in King County, the Veterans and Human Services Levy Service Improvement Plan and the Recovery Plan for Mental Health Services.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

The number of juveniles charged with drug-related crimes and referred for substance abuse services continues to increase. An estimated 80% of the 1300 youth annually placed on probation and who are assessed as moderate or high risk to reoffend are chemically dependent or substance abusers.  An estimated 325, or 25% of these youth, are eligible for and could benefit from juvenile drug court services.  There is currently insufficient capacity to increase the number of youth served annually in the King County Juvenile Drug Court (JDC) program.  This strategy strengthens the program and increases the number of youth who have access to the JDC.

- B.	Reason for Inclusion of the Strategy

JDC programs are effective at reducing recidivism and keeping youth engaged in the treatment process. Two outcome studies specific to the King County JDC have documented significant reductions in recidivism among program participants.  Juvenile justice has increasingly become the service delivery point for adolescents with substance abuse and co-occurring problems who lack resources for other assistance.  The JDC model provides improved, expanded, yet cost-effective adolescent substance abuse in a coordinated system of care.  The model of care in King County challenges systemic inequities and facilitates dialogue among justice and treatment professionals, families, and the youth themselves.  The implementation of evidence-based practices and the Reclaiming Futures Project have transformed disconnected laws, programs and professionals into an effective, efficient and successful community of responders, helping youth reclaim their lives while improving public health and public safety.

- C.	Service Components/Design

JDC is organized around the ten key components that define a drug court:

1) integrated systems (substance abuse treatment services and the court);

2) protection and assurance of legal rights, advocacy and confidentiality;  3) early identification and intervention;  4) access to comprehensive services and individualized case planning;  5) frequent case monitoring and drug testing;

6) graduated responses and rewards;  7) increased judicial supervision;

8) deliberate program evaluation and monitoring;  9) a collaborative, non-adversarial, cross-trained team;  and 10) partnerships with public agencies and community-based organizations.

- D.	Target Population

JDC serves King County youth involved in the juvenile justice system who are identified as having substance abuse issues or are diagnosed as chemically dependent.

- E.	Program Goal

Strengthen the JDC program and increase the number of youth who have access to the Juvenile Drug Court.

- F.	Outputs/Outcomes

An additional 36 youth per year will be served and the current capacity will be maintained for a total capacity of 72 youth served annually.

Expected outcomes include: 1) Reduced substance abuse/dependence and delinquent activity among participants, 2) Improved coordination between the court and community agencies, 3) Increased familial involvement in youth’s legal and treatment process, and 4) Increased protective factors and decreased risk factors among youth and their families.  Long term outcomes include a reduction in recidivism and a decreased use of secure detention and/or state juvenile rehabilitation institutions.

2.	Funding Resources Needed and Spending Plan

The expansion of JDC will have an annual cost of $588,000.

| Dates | Activity | Funding |
| --- | --- | --- |
| Sept – Dec 2008 | Start-up (staff hiring and training) | $250,000 |
|  | Total Funds 2008 | $250,000 |
| Jan – Dec 2009 | Phasing in ongoing services | $588,000 |
|  | Total Funds 2009 | $588,000 |
| 2010 and onward | Ongoing program expansion costs | $588,000 |
| Ongoing Annual | Total Funds | $588,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers (and where possible FTE capacity added via this strategy)

| Type of Provider: | Proposed additional FTE: | Proposed additional contracted positions: |
| --- | --- | --- |
| Treatment Liaison | 1.0 |  |
| Juvenile Drug Court JPC Case manager | 2.0 |  |
| Public Defender | .25 FTE @ PDIII class |  |
| Prosecutor (.25 FTE @ PDIII) | .25 FTE @ PDIII |  |
| Contracted Mentor Program |  | 3.0 FTE |

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

Treatment liaison and case management positions will be recruited, hired and trained by KCSC 9/1/08 – 3/31/09.  Public defense and prosecutor time assigned to JDC will also be increased during this same time period.

- C.	Partnership/Linkages

Existing partnerships will continue to be fostered and developed between the substance abuse treatment provider community and the juvenile justice system.  Linkages will also occur with MIDD strategy 6a.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

| Phase: | Timeline: | Strategies: | Target # of children: |
| --- | --- | --- | --- |
| Phase I – Build to capacity | 08/15/08 –12/31/08 | Expand and implement eligibility criteria | 36 |
| Phase II | 01/01/09 –12/31/09 | Continue expansion under revised criteria Expand and provide earlier clinical screening and assessments (integrate short GAIN into risk assessment) | 72 |
| Phase III | Jan 2010 onward | Sustained implementation | 72 |

- B.	Procurement of Providers

| Dates: | Activity: |
| --- | --- |
| Sept 15 – Dec 2008 | Amend existing contracts and add treatment capacity |
| Sept 15 – Dec 2008 | Develop contact for mentoring services |
| January 2009 | Phase in mentoring services |
| June 1, 2009 | Fully operating programs |

- C.	Contracting of Services

The RFP for contracted mentor services will be issued and awarded 9/15 – 12/31/08 for service provision beginning 1/1/09.

- D.	Services Start Date(s)

Services to clients will increase beginning in September 2008.

Jail and Hospital Diversion Programs

10a – 12d

Strategy Title:	Pre-Booking Diversion Programs

Strategy No:	10a – Crisis Intervention Training Program for King County Sheriff, Police, Jail Staff and Other First Responders

County Policy Goals Addressed:

- Diversion of youth and adults with mental illness and chemical dependency from initial or further justice system involvement.

- A reduction of the number of people with mental illness and chemical dependency using costly interventions like jail, emergency rooms and hospitals.

- Explicit linkage with, and furthering of, other council directed efforts including the Adult and Juvenile Justice Operational Master Plans, the Ten-Year Plan to End Homelessness in King County, the Veterans and Human Services Levy Service Improvement Plan and the Recovery Plan for Mental Health Services.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

In the police departments of cities in the United States with populations greater than 100,000, approximately 7% of all police contacts, both investigations and complaints, involve a person believed to have a mental illness.   It is a major challenge for police and other first responders to maintain the safety of everyone involved in these situations while also resolving the situation so they can move on to other calls and duties.  Crisis Intervention Training (CIT) equips police and other first responders with the training needed to enable them to respond most effectively to individuals in crisis and to help these individuals access the most appropriate and least restrictive services while preserving public safety. The Seattle Police Department has had a successful, nationally recognized CIT program for a number of years, but this training has not been readily available to the other 25 police jurisdictions or to other first responders in King County.

- B.	Reason for Inclusion of the Strategy

Research has shown CIT to be effective in improving community response to individuals with mental illness and chemical dependency, increasing the use of jail diversion options and reducing the number of people with mental illness going to jail, and reducing police officer injury rates.

- C.	Service Components/Design

Provide 40-hour CIT training to police officers in any jurisdiction in King County who request full training.  Provide one-day training for other officers and to other first responders.

- D.	Target Population

Police officers (including officers working in public schools), firefighters, emergency medical technicians, ambulance drivers, and jail staff throughout King County.  When space is available, other interested stakeholders who would benefit from the training, such as prosecuting attorneys and public defenders, may also be invited to participate.

- E.	Program Goal

Increase the knowledge base and skill set of police and other emergency workers in responding to calls involving individuals who may be affected by mental illness and/or chemical dependency.

- F.	Outputs/Outcomes

Provide full CIT to 480 police and other first responders per year and a brief, one day training to another 1200 first responders per year.

Training will result in increased safety for first responders and individuals in crisis and also increase the use of community resources resulting in decreased jail bookings and hospital emergency department admissions.

2.	Funding Resources Needed and Spending Plan

The project needs $1.5 million per year to implement CIT throughout King County.

The spending plan is as follows:

| Dates | Activity | Funding |
| --- | --- | --- |
| Sept - Dec 2008 | Start-up, which includes hiring 2 FTE staff. Funding pays for salary and benefits, overhead, office space, equipment and set-up. Classroom space is obtained | $ 50,000 |
|  | Total Funds 2008 | $ 50,000 |
| Jan – Dec 2009 | King County Sheriff’s Office (KCSO) staff, overhead, and office space | $ 220,000 |
|  | Training costs for 1,680 students, including training materials and classroom space | $1,280,000 |
|  | Total Funds 2009 | $1,500,000 |
| Ongoing Annual | Total Funds | $1,500,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and Type of Providers (and where possible FTE capacity added via this strategy)

This strategy involves a single provider, the KSCO who will hire a 1.0 FTE Educator/Consultant II or III who will manage the program and a 1.0 FTE Administrative Specialist II who will provide administrative support.  The KCSO will secure specialized training instructors as needed on a fee-for-service basis.

- B.	Staff Resource Development  Plan and Timeline (e.g. training needs, etc.)

The KCSO has identified appropriate job classifications and can begin the hiring process as soon as funding is allocated.

Sept - Dec 2008 -- KCSO hires trained Educator/Consultant and Administrative Specialist staff.  Specialized instructors are identified and secured as needed.

- C.	Partnership/Linkages

King County MHCADSD will need to continue to maintain a significant partnership with the KCSO, which will be responsible for managing the crisis intervention training program for police officers and other first responders in King County.  Other partners needed for a successful training program include the King County NAMI affiliates, all 26 law enforcement agencies in King County, tribal police, service providers, jails, and other first responder agencies.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

KCSO staff persons recruited and hired by November 1, 2008.

Program design and training curriculum will be substantially completed by December 1, 2008.

Specialized instructors and classroom space will be secured by December 31, 2008.

First trainings will be offered in January 2009.

- B.	Procurement of Providers

Not applicable.

- C.	Contracting of Services

Not applicable.

- D.	Services Start Date(s)

Begin trainings in January 2009.

Strategy Title:	Pre-Booking Diversion Programs

Strategy No:	10b – Adult Crisis Diversion Center, Respite Beds and Mobile Behavioral Health Crisis Team

County Policy Goals Addressed:

- Diversion of youth and adults with mental illness and chemical dependency from initial or further justice system involvement.

- A reduction of the number of people with mental illness and chemical dependency using costly interventions like jail, emergency rooms and hospitals.

- Explicit linkage with, and furthering of, other council directed efforts including the Adult and Juvenile Justice Operational Master Plans, the Ten-Year Plan to End Homelessness in King County, the Veterans and Human Services Levy Service Improvement Plan and the Recovery Plan for Mental Health Services.

- A reduction of the number of people who cycle through the jail, returning repeatedly as a result of their mental illness or chemical dependency.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

Hospital emergency departments across King County are regularly overcrowded with individuals waiting for mental health or chemical dependency assessments and placement dispositions.  In many cases, individuals who have been assessed as needing involuntary commitment have had to stay in emergency departments for up to three days waiting for admission to an involuntary inpatient unit.  On any given day in jails throughout King County, an estimated 15 percent of inmates have a serious mental illness and 80 percent have substance abuse problems.  Once in jail, individuals with mental illness stay much longer than inmates without mental illness, and the daily cost of serving them in the jail is much greater.  Diverting individuals from the jail, when appropriate given the nature of the criminal offense and the potential risk to public safety, not only reduces costs for city and county governments, but also provides more appropriate and humane care.

- B.	Reason for Inclusion of the Strategy

Creating a crisis diversion facility would give police options for diverting individuals who are in crisis due to mental illness and/or substance abuse from jails and hospital emergency departments.  A crisis diversion facility, combined with mobile crisis teams and respite housing, would also link individuals in crisis with needed community services that would help keep individuals from constantly recycling through expensive emergency services.

- C.	Service Components/Design

Establish a crisis diversion facility (CDF) where police and other first responders may refer/bring individuals in crisis for evaluation, crisis resolution and linkage to appropriate community-based care.  Develop a mobile crisis team that can assist first responders in finding appropriate resources or transporting individuals to and from the diversion facility.  Provide interim “respite” housing for homeless individuals ready to leave the CDF, but in need of temporary housing while permanent supported housing is being arranged.  Includes data collection that will be linked to the high-utilizer database maintained by King County Mental Health, Chemical Abuse and Dependency Services Division.

- D.	Target Population

Adults in crisis in the community who might otherwise be arrested for minor crimes and taken to jail or brought to a hospital emergency department.  The exact criteria for diversion have not yet been established.  Criteria will be established during a planning process involving community and criminal justice system stakeholders.  Individuals who have been seen in emergency departments or at jail booking and who are ready for discharge, but still in crisis and in need of services, may also be eligible.

- E.	Program Goal

Reduce admissions to jails, hospital emergency departments and psychiatric hospital units.

- F.	Outputs/Outcomes

Estimated 3000-5000 admissions per year.

Outcomes will include linkages of individuals admitted to needed community treatment and housing, reduced admissions to emergency rooms, and reduced admissions to jails.

2.	Funding Resources Needed and Spending Plan

| Dates | Activity | Funding |
| --- | --- | --- |
| April 2-3 | Initial planning meeting with national consultants | $350 |
| June-December 2008 | Monthly planning meetings with stakeholders. Include visits to established successful diversion programs in other jurisdictions. Identify potential sites for diversion facility and strategy for securing site and building out facility. Determine strategy for crisis teams and respite/interim housing. | $ 10,000 |
|  | Total Funds 2008 | $10,350 |
| Jan – Mar 2009 | Develop and issue Report For Proposal(s) (RFP). May consider one RFP for all services, or separate RFPs for each component of diversion strategy. |  |
| March-October 2009 | Phased-in selection of contractors, contracting, facility remodel, recruitment of staff, training, development of policies and procedures. | $4.5 million |
| November 1, 2009 | Facility, crisis teams and crisis respite programs open for services |  |
|  | Total Funds 2009 | $ 4.5 million |
| 2010 and onward | Ongoing Crisis Diversion Program | $6.1 million |
| Ongoing Annual | Total Funds | $6.1 million |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers

Still to be developed

May have one provider for all three components of strategy, or up to three providers providing separate but coordinated services

- B.	Staff Resource Develop Plan and Timeline

Still to be developed

Will depend on the model developed through the planning process

- C.	Partnership/Linkages

We have initiated a planning process that will continue through the remainder of 2008.  The first meeting of the planning group was facilitated by consultants from the National GAINS Center and the Bexar County Jail Diversion Program, which was the recipient of the Gold Achievement Award from the American Psychiatric Association in the category of community-based programs.  Partners  in the ongoing planning process will include representatives from the criminal justice system (prosecuting attorneys, public defender, courts, jails, police), hospitals, community providers of mental health and chemical dependency services, housing providers, National Alliance on Mental Illness,  Developmental Disabilities Division, Crisis Clinic, Department of Corrections, and King County Mental Health, Chemical Abuse and Dependency Services Division.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

Monthly meeting of planning group:			May - December 2008

Develop and issue RFP(s)				January - March  2009

Phased-in selection of contractors, contracting,		March - October  2009 facility remodel, recruitment of staff,

training, development of policies and

procedures.

Open facility, begin crisis teams and 			November   2009

open respite housing

- B.	Procurement of Providers

Exact timeline to be determined

- C.	Contracting of Services

Exact timeline to be determined

- D.	Services Start Date(s)

November 1, 2009

Strategy Title:	Expand Access to Diversion Options and Therapeutic Courts and Improve Jail Services Provided to Individuals with Mental Illness and Chemical Dependency

Strategy No:	11a – Increase Capacity for Jail Liaison Program

County Policy Goals Addressed:

  - Diversion of youth and adults with mental illness and chemical dependency from initial or further justice system involvement.

  - Explicit linkage with, and furthering of, other council directed efforts including the Adult and Juvenile Justice Operational Master Plans, the Ten-Year Plan to End Homelessness in King County, the Veterans and Human Services Levy Service Improvement Plan and the Recovery Plan for Mental Health Services.

  - A reduction of the number of people who cycle through the jail, returning repeatedly as a result of their mental illness or chemical dependency.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

There are currently four jail liaisons working in King County and municipal jails, and in the Community Center for Alternative Programs (CCAP). These liaisons are now at full capacity, and an additional liaison is needed in order to expand this service to an additional jail population not currently being served.  This strategy will expand the liaison service to the work release program so that these individuals will receive the community support services needed to meet their mental health and chemical dependency treatment needs and reduce the likelihood of their re-offending.

- B.	Reason for Inclusion of the Strategy

Many individuals with mental illness and/or chemical dependency end up in jail due to behavior that is associated with their illness, and, once in jail, they stay longer than individuals charged with the same crime who do not have these illnesses.  In many cases, entry into the criminal justice system could be avoided if people were provided with the appropriate community supports and services.  Jail liaisons help link these individuals with appropriate community services and thereby reduce the length of stay in jails and increase the likelihood of successful community reintegration.

- C.	Service Components/Design

The King County Mental Health, Chemical Abuse and Dependency Services Division (MHCADSD) contracts with Sound Mental Health (SMH) to provide criminal justice liaison services.  The goal of the liaisons is to directly connect adult defendants with the community services it will take to keep them from returning to jail.

Liaisons initially meet with adult defendants who are due to be released from jail within forty-five to ten business days, or who are court-ordered to CCAP, and assess what their needs will be upon release or discharge.  They refer defendants directly to mental health treatment, co-occurring disorders programs, Reentry Case Management Services, Department of Social and Health Services (DSHS), Alcoholism and Drug Addiction Treatment and Support Act (ADATSA) services, the Municipal Court Resource Center and Veterans Reintegration Services, among others.  They also provide information on temporary housing, and dental and medical services in the community.  Criminal Justice Liaisons work closely with Public Defenders and various probation and community corrections staff to negotiate release of inmates into treatment.  As mental health professionals with specialties in co-occurring disorders, the Criminal Justice Liaisons are in a unique position to assist the large numbers of inmates with mental health concerns, as well as those with both mental health and chemical dependency disorders.

- D.	Target Population

King County Work Education Release (WER) inmate-clients who are residents of King County or likely to be homeless within King County upon release from custody, and who are assessed as needing mental health services, chemical dependency treatment, other human services, or housing upon release.

- E.	Program Goals

Expand criminal justice liaison services to WER inmates to enhance their access to mental health services, chemical dependency treatment, and co-occurring disorders programs in the community.  Improve the likelihood that clients will be placed in housing (temporary or permanent) upon discharge from WER.  Assist WER inmates in applying for DSHS benefits when they are within 45 days of discharge.  Refer veterans to Veterans Reintegration Services.

- F.	Outputs/Outcomes

- Total number of clients served per year: 360

- Outcomes will include increased referrals to and engagement with community-based treatment agencies, improved mental health status, reduced use of drugs and alcohol, and reduced jail recidivism.

2.	Funding Resources Needed and Spending Plan

| Dates | Activity | Funding |
| --- | --- | --- |
| Sept- December | SMH hires and trains 1 FTE liaison. Funding pays for salary and benefits, administrative overhead, office space, equipment. | $20,000 |
|  | Total Funds 2008 | $20,000 |
| Jan – Dec 2009 | New FTE serves | $80,000 |
|  | Total Funds 2009 | $80,000 |
| Ongoing Annual | Total Funds | $80,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of providers (and where possible FTE capacity added via this strategy)

This strategy involves a single provider, Sound Mental Health, since this is an expansion of a current service being provided by an agency that previously was selected in a competitive process.  Specifically, the strategy will increase criminal justice liaison staffing by 1.0 FTE to be sited at the Work Education Release offices, administered by the King County Department of Adult and Juvenile Detention, Community Corrections Division.  Current staffing consists of 4.0 FTE criminal justice liaisons located throughout King County.  With the addition of the fifth liaison, staff will be sited at the following locations:

  - CCAP (1.0 FTE funded by King County Current Expense)

  - King County Correctional Facility (2.0 FTE funded by King County Current Expense)

  - South and East King County municipal jails (1.0 FTE funded by State Jail Services Funds)

  - Work Education Release (1.0 FTE to be funded by MIDD sales tax)

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

Sound Mental Health has already developed a complete job description, training requirements, and standard operating procedures for the criminal justice liaison position.  Existing criminal justice liaison staff will provide orientation to the position.  Technical assistance will be provided by King County MHCADSD/CJI staff.

- C.	Partnership/Linkages

This strategy will involve a partnership with the King County Department of Adult & Juvenile Detention/Community Corrections Division (CCD) that operates WER.  MHCADSD/CJI staff will work with CCD/WER managers to plan for locating the 1.0 FTE criminal justice liaison at WER upon approval.  Planning will include the securing of necessary office space and equipment and outlining referral protocols between WER Case Workers and the criminal justice liaison assigned to WER.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

The agency will need to advertise and recruit to fill the additional Criminal Justice Liaison position.  Expected timeline is 45 to 60 days after the Provider is notified.  The candidate hired will need to successfully apply for jail clearance through the King County Department of Adult and Juvenile Detention.  This application process typically takes about 30 days.  Direct services will begin when the Criminal Justice Liaison has obtained jail clearance.

- B.	Procurement of Providers

Since MHCADSD already contracts with Sound Mental Health to provide Criminal Justice Liaison services, as noted above, no RFP is required.  King County will need to amend the Sound Mental Health contract to add funding for the additional position.

- C.	Contracting of Services

See previous bullet.

- D.	Services Start Date(s)

Services to consumers will begin November 1, 2008

Strategy Title:	Expand Access to Diversion Options and Therapeutic Courts and Improve Jail Services provided to Individuals with Mental Illness and Chemical Dependency

Strategy No:	11b – Increase Services Available for New or Existing Mental Health Court Programs

County Policy Goals Addressed:

- Diversion of youth and adults with mental illness and chemical dependency from initial or further justice system involvement.

- Explicit linkage with, and furthering of, other council directed efforts including the Adult and Juvenile Justice Operational Master Plans, the Ten-Year Plan to End Homelessness in King County, the Veterans and Human Services Levy Service Improvement Plan, and the Recovery Plan for Mental Health Services.

- A reduction of the number of people who cycle through the jail, returning repeatedly as a result of their mental illness or chemical dependency.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

The prevalence of people with mental illness in the criminal justice system is a nationwide problem.  Estimates of the prevalence of people with mental illness in jails ranges from 5% to 16%, depending on the definition of mental illness that is used. On any given day in city jails throughout King County, an estimated 15% of inmates have serious mental illness.  Once in jail, these individuals stay much longer than inmates with similar charges who are not mentally ill.  Mental health court is an effective tool for engaging and keeping people with mental illness in community-based treatment.  At the present time, access to mental health court is limited to just a few jurisdictions.

- B.	Reason for Inclusion of the Strategy

Mental health courts are an essential component of a jail diversion continuum of service and have been shown to be effective in engaging clients in treatment and reducing future jail bookings.  Mental health court services are now limited to individuals in King County District Court, Seattle Municipal Court, and Auburn Municipal Court.  Increasing access to mental health court could improve mental health outcomes for people in the criminal justice system and reduce the prevalence of people with mental illness in jails across King County.

- C.	Service Components/Design

This strategy will enhance services and capacities at existing mental health courts or implement new mental health court programs to increase access to these programs for eligible adult misdemeanants.  Service enhancements may include the placement of a Mental Health Professional (called a “court monitor” or “court liaison”) and a peer support specialist within the mental health court team.  The mental health court program must have sufficient judicial, public defender and prosecutor staff to accommodate the increased or new court caseloads, along with sufficient probation staff to monitor eligible clients in terms of court compliance.  Additionally, the mental health court program should arrange for necessary transports, including security, from jail to the court.

Treatment and other human service components may be included; for example, increased mental health and co-occurring disorder treatment capacity, housing resources and low-barrier access for direct referrals from the mental health court staff to community treatment providers may be considered.  The capacity to serve both the population opting into the mental health court as well as those appearing before the court that are unable to opt-in because of their lack of legal competency may be included.  However, most of the treatment and other human services provided in the community for mental health court participants, including case management, are expected to be covered by other resources including other strategies identified and funded under the MIDD.

- D.	Target Population

Adult misdemeanants with serious mental illness who volunteer to participate in a mental health court program through an “opt-in” process.  An important goal for this strategy is to provide access for participation from individuals in court jurisdictions in all parts of King County.

- E.	Program Goals

To be determined by adoption of revised strategy after receipt of MIDD Oversight Committee report in April, 2009

- F.	Outputs/Outcomes:

To be determined by adoption of revised strategy after receipt of MIDD Oversight Committee report in April, 2009

2.	Funding Resources Needed and Spending Plan

To be determined by adoption of revised strategy after receipt of MIDD Oversight Committee report in April, 2009

3.	Provider Resources Needed (number and specialty/type)

To be determined by adoption of revised strategy after receipt of MIDD Oversight Committee report in April, 2009

- A.	Number and type of Providers (and where possible FTE capacity added via this strategy)

To be determined by adoption of revised strategy after receipt of MIDD Oversight Committee report in April, 2009

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

To be determined by adoption of revised strategy after receipt of MIDD Oversight Committee report in April, 2009

- C.	Partnership/Linkages

To be determined by adoption of revised strategy after receipt of MIDD Oversight Committee report in April, 2009

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

To be determined by adoption of revised strategy after receipt of MIDD Oversight Committee report in April, 2009

- B.	Procurement of Providers

To be determined by adoption of revised strategy after receipt of MIDD Oversight Committee report in April, 2009

- C.	Contracting of Services

To be determined by adoption of revised strategy after receipt of MIDD Oversight Committee report in April, 2009

- D.	Services Start Date(s)

To be determined by adoption of revised strategy after receipt of MIDD Oversight Committee report in April, 2009

Strategy Title:	Expand Re-Entry Programs

Strategy No:	12a - Increase Community Re-entry from Jail Program Capacity

County Policy Goals Addressed:

- Diversion of youth and adults with mental illness and chemical dependency from initial or further justice system involvement.

- Explicit linkage with, and furthering of, other council directed efforts including the Adult and Juvenile Justice Operational Master Plans, the Ten-Year Plan to End Homelessness in King County, the Veterans and Human Services Levy Service Improvement Plan and the Recovery Plan for Mental Health Services.

- A reduction of the number of people who cycle through the jail, returning repeatedly as a result of their mental illness or chemical dependency.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

On any given day in the King County jail, an estimated 15 percent of inmates have a serious mental illness and 80 percent have substance abuse problems.  Re-entry from jail or a court-ordered alternative for these populations is imperative to assure they follow through on their re-entry plans and get connected to treatment and other services in the community.  King County Criminal Justice Initiatives data show that, without re-entry case management services, many offender-clients fail to connect to treatment and other services on their own – or drop out of services within a short timeframe.

- B.	Reason for Inclusion of the Strategy

The Re-entry Case Management Services (RCMS) program is intended to provide intensive, short term case management to individuals with mental health and/or substance abuse problems who are close to release and in need of assistance to reintegrate back into the community in order to keep from re-offending and returning to jail.  This intensive case management is the “hand off” from the staff working inside the jail or at the Community Center for Alternative Programs (i.e. Criminal Justice Liaisons) to have immediate day of release/discharge assistance in creating longer term linkages to outpatient treatment services, and support in navigating the complex funding, treatment, housing, and health care systems in the community.

The County recognizes that gainful employment and earning a livable wage is a necessity for successful reintegration into the community for those individuals who are employment ready.  Employment and vocational services are necessary components of a comprehensive re-entry program but currently limited in the RCMS.

- C.	Service Components/Design

RCMS is administered by Sound Mental Health via collaboration between the King County Department of Community & Human Services/Mental Health, Chemical Abuse and Dependency Services Division (MHCADSD) and the King County Department of Adult & Juvenile Detention (DAJD)/Community Corrections Division (CCD).  RCMS services, provided by re-entry case managers, are available to adult offenders exiting a King County Jail or CCD program, such as Work and Education Release (WER) or the Community Center for Alternative Programs (CCAP).  Eligibility for RCMS includes individuals who have a mental health and/or substance abuse disorder and are within 45 days of release from a King County Jail or currently serving a sentence at WER or CCAP.

Re-entry Case Management consists of:

  - Re-entry needs assessment

  - Pre-release engagement consisting of a minimum of one face-to-face meeting

  - Facilitation of application for public entitlements and other benefits

  - Medication monitoring

  - Linkage to mental health services and substance abuse treatment

  - Assistance with basic needs

  - Assistance with transportation (i.e., bus tickets)

  - Assistance with physical health care resources

  - Assistance with shelter and transitional housing resources

  - Linkage to pre-vocational and employment services and resources

- D.	Target Population

- Adult inmates with mental illness and/or chemical dependency housed in the King County Correctional Facility (KCCF), Norm Maleng Regional Justice Center (RJC), or WER who are within 45 days of release and will not be transferred to prison or another county, assessed as needing treatment, and are not currently enrolled in outpatient treatment services.

- Adult defendants and offenders with mental illness and/or chemical dependency who are court-ordered to CCAP or another CCD program, – and adult inmates who are within 45 days of release from KCCF, RJC, or WER – and assessed as being employment ready and/or amenable to participating in vocational/pre-employment services.

- E.	Program Goals

- Provide increased access to intensive, short term case management to individuals with mental health and/or chemical dependency disorders who are close to release and in need of assistance in reintegrating back into the community.  Provide immediate assistance for more participants in accessing

publicly funded benefits (if eligible), housing, rental assistance, and outpatient treatment and other services in the community upon release.

- Focused re-entry case management will be provided to individuals participating in jail-based vocational programs to secure successful linkage to community-based employment and vocational service providers.  Additionally, individuals participating in a CCD alternative program who are in treatment and employment ready will be targeted for focused reentry case management and linked to employment and vocational services.

  - Individuals will be initially linked with County funded resources including, but not limited to, the WorkSource system and King County Jobs Initiative (KCJI).

  - Linkages would also be made with CCD’s partner agencies for other employment and vocational services.

- F.	Outputs/Outcomes

- Three re-entry case managers will serve an additional 1,000 individuals per year

- The re-entry employment liaison will serve 200 individuals per year

- Increased treatment involvement and treatment completion

- Increased housing stability

- Reduced criminal justice involvement

- Increased employment among program recipients

2.	Funding Resources Needed and Spending Plan

$320,000 per year will provide four additional FTE to this program.  This includes the cost per FTE as well as office space/equipment, a flexible fund account for participant incidentals, and administration.

- $240,000 for three FTE re-entry case mangers will be earmarked for Target Population #1 (see Target Population section above).  The contract related to Target Population #1 is managed by MHCADSD, which intends to amend its contract with Sound Mental Health to add capacity immediately upon allocation of funds.

| Target Population #1 – Reentry Case Managers |
| --- |
| Dates | Activity | Funding |
| Sept 2008 | Amend Sound Mental Health contract to add 3 FTE re-entry case managers plus flex funds | $80,000 |
|  | Total Funds 2008 | $80,000 |
| Jan – Dec 2009 | 3 FTE re-entry case managers plus flex funds | $240,000 |
|  | Total Funds 2009 | $240,000 |
| Ongoing Annual | Total Funds | $240,000 |

- $80,000 for one FTE re-entry employment liaison plus administration will be earmarked for Target Population #2.  The contract related to Target Population #2 is managed by DAJD/CCD, which will issue a new Request for Proposals (RFP).

| Target Population #2 – Reentry Employment Liaison |
| --- |
| Dates | Activity | Funding |
| Sept – Nov 2008 | Develop and issue RFP, competitive bidding process, selection of provider, contract negotiations |  |
| December 2008 | Start-up for selected provider to hire and train 1 FTE re-entry employment liaison | $6,000 |
| Sept – Dec 2008 | CCD Administration | $1,500 |
|  | Total Funds 2008 | $7,500 |
| Jan – Dec 2009 | Funding pays for 1.0 FTE contracted salary and benefits, office space, and equipment. | $76,500 |
| Jan – Dec 2009 | CCD Administration | $3,500 |
|  | Total Funds 2009 | $80,000 |
| Ongoing Annual | Total Funds | $80,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers (and where possible FTE capacity added via this strategy):

- Target Population #1: The strategy currently involves a single provider, Sound Mental Health (SMH), and will increase RCMS staffing capacity for Target Population #1 by adding 3.0 FTE to the current 1.3 FTE Re-entry case managers.  This increase allows staff to be sited both downtown near KCCF, WER and CCAP as well as in South King County near the RJC.  The provider agency will assist with providing office space for the Re-entry Case Managers serving South and East King County.

- Target Population #2: This strategy will involve a single provider who will be contracted by King County DAJD/CCD following a successful bid for services via a RFP process. The 1.0 FTE Re-entry Employment Liaison staff will be sited downtown near KCCF, WER and CCAP.

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

- Target Population #1: SMH has developed a complete job description and classification, training requirements, and standard operating procedures for the Re-entry Case Manager position.  The existing SMH Criminal Justice Liaison and Re-entry Services Program Manager and Re-entry Case Managers will provide orientation and training.  Technical Assistance with be

provided by King County MHCADSD/Criminal Justice Initiative (CJI) Staff.  Training includes, but is not limited to:

  - Working with mentally ill and chemically dependent offenders

  - Staff Safety

  - Working knowledge of community-based resources throughout King County

  - System navigation (State, County, City)

  - Working with the criminal justice system (jails, courts, public defense, probation)

- Target Population #2: The selected provider agency will develop a complete job description and classification, training requirements and standard operating procedures for the Re-entry Employment Liaison position, as approved by CCD.  Technical Assistance will be provided by King County DAJD/CCD Administrator for Re-entry and Education Programs and Services.  An orientation and training will be provided by the King County DAJD community programs staff at KCCF and RJC.  Other training, including Gordon Graham’s Breaking Barriers series and case management trainings available from KCJI, will be provided to increase the staff’s knowledge of safety issues, employer/employment-related case management, and build effective strategies for working with populations with criminal history.

- C.	Partnership/Linkages

This strategy involves cooperation and collaboration between the MHCADSD and CCD, which manage separate contracts for the services described in this strategy.  MHCADSD intends to amend its existing contract with Sound Mental Health to expand services for Target Population #1 and add capacity.   CCD intends to issue a Request for Proposal and award a contract with a community-based provider to provide employment and vocational focused services for Target Population #2.  Other partnerships involved in increasing employment services include Worksource and the Division of Vocational Rehabilitation.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

- Target Population #1: Sound Mental Health will recruit and hire the additional 3.0 FTE staff to expand services for Target Population #1 and add capacity.  At least 2.0 FTE will be sited in South King County.  The expected timeline for this is 45 to 60 days after the provider is notified.  Eligible candidates will need to be approved for jail clearance by the DAJD.

- Target Population #2: Once funding is secured, CCD will develop and release a RFP.  The expected timeline from development to contract award notification is three to four months.  The 1.0 FTE staff will be recruited and hired within one month of award notification and execution of a contract. Eligible candidates must be approved for DAJD clearance to enter a King County jail.  Direct services can be provided in the provider office and in the community only until such candidate

has obtained clearance, which takes approximately 30 days. Overall implementation is expected to take approximately six months.

  - B.	Procurement of Providers

MHCADSD currently contracts with Sound Mental Health for RCMS services.  Since this is an expansion of an existing program, no RFP is required.  King County contract staff will amend the existing SMH contract to add funding and positions dedicated to the program.

Procurement of a provider for Reentry Employment Liaison services will be completed no later than November 30, 2008.

- C.	Contracting of Services

Target Population #1: See previous section pertaining to MHCADSD contract.

Target Population #2: CCD plans to contract for Reentry Employment Liaison services by January 1, 2009.  If funds are available, the contract may begin December 2008 to include one month of start-up.

- D.	Services State Date(s)

Target Population #1:  October 1, 2008

Target Population #2:  January 1, 2009

Strategy Title:	Expand Re-entry Programs

Strategy No:	12b – Hospital Re-entry to the Community Respite Beds

County Policy Goal Addressed

- A reduction of the number of people with mental illness and chemical dependency using costly interventions like jail, emergency rooms and hospitals.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

Homeless people with mental illness and/or chemical dependency often stay in local hospitals longer than medically necessary due to the challenges hospitals face in finding placement options to meet the complex needs of these individuals.  Current programs do not meet these needs.  A recent survey conducted by four local hospitals over a six- week period identified 333 homeless people who needed housing upon discharge.  These people spent a total of 244 days in the hospital due solely to the lack of a safe placement, representing an estimated annual cost of three million dollars.  The existing Medical Respite Program, a collaborative project between Health Care for the Homeless Network (HCHN) and Harborview Medical Center’s Pioneer Square Clinic, is at capacity and provides recuperation options for some types of patients, but is not able to serve those with more complex medical and behavioral health needs.  In addition, the network of boarding and nursing homes is challenged to serve individuals with current substance abuse and/or mental illness.

- B.	Reason for Inclusion of the Strategy

There is a pressing need for hospital beds, and particularly psychiatric beds, in King County.  About one out of every four individuals detained under the mental illness involuntary commitment law has had to be held in emergency rooms and hospitals.  These facilities are not licensed for involuntary treatment services due to unavailability of psychiatric in-patient beds.  This practice, which is a national problem, is called “boarding”.  Freeing up capacity on psychiatric units by discharging individuals when they no longer require a hospital level of care would reduce the incidence of boarding, reduce hospital costs, and assist individuals in their recovery.  Individuals with mental illness and/or chemical dependency, along with ongoing medical needs, also are often kept longer than necessary on inpatient medical units and in the emergency department.  These individuals also need a new recuperative care resource, including medical and psychiatric monitoring and intensive case management, to help them re-enter the community and begin their recovery.

- C.	Service Components/Design

The proposed service model being considered by the Respite Expansion/ Hospital Discharge Project planning group includes one or more facilities equipped to accept individuals being discharged from hospitals and staffed by health care professionals,  mental health and chemical dependency professionals, and discharge planners.  Services would include case management, medical (including medication) management, transportation to appointments and housing options, and the provision of basic needs (food, hygiene, laundry, etc.) while in the program.  Case management will be focused on linking homeless people to more stable housing and ongoing medical and mental health care and substance abuse treatment.

- D.	Target Population

Homeless persons with mental illness and/or chemical dependency who require short-term medical care upon discharge from hospitals.

- E.	Program Goal

Develop expanded respite care options for homeless individuals with mental illness and/or chemical dependency being discharged from hospitals.  Provide case management services to help these individuals access permanent supported housing, if needed.

- F.	Outputs/Outcomes

Estimated 350-500 individuals served per year, depending on the final service model.

Reduce the length of hospital stay for the target population.  This will reduce public costs for these individuals, free up capacity for those in need of a hospital level of care, and reduce the boarding of involuntarily detained individuals in emergency rooms and on medical units.

2.	Funding Resources Needed and Spending Plan

| Dates | Activity | Funding |
| --- | --- | --- |
| April-Sept 2008 | Continued planning under auspices of Medical Respite Expansion Project |  |
| Sept-December 2008 | Hire consultant/facilitator to complete planning | $20,000 |
|  | Total Funds 2008 | $20,000 |
| Jan–March 2009 | Find facility and finalize design. (retain consultant) | $15,000 |
| March-June 2009 | RFP and contracting process |  |
| June-Aug 2009 | Start-up : Hire and train staff; buy medical equipment, furniture, supplies, etc. | $85,000 |
| Sept-Dec 2009 | Services begin | $190,000 |
|  | Total Funds 2009 | $290,000 |
| Ongoing Annual | Total Funds | $565,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and Type of Providers (and where possible FTE capacity added via this strategy)

To be determined

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

To be determined

- C.	Partnership/Linkages

In June 2007, Public Health-Seattle and King County convened a workgroup to address the issues of recuperative care needs and hospital discharge of homeless patients and the need for a system-wide approach to developing and managing placement options.  Participants in this workgroup have included representatives from Harborview, Swedish, University of Washington, and Virginia Mason Medical Centers; the Committee to End Homelessness in King County; King County Mental Health, Chemical Abuse and Dependency Services Division; Life Care Centers; Downtown Emergency Service Center; City of Seattle Human Services Department, King County Office of Management and Budget; and United Way.  The planning group is continuing to meet, and this planning process includes potential use of the MIDD Sales Tax Funds for the component of the hospital discharge plan that would provide the critical mental health and chemical dependency services for the individuals in the respite program.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

Development of recommendations for model		Nov. 2007-June 2008

Develop agreements among stakeholders

regarding financing, responsibilities, policies 		July -December 2008

Find facility, complete specifics for plan 			Sept.-Dec. 2008

RFP/contracting process 					March –June 2009

- B.	Procurement of Providers

RFP process (if needed under final plan) for

mental health and chemical

dependency services component of plan		March-June 2009

- C.	Contracting of Services

Complete contracts				June 2009

- D.	Services Start Date(s)

Hire and train staff					June-Aug 2009

Open for services					September 2009

Strategy Title:	Expand Re-entry Programs

Strategy No:	12c – Increase Capacity for Harborview’s Psychiatric Emergency Services to Link Individuals to Community-Based Services upon Discharge from the Emergency Room

County Policy Goals Addressed:

- A reduction of the number of people with mental illness and chemical dependency using costly interventions like jail, emergency rooms and hospitals.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

This strategy was proposed during the original development of the Mental Illness and Drug Dependency Action Plan (MIDD) as a way of addressing the needs of individuals who are repeatedly admitted to Harborview Medical Center’s Psychiatric Emergency Services (PES) and to the Emergency Department (ED) as a whole, due to substance abuse and/or mental illness.  In 2007, there were over 6000 admissions to PES and over 80,000 to the entire ED.  In 2006, there were 332 individuals identified as the highest utilizers of ED services.  Of these 332 people, 62% were homeless, 49% were diagnosed with a mental illness and 74% were diagnosed as substance dependent.  In addition, over 70% of these 332 individuals had a significant medical illness that required treatment in the Emergency Department.  Without referral and linkage to housing and services, many will continue to return frequently in the future.  Increasing visits of high utilizers contributes to PES and ED crowding, thus increasing the number of individuals with mental illness and chemical dependency who are directed to other hospital emergency departments across King County.

- B.	Reason for Inclusion of the Strategy

Hospital emergency departments are increasingly experiencing difficulty in placing individuals who are frequent users of emergency services due to mental illness, homelessness and chemical dependency.  Emergency rooms are a very expensive resource, and individuals, and the public, would be better served if community service alternatives were provided to reduce the use of emergency services.

- C.	Service Components/Design

The final service design has not been determined at this time.  There are a number of programs targeting homeless individuals who are high utilizers of emergency medical services and jails that are being developed in the next year, and it is critical that these efforts be well-coordinated in order to reduce duplication of effort and to achieve the most efficient and effective results.  The High Utilizer Referral System is a major effort underway to serve homeless individuals who are frequently involved

with the criminal justice and hospital emergency systems.  Funding is provided by the Veterans and Human Services Levy and the United Way Campaign to End Chronic Homelessness.  The Service Improvement Plan being developed this year includes a redesign of the Emergency Services Patrol and Dutch Shisler Sobering Center, increased outreach and service engagement for individuals with chemical dependency and improved coordination among key stakeholders to identify high utilizers of criminal justice and emergency medical services in order to facilitate placement into dedicated supported housing.  In addition, strategy 1b in the MIDD targets this same population and includes providing outreach and engagement for individuals being discharged to shelters from hospitals and jails.

We propose delaying the final determination of design for this strategy in order to coordinate with these other strategies in order to create a well-coordinated and efficient system for responding to the needs of individuals who are high utilizers of emergency department services and jails.

- D.	Target Population

Adults who are frequent users of the Harborview Medical Center ED.

- E.	Program Goal

Provide increased coordination with other initiatives and providers to link individuals who are high utilizers of Harborview ED with ongoing community supports and housing

- F.	Outputs/Outcomes

Outputs will be determined once a final model is developed.

Expected outcomes include increased linkage of individuals to needed community treatment and housing and reduced use of emergency medical services.

2.	Funding Resources Needed and Spending Plan

To be determined.  The budget identified in the MIDD is $200,000 per year to pay for two full-time professional staff and one program assistant.

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers

To be determined

- B.	Staff Resource Develop Plan and Timeline

Still to be developed

Will depend on the model developed through the planning process

- C.	Partnership/Linkages

Stakeholders include Harborview Medical Center, The Committee to End Homelessness, The Veterans and Human Services Levy Boards, United Way of King County, shelter providers, jails, and hospitals throughout King County, the King County Department of Community and Human Services, and Public Health –Seattle and King County.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

To be determined

- B.	Procurement of Providers

To be determined

- C.	Contracting of Services

To be determined

- D.	Services Start Date(s)

To be determined

Strategy Title:  Expand Re-entry Programs

Strategy No:	12d – Urinalysis Supervision for Community Center for Alternative Program Clients

County Policy Goal Addressed:

- A reduction of the number of people who cycle through the jail, returning repeatedly as a result of their mental illness or chemical dependency.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

The King County Community Center for Alternative Programs (CCAP) is an effective diversion resource for individuals who no longer need secure detention but who are required by a court to complete certain conditions for release, such as urinalyses.  This strategy will increase the efficiency in operation of CCAP.  Currently, community corrections staff conducts urinalyses on their clients to assure compliance with court requirements.

- B.	Reason for Inclusion of the Strategy

It is more cost-efficient and clinically appropriate to have designated non-Community Corrections staff perform this service.  In addition, the Community Corrections staffing patterns do not always assure that staff of the same gender as the client is available to complete the monitored urinalyses.

- C.	Service Components/Design (Brief)

A contract with an independent agency for a Urinalysis Technician(s) to provide analyses for both female and male clients of CCAP will be developed.  Urinalyses will be done for those who are ordered by the court to have one or more urine samples taken and analyzed each month.  Monitored urinalyses samples will be taken on-site at the CCAP location (presently located in the Yesler Building in Seattle).

- D.	Target Population

King County Community Center for Alternative Program clients who have been mandated by Superior Court or District Court to report to CCAP and participate in treatment

- E.	Program Goals

An increase in the efficiency of the services offered at CCAP.  Assure gender-specific staff is available for the collection of urine samples.

- F.	Outputs/Outcomes

Increased number of urinalyses each month collected and a decrease in CCAP staff time dedicated to providing this service.

2.	Funding Resources Needed and Spending Plan

| Dates | Activity | Funding |
| --- | --- | --- |
| Sept- December | Plans for office space and equipment are finalized with Facilities by CCD. Funding pays for office space modifications and fixtures. Request for Proposal (RFP) developed, issued and rated and contract negotiated. | $20,000 |
|  | Total Funds 2008 | $20,000 |
| Jan – Dec 2009 | New provider begins urinalyses on schedule determined by CCD. | $75,000 |
|  | Total Funds 2009 | $75,000 |
| Ongoing Annual | Total Funds | $75,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers (and where possible FTE capacity added via this strategy)

A single provider of one FTE will be needed.  Time and staffing will need to include both male and female Urinalysis Technicians.

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

Current staff resources at Mental Health, Chemical Abuse and Dependency Services Division (MHCADSD) and Community Corrections Division (CCD) are adequate to develop the request for proposals and establish a timeline for the project.

- C.	Partnership/Linkages

This strategy will involve a partnership with the King County Department of Adult & Juvenile Detention/Community Corrections Division (CCD) that operates CCAP.  MHCADSD/CJI staff will work with CCD/CCAP managers to plan for locating space for monitoring and processing of urinalyses and developing a request for proposals upon approval.  Planning will include the securing of necessary office space and equipment and outlining referral and processing protocols between CCAP Case Workers and the contracted provider.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

| Dates: | Activity: |
| --- | --- |
| Sept- December 2008 | Plans for office space and equipment are finalized with Facilities by CCD. Funding pays for office space modifications and fixtures (portable fixtures will be considered as an option). |
| Sept- December 2008 | RFP developed, issued and rated, and contract negotiated. |
| Jan – Dec 2009 | Contract issued. New provider begins urinalyses on schedule determined by CCD. |

- B.	Procurement of Providers

Sept - November 2008 – RFP developed, issued and rated. and award selection/notification made.

- C.	Contracting of Services

December 2008  - Contract negotiations completed.

- D.	Services Start Date(s)

Services to clients will begin February 1, 2009.

Domestic Violence, Sexual Assault, and Expansion of Adult Drug Court

13a – 15a

Strategy Title:	Mental Health Services for Domestic Violence Survivors with Associated Coordination and Training

Strategy No:	#13a Domestic Violence/Mental Health Services and System Coordination

Policy Goal Addressed:

- A reduction in the incidence and severity of chemical dependency and mental and emotional disorders in youth and adults.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

Individuals who experience ongoing abuse by an intimate partner (“survivors”) are at increased risk for developing depression, post-traumatic stress disorder (PTSD), and other mental health problems. Analysis of research studies across multiple settings serving battered women, including hospital emergency rooms, and psychiatric settings, indicated that an average of 48% of women were experiencing depression and 64% were experiencing PTSD.

There are many access barriers to survivors of domestic violence (DV) who have mental health and substance abuse concerns.  DV survivors experience unique safety concerns due to stalking, threats, physical violence, and ongoing emotional abuse by their abusive partners.  Nationally and in King County, providers of mental health and substance abuse treatment services are often unfamiliar with the needs of DV survivors.  Many providers of DV services are unfamiliar with screening for or responding to mental health and substance abuse issues.  As a result of these and other barriers, DV survivors who need mental health services are often either not identified or are unable to receive services.

Community-based DV advocacy programs in King County currently provide a broad range of services to DV survivors, including safety planning, support, shelter and transitional housing, assistance with employment, etc. at confidential locations.  These programs do not currently have the ability to assess for or respond to survivors’ mental health concerns.  Nationally and in King County, providers of mental health and substance abuse treatment services often do not have the ability to assess for or respond to the unique safety and support needs of DV survivors.

- B.	Reason for Inclusion of the Strategy

Services described in this strategy will increase access to early intervention for mental health and substance abuse issues, and prevention of severe mental health and substance abuse issues for survivors of DV, throughout King County.

As described above, many DV survivors who are experiencing or are at-risk for significant mental health and substance abuse problems can not access services.  This can have a negative impact on their functioning, their safety, and their ability to leave abusive relationships. DV survivors from East African, Eastern European, South Asian and other immigrant and refugee communities, face the additional barrier of the lack of available culturally-appropriate mental health services.

The  2006 Safe and Bright Futures report and 2006 WA State Coalition Against Domestic Violence Fatality Review Project report recommend that mental health and substance abuse professionals and domestic violence programs:  a) collaborate on cross-training in order to increase their ability to provide the appropriate range of services to domestic violence survivors who are suicidal or have other mental health concerns, and b) coordinate services and ensure systematic changes to agency policies, procedures and practices.

- C.	Service Components/Design

Licensed mental health professionals (MHPs) with expertise in DV and substance abuse will be employed by community-based domestic violence victim advocacy programs around King County to provide assessment and mental health treatment to DV survivors.  Treatment will include brief therapy, and mental health support, in group and/or individual sessions. MHPs will provide assessment and referrals to community mental health and substance abuse agencies for those DV survivors who need more intensive services.  One of these MHPs will be housed at an agency serving immigrant and refugee survivors of DV.  Mental health professionals will offer consultation to DV advocacy staff and staff of community mental health or substance abuse agencies.   In addition, a Systems Coordinator/Trainer will be funded to coordinate ongoing cross training, policy development, and consultation on DV and related issues between mental health, substance abuse, sexual assault and DV agencies throughout King County.

- D.	Target Population

- DV survivors who are experiencing mental health and substance abuse concerns will have access to early intervention services and prevention of severe mental health and substance abuse issues.

- Providers at sexual assault, mental health, substance abuse, and domestic violence agencies who work survivors of DV with mental health and substance abuse/substance abuse issues and participate in the coordination and cross training work of this program.

- E.	Program Goal

Integrate mental health services within community-based domestic violence agencies, making them accessible to DV survivors.  Improve screening, referral, coordination and collaboration between mental health, substance abuse, domestic violence and sexual assault service providers.

- F.	Outputs/Proposed Outcomes

Total number of clients served per year: 175-200

Total numbers of counselors and advocates trained per year: 200

Expected outcomes for Domestic Violence survivors served

- Increased access to mental health and substance abuse treatment services for domestic violence survivors

- Culturally relevant mental health services provided to DV survivors from immigrant and refugee communities in their own language

- Decreased mental health concerns among DV survivors served

- Increased resiliency and coping skills among DV survivors served

Expected System Outcomes

- Consistent screening for DV among participating mental health and substance abuse agencies, and increased referrals to DV providers

- Consistent screening for mental health and substance abuse needs among DV agencies

- Improved ability of DV, sexual assault, mental health and substance abuse providers to serve individuals with DV and mental health issues

2.	Funding Resources Needed and Spending Plan

| Dates | Activity | Funding |
| --- | --- | --- |
| October-December, 2008 | Funding for start-up, equipment, administrative costs | $31,000 |
| January-December 2009 | Funding for 3.5 MHPs and a.5 FTE systems coordinator/trainer, as well as interpreter services, to provide services and service coordination. (Funding includes administrative costs) Training is provided to DV, substance abuse, and mental health providers on screening protocols. Coordination efforts are put in place. | $310,000 |
| 2009 | Total Funds | $310,000 |
| Ongoing Annual | Total Funds | $310,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and Type of Providers (and where possible FTE capacity added via this strategy)

Providers will provide regional access to services: Domestic Abuse Women’s Network in South King County, Eastside Domestic Violence Program on the Eastside, and New Beginnings for Battered Women and their children in Seattle.  The DV program at Refugee Women’s Alliance (REWA), which serves 16 language communities, will house a mental health provider to serve refugee and immigrant survivors.  The King County Coalition Against Domestic Violence will house the .5 FTE systems coordinator/trainer, as this community-based coalition has unique leadership with and access to all of the community-based DV agencies, as well with Community Sexual Assault Providers described in #14a in King County.

3 MHPs added to community-based DV agencies

.5 FTE MHP housed at culturally-specific provider of domestic violence and sexual assault advocacy services (linking with the .5 FTE in the Sexual Assault Services strategy 14a)

.5 Systems Coordinator/Trainer (linking with the .5 FTE in the Sexual Assault services strategy 14a).

Interpreters for service provision to immigrant and refugee survivors at REWA

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

| Dates: | Activity: |
| --- | --- |
| October-December 2008 | Start up (hire and train MHPs at DV agencies and hire systems coordinator) |
| January 2009 | Staff at DV agencies work with staff at mental health agencies to develop protocols for service provision at DV agencies |
| February-March 2009 | Protocol development and staff training continue. |
| March 2009 | Services begin. |
| May-December 2009 | Services continue Training is provided to DV, sexual assault, substance abuse, and mental health providers on screening protocols, coordination efforts in place |

- C.	Partnership/Linkages

This strategy will involve a partnership between community based DV agencies,  mental health and substance abuse treatment programs, and sexual assault agencies.  Mental health professionals will consult with and refer to staff of the Domestic Violence Early Intervention/Prevention program described in strategy 13b.  In addition, there will be linkages with the DV and Mental Health Collaboration funded by the Office on Violence Against Women through the City of Seattle.

Note: This strategy is linked with the sexual assault strategy, which will fund also fund an .5 FTE systems coordinator and trainer to providing systems coordination and training on sexual assault issues, and an .5 FTE MHP to serve immigrant and

refugee victims of sexual assault who are experiencing mental health and substance abuse concerns.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

Staff identified and hired by January 31, 2009

Services to DV survivors begin March, 2009.

Systems coordination and training efforts begin March 2009.

- B.	Procurement of Providers

The strategy is designed to be implemented within the DV provider community by agencies providing a full continuum of services, including emergency shelter, transitional housing and community-based advocacy programs.  The County will contract with the three large regional providers of this service continuum, as well as with the Refugee Women’s Alliance, which is uniquely positioned to serve survivors from refugee and immigrant communities.  DV agencies offer services in confidential locations, and have a high level of statutory protection for client records and client communication (Relevant statutes are RCW 5.60.060 (8), 70.123.075, 70.123.076).

- C.	Contracting of Services:

See above.

- D.	Services Start date(s)

March 2009.

Strategy Title:	Provide early intervention for Children Experiencing Domestic Violence and for Their Supportive Parent

Strategy No:	#13b – Domestic Violence Early Intervention/Prevention

Policy Goal Addressed:

- A reduction in the incidence and severity of chemical dependency and mental and emotional disorders in youth and adults.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

Approximately 60,000 children in King County are exposed to domestic violence (DV) each year.  In King County, there are a broad range of services available to adult victims and adult perpetrators of DV, as well as mental health services for adults and for children.  However, there are no specialized counseling services in the King County region to help children recover from DV.

Children who experience DV are at great risk for becoming aggressive, antisocial, withdraw, or fearful and for having poor social skills.  They often experience high levels of anxiety and depression and other symptoms of trauma.  The strongest known risk factor for becoming a DV perpetrator is witnessing DV as a child.  A study conducted in King County found that increased exposure to violence was associated with lower cognitive functioning and that exposed children were more likely to be suspended from school.

The Safe and Bright Futures project was a two-year federally-funded community planning project involving several community partners led by the Health Department and the Department of Judicial Administration.  The project conducted a needs assessment and developed recommendations to improve regional responses to children affected by DV in King County.  The priority recommendation of the plan was to develop and implement a Children’s DV Response Team to provide direct services to children who experience DV.

A very small pilot project was begun in South King County 2007 through Sound Mental Health (Tukwila office), Domestic Abuse Women’s Network, and the South King County YWCA.  This pilot currently serves 10 families at a time.  MIDD funds would allow for program expansion to families throughout South King County, where there is the greatest need for services.

- B.	Reason for Inclusion of the Strategy

Currently there is no integrated mental health and DV advocacy service in King County to meet the unique needs of children who experience DV.  Provision of these services will help to reduce the negative mental health impacts on children who experience DV, strengthen the child’s relationship with their supportive parent, and their linkages to other supportive people in their lives.  In addition the project has potential to reduce the risks of future battering, victimization and associated behavioral problems among children served, thereby reducing the prevalence of DV in the community in the long-term.

- C.	Service Components/Design

A team will provide mental health and advocacy services to children, ages 0-12 who have experienced DV, and support, advocacy and parent education to their non-violent parent.  The team will consist of a children’s mental health therapist, a children’s DV advocate, and other team members as identified by the family (including supportive family members, case workers, teachers, etc.).  Children will be assessed through a parent and child interview, and use of established screening tools. Children’s treatment will include evidence-based Trauma Focused Cognitive Behavioral-Therapy, as well as Kids Club, a tested group therapy intervention for children experiencing DV.   Children and families will be referred through the DV Protection Order Advocacy program, as well as through other partner agencies.

- D.	Target Population

Children who have experienced DV and are identified by their parents, teachers and providers as needing services, and their supportive parents, who are residents of King County.

- E.	Program Goal

Develop and maintain an evidence-based intervention for children who experience DV and their supportive parent.

- F.	Outputs/Outcomes:

Team members will provide ongoing services annually to approximately 85 families with 150 children.  Services will include one or more of the following: therapeutic intervention, service coordination and connection, and advocacy and support.

Projected outcomes to include:

- Decrease trauma symptoms exhibited by children.

- Reduce children’s externalizing behaviors as observed in school, community, and family settings.

- Reduce children’s internalizing behaviors.

- Increase protective/resiliency factors available to children and their supportive parents.

- Reduce children’s negative beliefs related to the domestic violence, including that the violence is their fault, and/or that violence is an appropriate way to solve problems.

- Improve social and relationship skills so that children may access needed social supports in the future.

- Support and strengthen the relationship between children and their supportive parents.

- Increase supportive parents’ understanding of the impact of domestic violence on their children, and ways to help.

- Increase the awareness of the impact of DV on children among other supportive adults in the children’s natural environment so that they may support the family in positive change.

2.	Funding Resources Needed and Spending Plan

| Dates | Activity | Funding |
| --- | --- | --- |
| September-December 2008 | Start-up (Hire, train and orient staff), develop subcontracts and begin providing services | $70,000 |
|  | Total Funds 2008 | $70,000 |
| January-December 2009 | Provide services to children and their supportive parent 1 FTE lead children’s mental health clinician at Sound Mental Health 1 FTE children’s DV advocate at DAWN 1 FTE children’s DV advocate at the South King County YWCA | $200,000 |
| Ongoing Annual | Total Funds | $200,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of providers (and where possible FTE capacity added via this strategy):

This strategy involves one provider and its two subcontractors who were involved in regional planning for this project, and in a small ongoing pilot to initiate services in 2007-2008: (Sound Mental Health, Domestic Abuse Women’s Network (DAWN) and the South King County YWCA).  One lead clinician will be added at Sound Mental Health.  Two FTEs children’s DV advocates will be added at the subcontractors.

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

A pilot team from these three agencies has already begun providing services to a small number of families in South King County.  Program protocols were developed through a small start-up grant in 2007.

| Dates: | Activity: |
| --- | --- |
| September- December 2008 | Funding to Sound Mental Health and the two sub contractors. Hire and train program staff. Update and expand program protocols. Coordination with referral sources to generate additional referrals. |
| January 2009-December 2009 | Services provided to children and families. |

- C.	Partnership/Linkages

This strategy will involve a partnership between the three listed agencies, as well as the DV Protection Order Advocacy Program, schools, Child Protective Services, Safehavens Supervised Visitation Center at the Regional Justice Center, and other relevant agencies.  Staff will consult with and refer to staff of the Mental Health Services for Domestic Violence Survivors program described in strategy 13b.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline:

Staff identified, hired, and trained September-December 2008

Services begin January 1, 2009

- B.	Procurement of Providers

MHCADSD already contracts with Sound Mental Health.  A contract amendment would allow for funding of this program.

- C.	Contracting of Services

See previous

- D.	Services Start date

Services to children and families will begin January 1, 2009.

Strategy Title:	Expand Access to Mental Health Services for Survivors of Sexual Assault

Strategy No:	14a-Sexual Assault Services

Policy Goal Addressed:

- Reduction in the incidence and severity of chemical dependency and mental and emotional disorders in youth and adults.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

One third of women in King County will have a sexual assault experience during their lifetime, based on the Washington State Prevalence Survey.  Of these women, at least 30% will develop Post Traumatic Stress Disorder (PTSD), a trauma-specific diagnosis, or depression.  These women will have higher rates of binge drinking and drug use than women who have not experienced sexual assault, as well as co-morbid depression and substance abuse disorders.  In the study sample, 80% of the women’s experiences had occurred by the age of 18.  The prevalence study only included women, but men are sexually assaulted as well and have comparable rates of mental health conditions. Virtually all sexual assault victims are affected by their experiences and have at least some distressing mental health symptoms. There is effective treatment; however, victims frequently cannot access treatment for the following reasons:

- A significant number of victims do not have insurance and therefore have limited access to specialized mental health services. Some are experiencing impaired functioning but their symptoms are not severe enough to enable them to qualify for services at public mental health programs.  Those victims who do not get access to timely treatment may deteriorate or develop maladaptive ways of coping such as abusing substances.

- Public mental health programs do not always have the specialized expertise to deliver the proven treatments combined with advocacy and support services. Their treatment focus is often on other urgent problems and needs for victims that do not include the impact of the victimization.

- For sexual assault victims from many immigrant and refugee communities, there are no cultural and sexual assault-specific mental health or substance abuse services available.

Washington State is a national leader in providing integrated services to sexual assault victims through Community Sexual Assault Programs (CSAPs).  In 1995, recognizing the unique service needs of sexual assault victims, the Washington State Office of Crime Victim’s Advocacy established the CSAP model to ensure that sexual assault victims would receive uniform, integrated services throughout the state.  CSAPS must be accredited, and are required to meet specific service training requirements, participate in a common data collection system, provide legal and

medical advocacy, prevention education, case management, therapy or access to therapy, and a 24-hour response.  In King County the accredited CSAP programs provide evidence-based cognitive-behavioral therapy integrated with the other sexual assault advocacy services described above.  For example, a child victim who has been abused, is experiencing PTSD, and has to go to a trial as a witness, receives integrated legal and medical advocacy, therapy and support through a single program.  The four Community Sexual Assault Programs (CSAPs) in King County have limited capacity and funding for treatment (for example, for every client accepted at the King County Sexual Assault Resource Center for mental health treatment, eight were turned away/ referred out).

- B.	Reason for Inclusion of the Strategy

This strategy will increase access to early intervention services for mental health issues, and prevention of severe mental health issues for survivors of sexual assault  throughout King County, and increase coordination between programs serving sexual assault survivors who are experiencing mental illness, substance abuse and domestic violence.

- C.	Service Components/Design

Expand the capacity of Community Sexual Assault Programs (CSAPs) and culturally specific providers of sexual assault advocacy services to provide evidence-based mental health services to adult and child victims of sexual assault throughout King County.   Increase access to services for women and children from immigrant and refugee communities by housing a mental health provider specializing in evidence-based trauma-focused therapy at an agency serving these communities. Develop consulting relationships between specialized providers of sexual assault services and community mental health agencies to ensure mental health treatment that addresses the specific trauma of sexual assault.   A Systems Coordinator/Trainer will coordinate ongoing cross training, policy development, and consultation on sexual assault and related issues between mental health, substance abuse, sexual assault and DV agencies.

- D.	Target Population

- Adult, child and youth survivors of sexual assault who are experiencing mental health and substance abuse concerns will have access to early intervention services and prevention of severe mental health issues.

- Providers at sexual assault, mental health, substance abuse, and domestic violence agencies who work survivors of DV with mental health and substance abuse issues and participate in the coordination and cross training work of this program.

- E.	Program Goal

Increase access to evidence-based and culturally-appropriate services for adult and child victims of sexual assault with mental health and advocacy needs.  Improve

screening, referral, coordination and collaboration between mental health, substance abuse, domestic violence and sexual assault service providers.

- F.	Outputs/ Outcomes

Expected Outcomes for Sexual Assault survivors served:

- Therapy and case management services provided to 400 adult, youth and child victims of sexual assault.

- Increased access to services for adult, youth and child victims who currently do not have access to specialized sexual assault services.

- Reduction in trauma symptoms for adult, youth and child victims of sexual assault receiving services.

- Culturally relevant mental health services provided to sexual assault survivors from immigrant and refugee communities in their own language

- Increased resiliency and coping skills among sexual assault survivors served

Expected System Outcomes

- Increased coordination between public mental health programs and CSAPS to better serve sexual assault victims.

- Increased coordination between CSAPS and culturally specific providers of sexual assault advocacy services.

- Improved ability of sexual assault, domestic violence, mental health and substance abuse providers to serve individuals with DV and mental health issues.

2.	Funding Resources Needed and Spending Plan

This program requires $500,000 of MIDD funds annually to expand the regional capacity to provide evidence-based trauma-focused therapy to adult, youth and child victims of sexual assault throughout King County.

| Date | Activity | Funding |
| --- | --- | --- |
| Sept 2008 October-Dec 2008 | Providers identify, hire and train staff Begin service provision | $110,000 |
|  | Total Funds 2008 | $110,000 |
| Jan – Dec 2009 | Service provision continues. Establish and maintain consultation between CSAPS and mental health providers. Provide annual training in evidence-based therapy for PTSD and depression in child, youth and adult sexual assault victims. | $500,000 |
|  | Total Funds 2009 | $500,000 |
| Ongoing Annual | Total Funds | $500,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and Type of Providers (and where possible FTE capacity added via this strategy)

- 4 FTES added to CSAP agencies.

- .5 FTE added for Mental Health Provider housed at culturally-specific provider of sexual assault and domestic violence advocacy services (linking with the .5 FTE in the domestic violence proposal for the MIDD)

- .5 Systems Coordinator/Trainer (linking with the .5 FTE in the domestic violence services strategy 14a).

- Funds for interpreters for services to immigrant and refugee survivors

Providers will be the accredited CSAP agencies providing services throughout King County.  The Refugee Women’s Alliance will house a mental health provider to serve refugee and immigrant victims of sexual assault, as this program serves sexual assault survivors from 16 different language communities.  The King County Coalition Against Domestic Violence will house the .5 FTE systems coordinator/trainer.

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

| Dates: | Activity: |
| --- | --- |
| Oct-Dec 2008 | CSAPS begin service provision Staff of CSAPS and culturally-specific provider collaborates to develop protocols for culturally specific provider to incorporate MHP onto staff. |
| Jan – Dec 2009 and ongoing | CSAPS continue service provision. MHP at culturally-specific provider agency begins service provision. Coordination efforts begin. CSAPS, mental health providers and culturally-specific providers establish consult group re service provision to sexual assault victims, and consult on complex cases. Annual training for mental health providers in providing evidence-based therapy for PTSD and depression in child, youth and adult sexual assault victims. |

- C.	Partnership/Linkages

The CSAPs, public mental health agencies, and culturally specific providers of sexual assault advocacy services will work together to strengthen and maintain existing partnerships to improve the quality of mental health services available to victims of sexual assault.  The project will partner with all member agencies of the King County Sexual Assault Coalition.

Note:	This strategy is linked with the domestic violence strategy, which will also fund an .5 FTE systems coordinator and trainer to providing systems coordination and training on sexual assault issues, and an .5 FTE MHP to serve immigrant and refugee victims of sexual assault who are experiencing mental health concerns.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

- Staff identified and hired by or before September 30, 2008

- Services at CSAPS begin October 2008.

- Services at Refugee Women’s Alliance will begin January 2009

- System coordination efforts begin January 2009.

- B.	Procurement of Providers

The strategies are designed to be implemented within the Community Sexual Assault Provider agencies.  The County will contract with the accredited CSAP programs, with the Refugee Women’s Alliance, which is uniquely positioned to serve survivors from refugee and immigrant communities, and with the King County Coalition Against Domestic Violence (as described in #13a).  CSAP programs have a high level of statutory protection for client records and client communication (Relevant statutes are RCW 5.60.060 (8), 70.123.075, 70.123.076).

C.	Contracting of Services:

- D.	Services Start Date(s)

October 2008

Strategy Title:	Enhancement Services for King County Adult Drug Diversion Court

Strategy No:	15a –Drug Court: Expansion and Enhancement of Recovery Support Services

County Policy Goals Addressed:

- Diversion of youth and adults with mental illness and chemical dependency from initial or further justice system involvement.

- Explicit linkage with, and furthering of, other council directed efforts including the Adult and Juvenile Justice Operational Master Plans, the Ten-Year Plan to End Homelessness in King County, the Veterans and Human Services Levy Service Improvement Plan and the Recovery Plan for Mental Health Services.

- A reduction of the number of people who cycle through the jail, returning repeatedly as a result of their mental illness or chemical dependency.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

This strategy funds critical gaps in services to individuals in the King County Adult Drug Diversion Court.   State funding that supports drug courts can only be used for Division of Alcohol and Substance Abuse approved chemical dependency treatment and transportation services.  In order to succeed, drug court defendants need a broad range of recovery support services.   The services must address not only the needs and circumstances of the general drug court population, such as lack of employment and housing, but also those needs endemic to specialized populations served by the program, such as young adults and women. Research is clear that providing additional recovery support services increases the likelihood of long term success and reduces recidivism in both substance use and criminal behavior.  Proposed services include:

- Access to employment and training through dedicated linkage to MIDD strategy 2b.

- Housing case management services.

- Access to evidence-based treatment such as multisystemic therapy and wraparound services adapted for the young adult drug court population (ages 18 to 24)

- Access to increased evidence-based treatment for women with co-occurring disorders, substance abuse and other disorders related to trauma such as post-traumatic stress and borderline personality disorders.

- Access to suboxone treatment.  A medication approved for the treatment of opiate dependence.  Currently, opiate dependent clients receiving methadone must go to a limited number of outpatient clinics.  Opiate dependent clients can receive suboxone instead of methadone and receive services in

traditional outpatient agencies.  This change will provide more patients the opportunity to access treatment.

- Access to an educational program – CHOICES.  Designed for adult offenders with learning disabilities and/or attention deficit disorders.

- B.	Reason for Inclusion of the Strategy

The proposed services will increase the likelihood of long-term recovery for drug court participants, and decrease jail days, hospitalization and use of other crisis services.  The specific strategies have been identified and prioritized for the following reasons:

- Access to employment and training - 65% of participants in King County Drug Court are unemployed.

- Access to housing and housing support services - 53 % of King County Drug Court participants have been homeless during the prior 6 months.  An estimated 40% are homeless at the time that they opt-in to the program; an estimated 200 will be in need of housing or residing in subsidized housing at any one time. According to a 2004 report on drug courts and public policy, housing has been identified by most drug court programs as the most immediate and critical need presented by many participants.   The report further notes that regardless of the quality of treatment and other services provided, a defendant who returns daily to a drug using environment will have little chance of overcoming his/her addiction.

Internal housing case management services are needed to assist participants with acquiring supportive recovery oriented housing that will be made available through MIDD and other funding sources.  The housing case manager will provide linkage to necessary services and assist participants in overcoming obstacles to permanent housing such as lack of rental history, prior criminal and poor credit history.

- Enhanced treatment for young adults - Access to evidence-based treatment and ancillary services for the young adult population (ages 18 to 24).  Drug Court participants in this age category would benefit from multi-systemic therapy, wraparound and other proven treatments currently reserved for youth under age 18.   The services would be adapted and individualized for the 18 to 24 year old drug court population currently being served in a specialized age-appropriate program.

- Enhanced and expanded treatment for women with co-occurring disorders undergoing treatment in a women’s program.  Currently approximately 150 women are enrolled in drug court, 15% are enrolled in a specialized women’s program at Harborview Addictions Program. Studies have shown that a majority of women involved in the criminal justice system suffer from trauma-related disorders and are in need of specialized services. Summary Observations from “Information Relevant to Female Participants in Drug Courts:” prepared by: Bureau of Justice Administration Drug Court  Clearinghouse Project Date: February 10, 2007,reports that although significantly more males than females are enrolled in drug courts, many programs report that women participants appear to be more heavily involved with drugs and a drug “lifestyle”(including prostitution) by the time they become involved in the criminal court process than men; this situation necessarily bears on the likelihood of a woman’s success in the program and the special needs they will likely present –

Three of the most significant of which are:

  - The need for clean and sober housing

  - The need for support in dealing with negative relationships which likely keep many women in drugs (e.g., economic, domestic violence, etc.); and

  - The need to deal with the impact of physical and other abuse they have likely experienced.

- Access to the Adult CHOICES program for offenders with leaning disabilities and/or Attention Deficit Disorders.  King County District Court has referred offenders with learning disabilities and/or attention deficit disorders to the CHOICES program designed to address offenders’ difficulties in social skills, anger management, decision making and problem solving since 1989. Graduates of the CHOICES program re-offend 49% less than individuals in the comparison group; the comparison group included people who were screened, received an intake interview and were seen as appropriate for the program but never enrolled or attended classes. These statistics have been consistent since 1988.

Researchers have found that compared to the general population, the offender population, especially those in corrections facilities needing special education include at least 50% of adult prisoners.

Although, King County Drug Court defendants have not been screened for learning disabilities and attention deficit disorder to discern prevalence, a 1998 study of 512 King County Drug Court participants revealed that 31% did not have a high school degree or GED.

- C.	Service Components/Design

Expansion and enhancement of services for King County Drug Diversion Court participants, including, access to employment and training, access to evidence-based treatment for the young adult population (ages 18 to 24), housing case management services, and enhancement and expansion of services for women with co-occurring, substance abuse and trauma related conditions.  The strategy also includes a plan to provide classes designed to attend to social and emotional difficulties posed by learning disabilities and attention deficit disorders.

- D.	Target Population

King County Adult Drug Court participants

- E.	Program Goal

Enhance and expand King County’s Adult Drug Diversion Court’s recovery support services.

- F.	Outputs/Outcomes

450 individual participants will benefit from one or more of the proposed expanded services annually.

- Reduce substance use and related criminal activity.

- Provide resources and support to assist drug dependent offenders in the acquisition of skills necessary for the maintenance of sobriety.

- Reduce the impact of drug related cases on criminal justice resources.

2.	Funding Resources Needed and Spending Plan

Enhancement Services for King County Adult Drug Diversion Court will have an annual cost of $325,000.

The spending plan is as follows:

| Dates | Activity | Funding |
| --- | --- | --- |
| Sept – Dec 2008 | Funding for 1.5 County FTE Housing Case Manager Position Expansion of contract for young adult services, 1 FTE (salary, benefits, administrative overhead). Expansion of contract by 1 FTE to allow expansion of women's group and enhancement of services for women with co-occurring disorders and trauma-related disorders. Funding for suboxone for women in drug court women's group, to be added to existing contract. Contract with the Learning Disabilities Association of Washington to provide the Choices Adult Program to drug court participants. | $38,000 $22,000 $33,000 $3000 $11,000 |
|  | Total Funds 2008 | $107,000 |
| Jan – Dec 2009 | Funding for 1.5 County FTE Housing Case Manager Position Expansion of contract for young adult services, 1 FTE (salary, benefits, administrative overhead). Expansion of contract by 1 FTE to allow expansion of women's group and enhancement of services for women with co-occurring disorders and trauma-related disorders. Funding for suboxone for women in drug court women's group, to be added to existing contract. Contract with the Learning Disabilities Association of Washington to provide the Choices Adult Program to drug court participants. | $115,000 $65,000 $100,000 $10,000 $35,000 |
|  | Total Funds 2009 | $325,000 |
| 2010 and onward | Ongoing program cost | $ 358,000 |
| Ongoing Annual | Total Funds | $358,000 |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and type of Providers (and where possible FTE capacity added via this strategy)

This strategy will provide funding for: 1.5 County FTE’s, 2 contract FTEs through contracts with 2 separate treatment providers and 1 contract for delivery of services from a nonprofit organization, as follows:

- 1.5 County FTE housing case managers, internal to King County Adult Drug Court Program.

- Funding for 1 contract FTE for provision of evidence-based services to young adults (ages 18 to 24) in the adult drug court program will be added to a current contract.

- Funding for 1 contract FTE for expansion of women's group and enhancement of services for women with co-occurring disorders and trauma-related disorders, including suboxone, will be added to a current contract.

- Drug Court will enter into a contract with the Learning Disabilities Association of Washington the CHOICES program to treat 42 offenders. King County District Court and Community Correction Alternatives Program will inform the contract between Drug Court and the CHOICES Program

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc)

| Dates: | Activity: |
| --- | --- |
| June – August 2008 | Recruit for County Housing Case Management positions. |
| Sept – Dec 31, 2008 | Hire housing case management positions |
| Sept – Dec 31, 2008 | Add funds to existing contract for young adult services. |
| Sept – Dec 31, 2008 | Add funds to existing contract for expansion of women's group and enhancement of services for women with co-occurring disorders and trauma-related disorders, including suboxone. |
| Sept – Dec 31, 2008 | Contract with the Learning Disabilities Association of Washington Adult Choices Program |
| January 1, 2009 | Fully operational programs |

- C.	Partnership/Linkages

King County Drug Court will continue to partner with King County Mental Health Chemical Abuse and Dependency Services, other criminal justice agencies, community treatment providers, residential facilities and housing programs.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

- Housing case manager positions will be recruited and in place September 2008.

- Amendments to an existing contract between the Department of Judicial Administration Drug Court Program and treatment providers for provision of evidence-based treatment services for young adults and expansion and enhancement of services for drug court women participants will be in place by September 2008.

- Contract with the Learning Disabilities Association of Washington Adult Choices Program will be in place in September 2008.

- B.	Procurement of Providers

Not Applicable

- C.	Contracting of Services

Amendment to an existing contract between the Department of Judicial Administration Drug Court Program and a treatment provider for provision of evidence-based treatment services for young adults will be in place by September 2008.

Amendment to an existing contract between the Department of Judicial Administration Drug Court Program and a treatment provider for provision of additional services for a drug court women’s group will be in place by September 2008.

A contract between Department of Judicial Administration Drug Court Program and the Learning Disabilities Association of Washington will be in place by September 2008.

- D.	Services Start Date(s)

September 2008

Housing Development

16a

Strategy Title:	Increase Housing Available for Individuals with Mental Illness and/or Chemical Dependency

Strategy No:	#16a – Housing Development

County Policy Goal(s) Addressed:

- A reduction of the number of people with mental illness and chemical dependency using costly interventions like jail, emergency rooms and hospitals.

- Explicit linkage with, and furthering of, other council directed efforts including the Adult and Juvenile Justice Operational Master Plans, the Ten-Year Plan to End Homelessness in King County, the Veterans and Human Services Levy Service Improvement Plan and the Recovery Plan for Mental Health Services.

- A reduction of the number of people who cycle through the jail, returning repeatedly as a result of their mental illness or chemical dependency.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

The 2007 One Night Count found a total of 2651 people without housing or shelter throughout King County.  An additional estimated 6000 people were staying in shelters and transitional housing.  It is likely, based on local and national estimates, that over half of the homeless population have either a serious mental illness, chemical dependency, or both.  The Ten Year Plan to End Homelessness in King County calls for 9500 additional housing units by 2014:  4725 new and 4775 from existing stock.  Production has not kept pace with goals due to the lack of funding to support production.

- B.	Reason for Inclusion of the Strategy

- Homeless adults receiving outpatient mental health services are four times as likely to be incarcerated as those who have housing.  In this same study, homeless clients stayed an average 22 days in jail, compared to an average of two days for similar clients who had housing.

- Supportive or affordable housing has been shown to be a cost-effective public investment for populations who are most at risk for criminal justice involvement, lowering corrections and jail expenditures and freeing up funds for other pubic safety investments. Additionally, providing affordable or supportive housing to people leaving correctional facilities is an effective means of reducing the chance of future incarceration.

- Local examples such as the Downtown Emergency Services Center 1811 Eastlake Project and the Plymouth housing group’s Begin at Home Program have demonstrated large reductions in emergency medical visits as a result of providing housing for homeless individuals with mental illness and chemical dependency.

- C.	Service Components/Design

Funds will be used for four purposes:

  - Provide funds to fill budget gaps for housing projects that have not acquired all of the necessary funding to complete their capital budget. Delays in securing capital results in significant start-up construction delays and possible cost overruns.

  - Provide capital funding for new housing projects that might otherwise not be funded or that might be under funded due to lack of capital dollars.

  - Provide funds for time limited rental subsidies for those individuals and/or housing projects waiting for subsidies from the Housing Authorities or other funders of operating costs.

  - Provide funding for a revolving loan program for interim loans to affordable housing agencies for the acquisition of property that will be utilized for a housing project.  Interim loans will have a low interest rate, will be available for application throughout the year and will not need to be paid back until all permanent financing for the project is acquired.  The program will lower the costs of creating housing projects and will allow for the rapid acquisition of sites.

- D.	Target Population

Housing units funded through this strategy will be dedicated for the use of individuals with mental illness and/or chemical dependency who are homeless or being discharged from hospitals, jails, prisons, crisis diversion facilities, or residential chemical dependency treatment.

- E.	Program Goals

Increase the availability of housing specifically reserved for individuals with mental illness and/or chemical dependency.

- F.	Outputs/Outcomes

The number of units to be developed or made available through rental subsidies is yet to be determined, and will depend on the amount of funding allocated for this strategy and the specific proposals received from housing providers.  Outcomes will include a reduction in homelessness among the target population and an associated reduction in the use of jails and emergency medical services.

2.	Funding Resources Needed and Spending Plan

| Dates | Activity | Funding |
| --- | --- | --- |
| June-July 2008 | Notice of funding availability and announcement of priorities |  |
| September 2008 | Transfer of funds to the Housing and Community Development Program; housing applications received |  |
| December 2008 | Funding award decisions finalized | $18,000,000 |
|  | Total Funds 2008 | $18,000,000 |
| Ongoing annual | Total Funds | To be determined |

3.	Provider Resources Needed (number and specialty/type)

- A.	Number and Type of Providers (and where possible FTE capacity added via this strategy)

Mental health treatment providers, chemical dependency treatment providers, and affordable housing providers that serve the target population

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

Not needed.

- C.	Partnership/Linkages

Funds for new housing projects, a loan program and for gap funding would be made available to the King County Housing and Community Development Program (HCD) within the Department of Community and Human Services (DCHS) and included in their 2008 Funding Round.  This will enable funds to be managed without creating a new administrative structure.

Rental subsidies would be made available to mental health	and chemical dependency treatment providers serving homeless adults and youth.

4.	Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

Identify partially funded housing projects that have gap funding needs by May 8, 2008.

Announce the (contingent) availability of the new capital funds in May, 2008.

Conduct budget gap negotiations with agencies that have partially funded projects, to be completed by June 3, 2008.

Secure DCHS approval for amendments to partially funded projects by September 1, 2008.

- B.	Procurement of Providers for new housing projects

HCD announces availability of MIDD funding in the fall 2008 funding round by the end of June, 2008.

Pre-applications received and pre-app meetings with applicants completed by June 30, 2008.

Project applications received the first week in September 2008.

Final award decisions made by December 15, 2008.

- C.	Contracting of Services

For “budget gap” projects where MIDD provides the last needed capital, HCD will complete contracts as expeditiously as possible, not later than December 1, 2008.  For new projects partially funded with MIDD capital, contracting will depend on agencies securing all other sources of public and private capital needed.  It is anticipated that projects that are successful in other competitive funding rounds may be under contract and beginning construction by December, 2009.

- D.	Services Start Date(s)

Variable, depending on status of each proposal.

Mental Illness and Drug Dependency Implementation Plan

New Strategies

September 2, 2008

Strategy Title:  Crisis Intervention Team / Mental Health Partnership (CIT/MHP) Pilot Project

Strategy No:	 17a

County Policy Goals Addressed:

- A reduction of the number of mentally ill and chemically dependent using costly interventions like jail, emergency rooms and hospitals;

- A reduction of the number of people who recycle through the jail, returning repeatedly as a result of their mental illness or chemical dependency;

- A reduction of the incidence and severity of chemical dependency and mental and emotional disorders in youth and adults; and

- Diversion of mentally ill and chemically dependent youth and adults from initial or further justice system involvement.

1.	Program/Service Description

- A.	Problem or Need Addressed by the Strategy

In the police departments of cities in the United States with populations greater than 100,000, approximately 7% of all police contacts, both investigations and complaints, involve a person believed to have a mental illness.   Many of these contacts also involve abuse of drugs or alcohol.  It is a major challenge for police and other first responders to maintain the safety of everyone involved in these situations while also resolving the situation so they can move on to other calls and duties.

In Seattle, officers generate approximately 50 written reports per week involving individuals with mental issues, with 10 to 15 of these requiring follow up by the Police Department’s Crisis Intervention Team (CIT) Unit.  For each report written, one to two additional contacts per week between officers and individuals with signs of mental illness are cleared by officers as “oral warning given,” “assistance rendered,” or “no police action possible or necessary.”  In total then, SPD logs approximately 125 to 130 law enforcement contacts per week with individuals showing signs of mental illness.  Numerous additional undocumented contacts with these individuals also occur every week.

The Seattle Police Department (SPD) has had a successful, nationally recognized CIT program since 1998 to address persons in crisis as a result of mental illness.  A Police Sergeant oversees the work of two patrol officers assigned to the CIT.  In addition, approximately one-third of Seattle’s 600 patrol officers have been CIT-certified in a 40-hour course.  The unit and its CIT-trained patrol officers have assisted providers, family members, the Department of Corrections and non-CIT trained police officers on the street, with strategies to address the complex issues involved when persons with mental illness come to the attention of law enforcement.

Since the program was instituted, call numbers have increased while King County Department of Mental Health staffing levels have remained the same (28 full-time Designated Mental Health Professionals and less than 10 part-time DMHPs).  With increased demand, it has been difficult for these King County mental health providers to respond in a timely way to persons in crisis.  Often, the overworked DMHPs evaluate the individual many hours after the initial crisis and in a clinical setting.  Usually, by that time the crisis is over, but the individual has been detained and is at Harborview Medical Center or in jail.

The SPD proposes a 12-month West Precinct pilot project that dedicates mental health provider staff to providing “in field” assessments.  These staff members, paired with CIT officers, will ensure more timely evaluation of individuals to better ensure appropriate follow-up.  The patrol officers will be able to turn over these often complex and time-consuming calls to the CIT team, which will evaluate, determine the appropriate response, and refer promptly.  Patrol officers will be able to return more quickly to other 911 duties, and individuals in crisis will be better served.  As a consequence, both efficiency and effectiveness will be enhanced for the police, the courts, the health care system, and the individuals who need help.

The pairing of police with mental health providers is not a new concept.  The model has been successfully implemented in San Diego, Los Angeles, and Vancouver, B.C., and other cities.  The idea is currently being piloted by the Houston Police Department.

- B.	Reason for Inclusion of the Strategy

According to the Implementation Timeline of the MIDD Implementation Plan, the proposed Crisis Diversion Center that will be funded with the tax revenues is slated to open in October of 2009. Having mental health providers available in the field will ensure more timely assessment and appropriate referral to services as the diversion center is developed and brought on line.

There will be police, health care, and criminal justice cost savings due to efficient use of police patrol time, fewer jail bookings, and lower health care costs, particularly associated with cases that do not result in involuntary detention and hospitalization.  If the mental health providers can make the assessment on the street, significant costs associated with assessing at the hospital are also avoided (the time and costs of ambulance transfer, ER services, etc.).  In addition to system cost savings, the services of mental health professionals in the field will ensure more successful outcomes for the individuals in crisis.

- C.	Service Components/Design

Under the proposed pilot, the SPD CIT Unit would be staffed with two mental health providers.  One of the providers, a DMHP, would have the authority under King County to petition for involuntary treatment detentions.  The other would be a therapeutic MHP with expertise in the services and resources available to assist mentally ill individuals, including those presenting symptoms of drug abuse.  These two professionals, working in close concert with CIT Unit officers, will be able to respond immediately to field requests and have more time to spend on these cases.  These teams will consult with patrol officers, detectives, mental health court staff, family members, service providers, the Department of Corrections, and others to navigate complex systems (mental health, drug treatment, health care, social service, police, and criminal justice).

In the pilot phase, staffing coverage, working overlapping shifts, will be from Monday through Friday, between 8:00 a.m. and 7:00 p.m.  This is the period when the CIT call load is heaviest.

The pilot project will have an evaluation component to capture and document the results of the project.  (See Section 1F below.)

- D.	Target Population

SPD’s West Precinct includes the city’s traditional core for Seattle business, tourism, and governmental services.  Since the early 1990s, it has accommodated a disproportionate share of the city’s residential growth under the regional Growth Management Planning Strategy.  A large number of social service agencies in the West Precinct serve the city’s street and homeless population, which includes substantial numbers of individuals with mental illness and drug abuse problems.  This concentration of individuals makes the West Precinct the best geographic location for a pilot project.

- E.	Program Goals

The objectives for the CIT/MHP project link back directly to the King County policy goals set forth above.  The program goals are to:

- Get individuals in crisis more quickly connected with appropriate services that can help them achieve stability, including housing and social services for those who are homeless, and treatment for those suffering from mental illness and/or drug abuse.

- Reduce the wait time associated with assessing persons for possible detention due to mental illness and/or drug abuse.

- Decrease the amount of time patrol officers spend evaluating and assessing individuals who display symptoms of mental illness and/or drug abuse.

- Achieve other system cost savings through diversion from jail and costly hospital services and/or admissions.

- F.	Outputs/Outcomes

As part of the program design, the CIT/MHP Pilot Project will have an evaluation component to document and assess program outcomes, including the development of appropriate quantitative measures of performance.  Possible program results include the following:

- Reductions of mental health assessments by non-CIT trained patrol officers.

- Reductions of transports to Harborview for mental health assessments.

- Reductions of unnecessary ER visits and hospitalizations due to referrals by non-CIT trained patrol officers.

- Reductions in jail bookings where diversion would be appropriate.

- Increase in speedy referrals to appropriate services due to specialized and faster mental health provider response in the field.

- Funding Resources Needed and Spending Plan

| Two full-time mental health providers | $200,000 |
| --- | --- |
| Lease and operating expense for one vehicle for MHPs | $25,000 |
| Consultant contract for project evaluation | $25,000 |
| Total Pilot Costs | $250,000 |

3.   Provider Resources Needed (number and specialty/type)

- A.	Number and Type of Providers

Two FTE mental health providers will be hired for this project, one a therapeutic/homeless specialist (MHP) and one with authority under King County to petition for involuntary treatment detentions (DMHP).  (See Section 3C below.)

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

Two weeks will be allotted for orientation and familiarization with SPD operational protocols and policies.

- C.	Partnership/Linkages

SPD will contract with the King County Mental Health, Chemical Abuse and Dependency Services (KCMHCADS) Division to provide the mental health professionals for this project.  KCMHCADS currently employs and designates mental health providers who are trained and have with the authority to do involuntary detentions of mentally ill individuals.  The persons hired for this project will be detailed to SPD for work on this project.  This arrangement could be extended beyond the pilot project, assuming availability of resources and favorable project outcomes.

The CIT mental health providers will have experience working closely with law enforcement.  Therefore, they will be well positioned to assist with the Countywide CIT training that is being proposed.  CIT also will assist with the development and work closely with the County’s proposed Crisis Diversion Unit.

CIT will network and work closely with all social services, homeless and mental health providers to identify effective referrals for individuals in crisis encountered on the street.  One major existing resource in this area is the Homeless Outreach, Stabilization and Transition Project (HOST) with the Downtown Emergency Services Center.

4.  Implementation/Timelines

- A.	Project Planning and Overall Implementation Timeline

Contracting with KCMHCADS Division can be completed within 30 days of notification of funding availability.  Hiring MHP staff could be accomplished in two months.  Basic orientation to SPD will take approximately two weeks.

All dates are contingent on notification of the award of funding.  Assuming that occurs October 1, 2008, the contract with King County will be in place by November 1, 2008, new hires should be on board and ready for work by January 1, 2009, and CIT/MHP deployments for street service will begin by January 20, 2009.

- B.	Procurement of Providers

As specified above in Section 4A.

- C.	Contracting of Services

As specified above in Section 4A.

- D.	Services Start Date(s)

As specified above in Section 4A.

Strategy Title:	 Safe Housing and Treatment for Children in Prostitution Pilot Project

Strategy No:	17 b

This proposal targets children involved in prostitution.  Because of trauma and sexual abuse experienced at young ages, this group of extremely vulnerable children has complex issues, including extensive mental health and substance abuse issues.  To help these children, a comprehensive program of housing, and specialized and individualized services, is needed to meet their unique needs.

County Policy Goals Addressed:

- A reduction of the number of mentally ill and chemically dependent using costly interventions like jail [including juvenile detention], emergency rooms and hospitals;

- A reduction of the number of people who recycle through the jail, returning repeatedly as a result of their mental illness or chemical dependency;

- A reduction of the incidence and severity of chemical dependency and mental and emotional disorders in youth and adults;

- Diversion of mentally ill and chemically dependent youth and adults from initial or further justice system involvement; and

- Explicit linkage with, and furthering the work of, other council directed efforts including, the adult and juvenile justice operational master plans, the Plan to End Homelessness, the Veterans and Human Services Levy Services Improvement Plan and the county Recovery Plan.

1.  Program/Service Description

- A.	Problem or Need Addressed by the Strategy

The proposed program will provide critically needed outreach, housing, and health and social services to runaway and homeless children exploited by those engaged in the commercial sex trade.  Most of these children are girls, although some are boys, and some are self-identified transgendered youth.

Hundreds of children are exploited through prostitution in Seattle/King County each year. The average age of children arrested for prostitution and referred to King County Juvenile Court in 2007 was 15.5 years of age, though many started prostitution at younger ages.

These children have been victims over time and are victims in a number of ways. Most were victimized by physical, emotional, or sexual abuse, and other parental neglect before running away from home.  Abusive practices are used to lure children into prostitution.  Many commercially sexually exploited youth are psychologically manipulated and physically coerced by pimps, drug dealers, or gang members.  Once exploited, these children are often trapped in a cycle of violence, facing repeated beatings and degradation at the hands of pimps and johns. They face a high risk of pregnancy and of sexually transmitted diseases (including HIV and Hepatitis C).  They have a greater chance of developing psychiatric disorders and attempting suicide, and they are at high risk for drug and/or alcohol addiction.  In order to recover and successfully escape a brutal cycle, it is critical to give these children a safe haven where they can receive specialized care and services.

Because their exploiters have indoctrinated them, many return to the streets from detention.  And, because these children have repeatedly experienced significant trauma, they have profound trust issues.  They are tough and abrasive, do not seek services, and often difficult to reach.  Such challenges are made more difficult because their experience of sexual abuse and the associated trauma remain largely hidden from many case managers and social workers.  Even when social workers are aware of a child’s prostitution background and perilous situation, they do not know where to send them for help.

In a 2008 study of youth involved in prostitution in Seattle commissioned by the Seattle Human Services Department’s Domestic Violence and Sexual Assault Prevention Division, 238 adolescents were identified as involved in prostitution. These children were identified through reviews of 1,528 case records from 16 social service agencies.  The actual number of youth involved in prostitution in Seattle is likely higher.  Local data support national research findings that prostitution offenses by juveniles are underreported by the police.

Children involved in prostitution are heavy users of the criminal justice system.  Because their engagement in this activity is still treated as a crime, they are sometimes arrested and when they are, they are prosecuted through the juvenile court system.  In 2006, 49 juveniles from Seattle/King County were arrested for prostitution; juvenile arrests in the State increased from 50 in 2006 to 82 in 2007. This number is different from the 238 reported in the City of Seattle study because only some juveniles are arrested.

A recent analysis of youth with 35 prostitution and prostitution loitering charges between 2004 and 2006 found these 31 individuals charged with 211 offenses in King County Juvenile Court.  With a range from 2 to 23, each of these youth was referred to King County Juvenile Court an average of seven times. Altogether, they were detained 2,467 days. The primary arresting law enforcement agencies were the police departments of Seattle (104), Kent (26), and Federal Way (25); followed by the King County Sheriff (24).

2007 data collected by the detention case manager at YouthCare found 117 runaway and homeless girls in King County Juvenile Detention involved in prostitution (110 between 14 and 17 years old).  In addition, 13 boys and 5 self-identified transgendered youth in King County Juvenile Detention were involved in prostitution. Seventy-two (72) of the girls were homeless.  Of all the girls in detention, 39% were black, 28% white, and 15% American Indian/Alaskan Native. Many of the girls reported being involved in prostitution that involves a pimp and/or or those engaged in trafficking across state lines, is associated with gangs, or has Internet connections.

- B.	Reason for Inclusion of the Strategy

The service and treatment needs of runaway and homeless children who have been sexually exploited are substantial and largely unmet. While a number of local programs and services target runaway and homeless youth, none provide a safe haven and the comprehensive and intensive case management, mental health and substance abuse treatment services needed by those who have been involved in and sexually exploited by prostitution.

Outreach is a critical component of the proposed program since most children involved in prostitution do not seek services.  However, they may be open to services at a time of crisis, including arrest and detainment in juvenile court.  It is crucial to offer both safety and assistance when a child is ready to receive them.  Outreach without the availability of safe housing and coordinated, targeted treatment will not get the results we need.

Outreach will be the primary source of referrals into the program’s emergency or transitional living programs and it will be conducted at King County Juvenile Detention, at the Spruce Street Crisis Residential Center. The program will also receive referrals from street outreach conducted by a number of existing community programs.  For this needy population, King County Juvenile Detention corresponds directly to the jails cited in the county’s policy goals.

The proposed program will increase access to community mental health and substance abuse treatment by providing critically needed coordinated case management and other services, including specialized mental health and substance abuse treatment services, on-site for runaway and homeless youth involved in prostitution.  Today, such care is limited, fragmented, or simply does not exist.

In Washington, according to a needs assessment conducted in 2006, there is a critical shortage of mental health services for State-dependent, low-income persons, particularly those under the age of 18.  Access to these services is more difficult for homeless youth who typically are not enrolled in State services because they have not applied, are not qualified, or have left the system.

In Seattle/King County, local providers and Seattle Human Services Department staff estimate that 800 youth, many with dual diagnoses, need outpatient mental health services. Each year, an estimated 200 homeless youth need inpatient mental health treatment, but only about 25 receive more than a 72-hour inpatient psychiatric assessment. There are few therapists available to homeless persons and fewer than 100 homeless youth receive outpatient mental health services each year.

There are also few inpatient and outpatient substance abuse treatment services available to homeless youth. There are long waiting lists for King County inpatient programs and the number of state-funded beds is extremely limited.  The Washington State Department of Health found that treatment services funded by the Division of Alcohol and Substance Abuse for youth 12 to 17 years old served only 5,875 out of an estimated 24,981 eligibles in need of services in 2003.

The proposed program will provide an occupational skills center; and community-based employment support and other services will be offered.  Through these services, clients will be able to finish high school or complete credits for a General Educational Development (GED) in lieu of a high school diploma; prepare to apply to college; participate in occupational skills training programs; and obtain either unsubsidized or subsidized job internships. These services will help clients land permanent jobs, or help them to pursue post-secondary education, which will prepare them for future self-sufficiency.

As detailed in the Plan to End Young Adult Homelessness in Seattle/King County, current housing capacity for homeless youth and young adults does not meet the need for beds.  This is particularly true for those who are victims of commercial sexual exploitation.  The proposed program nearly doubles local capacity for longer-term, transitional living for homeless youth under the age of 18.  It does so while also providing for a range of wraparound services to children involved in prostitution, a subset of homeless youth whose needs are not being met.

There are 6 overnight shelters for homeless youth under 18 in Washington and all provide only overnight shelter.

The majority of children involved in prostitution are homeless or lack safe housing. The proposed program will provide critically needed safe housing and supportive services to these individuals.  A continuum of housing will be provided to move clients from crisis (emergency shelter) to stabilization (transitional living) to independent living. The program will also provide transitional beds for those who “age out” (reach their 19th birthday while still in the program).

Appropriate intervention, safe housing, and focused services can save children and help them turn their lives around.  This proposed program will provide the range of specialized features needed.

When a complete service delivery system is implemented, extremely vulnerable children will have housing and access to the full range of support services to help them escape sexual exploitation, heal from traumatic harm, and keep them from cycling again and again through the criminal justice system.

- C.	Service Components/Design

A full complement of needed services includes street and detention-based outreach; a continuum of safe housing (emergency beds, transitional beds, and beds for ”age-outs” (18 and older); intensive case management; legal advocacy; mental health services integrated with substance abuse treatment (including survivor support groups and specialized on-site trauma recovery counseling); health education; on-site life skills training (including support for GED or high school completion, preparation for enrollment in post-secondary education, job readiness training, employment placement, internships); and family reconciliation counseling.

- D.	Target Population

The target population is 250 runaway and homeless youth involved in prostitution in the Seattle/King County area (mainly girls, but also boys and self-identified transgendered youth) from 11 through 17 years old.  Under the comprehensive proposal, program participants who age out may continue to receive housing and other services. Outreach efforts will focus on youth who have frequent contacts with the criminal justice system.

- E.	Program Goals

The proposed program will provide children involved in prostitution with safe housing and extensive, individualized, support services.  Its goal is to give these children tools to leave the streets and prostitution, to become stable, and to achieve and maintain independence.

The top four components of the program to meet this goal include:

- Extensive King County Juvenile Detention, as well as street-based, outreach.

- Safe and stable housing.

- Comprehensive on-site, case management; integrated mental health and substance abuse services, including specialized trauma recovery services; and offsite referrals to specialized services as needed.

- Education and training delivered on-site and in the community to prepare children to become independent and achieve long term security.

- F.	Outputs/Outcomes

A chart showing the expected outcomes is shown below (Annual Measurable Outcomes).  All runaway and homeless youth (RHY) referenced in the chart are those specifically targeted for the proposed program, e.g. they are all children who have been sexually exploited as prostitutes.

2.   Funding Resources Needed and Spending Plan

Provide 4 emergency shelter beds, 4 transitional living beds for children 11 through 17 years old, and 2 transitional living beds for “age outs” (program participants 18 and older).  The project assumes contracting with a community provider with existing bed and staffing resources for runaway and homeless youth that can be leveraged to provide services that include 24/hour, 7 days/week residential staff; case management; comprehensive counseling, support groups; life skills training, and other client services.  The spending plan includes $30,000 for training staff and other providers to work with this specific group of clients.  A part-time information systems manager is included in the spending plan who will be responsible for developing data collection tools and tracking program outcomes.  The total number of new staff to be funded is 11.2 FTE. (See Section 3 below.)

Total Plan Costs:  $480,000

3.	Provider Resources Needed (number and specialty/type)

MIDD funds are to be provided to the City of Seattle. The City of Seattle will administer the necessary Request for Proposal processes which will be open to any organization or entity in King County.

- A.	Number and Type of Providers

The number and type of providers needed to run the operation include the new FTEs identified in Column A of the chart below.  Potential resources that may be available to leverage program funding are shown in Column B:

| (A) New Staff to be funded | New FTEs | (B) Potential Resources | FTE |
| --- | --- | --- | --- |
| Case Manager | 1.5 FTE | HMC Sexual Assault Center MH Providers | 0.5 FTE |
| House Coordinator | 0.5 FTE | Ryther Child Center Chem Dependency Provider | 1.0 FTE |
| Life Skills Coordinator | 1.0 FTE | Occupational Skills Instructors | 3.0 FTE |
| Youth Counselors | 6.5 FTE | Career Coordinators | 2.0 FTE |
| Psychologist | 1.0 FTE | Outreach Workers | 4.0 FTE |
| Chem Dep Provider | 0.5 FTE | Detention Case Manager | 1.0 FTE |
| Info Systems Manager | 0.2 FTE | School Teachers | 2.0 FTE |
| TOTAL | 11.2 FTE | TOTAL | 12.5 FTE ~ |

- B.	Staff Resource Development Plan and Timeline (e.g. training needs, etc.)

As soon as new staff are hired, a 12 month program of trainings will start, designed to help all involved work effectively with program clients.

- C.	Partnership/Linkages

Community Provider   A contract will be put in place with a community provider with significant background and capability in serving runaway and homeless youth, ideally including those involved in prostitution.  The provider will have a well established record of creating and maintaining innovative linkages with community partners including, among others, health care and social service agencies, correctional facilities, schools, employment and training programs, and substance abuse treatment programs.

4. Implementation/Timelines

- A.  	Project Planning and Overall Implementation Timeline

- B.	Procurement of Providers

- C.	Contracting of Services

- D.	Services Start Date(s)

Following the issuance of an RFP and after awarding a contract with a community provider, the program can be in operation within 6 months, assuming an existing infrastructure is in place.  During this interval, the following will be finalized:

- Recruitment, background checks, and hiring of staff will be completed.

- Memoranda of Understanding will be established with project partners.

- Training will commence.

- Printed materials about the program will be created for outreach and recruitment.

- Data collection tools will be developed to monitor and evaluate client progress.

Annual Measurable Outcomes

Conduct extensive outreach Contact 150 RHY both on the streets and in the juvenile justice system and provide them with information about services, referrals and advocacy. # and type of outreach encounters, referrals, and advocacy activities Increase safe and stable housing Provide 4 emergency shelter beds to care for 60 under-18 RHY Provide 4 transitional living beds to serve 10 under-18 RHY for extended periods Provide 2 transitional living beds for 15 18 and older RHY who age out Occupancy Rates/Program Engagement Occupancy rates out of 1,440 bed nights at the shelter Occupancy rates out of 1,440 bed nights at the under-18 transitional living unit Occupancy rates out of 720 bed nights at the 18 and older transitional living unit Program Completion/Stability # of RHY who reside at least 6 months in the under-18 transitional living unit # of RHY who reside at least 6 months in the 18 and older transitional living unit Safe Exits # of RHY who exit the program into a safe housing situation Reduce the risk of RHY to re-engage in prostitution by providing intensive case management; comprehensive, integrated, on- and off-site mental health and substance abuse services; education and life skills training; and employment training 65 RHY receive intensive, wraparound case management, including individualized service plans tailored to the needs of each individual. # of RHY who complete an Individual Service Plan (ISP); # of RHY who make progress on ISP goals, using a 5-point Likert scale at 3 month intervals 50% of 65 RHY participate in mental health and/or substance abuse services. # of RHY who are screened/assessed for mental health and substance abuse issues; # of RHY who receive 5 weeks of mental health and/or substance abuse services; # of RHY who enter treatment for substance abuse; # of RHY who complete substance abuse treatment; # (of RHY who attend 5 weeks of mental health and/or substance abuse group services 75% of 65 RHY gain employment-related skills # of RHY who complete a job readiness workshop, including developing a resume; # of RHY who complete occupational skills training either on-site or off-site; # of RHY who obtain subsidized employment either on-site or off-site (e.g. internships); # of RHY who obtain unsubsidized employment; # of RHY who maintain unsubsidized employment for at least 6 months 50% of 65 RHY enroll in education for a consistent period of time. # of RHY who enroll in high school or GED program; # of RHY who make literacy gains based on CASAS pre- and post-testing; # of RHY who obtain their high school diploma or GED; # of RHY who enroll in post-secondary education 75% of 65 RHY increase housing stability. # of RHY who obtain stable housing; # of RHY who maintain stable housing for at least 6 months 50% of 65 RHY do not re-engage in crimes, including prostitution, for at least 6 months after care # of RHY contacts with the juvenile justice system; # of RHY arrests for crimes, including prostitution

Appendices

A-E

Appendix A

Mental Illness and Drug Dependency Oversight Committee

Bill Block, Project Director

Committee to End Homelessness in King County

Representing: the Committee to End Homelessness in King County

Linda Brown, Member

King County Alcohol and Substance Abuse Administrative Board

Representing: the King County Alcohol and Substance Abuse Administrative Board

Will Callicoat, Director, Financial Policy

Washington State Hospital Association

Representing: the Washington State Hospital Association/King County Hospitals

Nancy Cole, Executive Director

National Alliance on Mental Illness-Greater Seattle

Representing: the National Alliance on Mental Illness in King County

Merril Cousin, Executive Director

King County Coalition Against Domestic Violence

Representing: domestic violence prevention services in King County

Bob Ferguson, Councilmember

King County Council

Representing: the King County Council

David Fleming, Director and Health Officer

Public Health – Seattle & King County

Representing: Public Health

Helen Halpert, Assistant Presiding Judge

King County Superior Court

Representing: Superior Court

Shirley Havenga, Chief Executive Officer

Community Psychiatric Clinic

Representing: a provider of both mental health and chemical dependency services in King County

Mike Heinisch, Executive Director

Kent Youth and Family Services

Representing: an agency providing mental health and chemical dependency services to youth in King County

David Hocraffer, Director

Office of Public Defense

Representing: the Office of Public Defense

Reed Holtgeerts, Director

King County Department of Adult and Juvenile Detention

Representing: Adult and Juvenile Detention

Darcy Jaffe, Interim Assistant Administrator
Ambulatory & Allied Care Services

Harborview Medical Center

Representing: Harborview Hospital

Norman Johnson, Executive Director

Therapeutic Health Services

Representing: A provider of culturally specific chemical dependency services in King County

Bruce Knutson, Director

Juvenile Court, King County Superior Court

Representing: the King County Systems Integration Initiative

Pete Lewis, Mayor

City of Auburn

Representing: the Suburban Cities Association

Barbara Linde, Presiding Judge

King County District Court

Representing: District Court

Marilyn Littlejohn, Executive Manager, Human Services

City of Seattle, Mayor’s Senior Staff

Representing: the City of Seattle

Jackie MacLean, Director

King County Department of Community and Human Services

Representing: the Department of Community and Human Services

Donald Madsen, Director

Associated Counsel for the Accused

Representing: a public defense agency in King County

Barbara Miner, Director

King County Department of Judicial Administration

Representing: Department of Judicial Administration

Phil Noble, Councilmember

City of Bellevue

Representing: the City of Bellevue

Kurt Ofsthus, Discharge Planner

NAVOS Inpatient Services

Representing: labor, representing a bona fide labor organization

Mario Paredes, Executive Director

Consejo Counseling and Referral Service

Representing: a provider of culturally-specific mental health services in King County

Susan Rahr, Sheriff

King County Sheriff’s Office

Representing: the Sheriff’s Office

Dan Satterberg, Prosecutor

King County Prosecuting Attorney’s Office

Representing: the Prosecuting Attorney’s Office

Mary Ellen Stone, Director

King County Sexual Assault Resource Center

Representing: a provider of sexual assault victim services in King County

Crystal Tetrick, Associate Director for Health Care Operations

Seattle Indian Health Board

Representing: the Council of Community Clinics

Eugene Wan, Member

King County Mental Health Advisory Board

Representing: the King County Mental Health Advisory Board

Sheryl Whitney, Assistant County Executive

Office of the King County Executive

Representing: the Executive

Appendix B

| Strategy Implementation Process |
| --- |
| Strategy Number and Description | Service Category | Age Category | Existing or New Service / Provider | RFP/ RFQ Needed | Services Start |
|  | MH=Mental Health | SA=Substance Abuse | Y=Youth/ Parents | A=Adult | OA=Older Adult | Exist-ing | New | Both |  | September 15, 2008 | Other Start Date |
|  |  |  |  |  |  |  |  |  |  | Or Upon Spending Authorization Approval by Council |  |
| 1a-1 | Increase access to community mental health treatment | MH |  | Y | A | OA | X |  |  |  | X |  |
| 1a-2 | Increase access to community substance abuse treatment |  | SA | Y | A | OA | X |  |  |  | X |  |
| 1b | Outreach and engagement to individuals leaving hospitals, jails, or crisis facilities | MH | SA | Y | A | OA |  | X |  | X |  | To be determined |
| 1c | Emergency room substance abuse early intervention program* |  | SA | Y | A | OA |  |  | X | X | X | Jan-1-09 |
|  |  |  |  |  |  |  |  |  |  | So KC Provider | Harborview | South KC Provider |
| 1d | Mental health crisis next day appointments and stabilization services | MH |  | Y | A | OA | X |  |  |  | X |  |
| 1e | Chemical dependency professional education and training |  | SA |  |  |  | X |  |  |  | X |  |
| 1f | Peer support and parent partner family assistance | MH | SA | Y |  |  |  | X |  | X |  | Jul-1-09 |
| 1g | Prevention and early intervention mental health and substance abuse services for older adults | MH | SA |  | A | OA | X |  |  |  |  | Nov-1-08 |
| 1h | Expand availability of crisis intervention and linkage to on-going services for older adults | MH | SA |  |  | OA | X |  |  |  |  | Dec-1-08 |
| 2a | Caseload reduction for mental health | MH |  | Y | A | OA | X |  |  |  | X |  |
|  | (use $3 million MIDD to leverage additional $3 million federal) |  |  |  |  |  |  |  |  |  |  |  |
| 2b | Employment services for individuals with mental illness and chemical dependency | MH | SA |  | A | OA |  |  | X | X |  | Nov-1-08 |
|  |  |  |  |  |  |  |  |  |  | SA |  |  |
| 3a | Supportive services for housing projects | MH | SA |  | A | OA |  | X |  | X |  | Nov-1-08 |
| 4a | Comprehensive chemical dependency outpatient services for parents in recovery |  | SA |  | A | OA |  | X |  | X |  | Jun-1-09 |
| 4b | Prevention services to children of substance abusers |  | SA | Y |  |  |  | X |  | X |  | Apr-1-09 |
| 4c | School district based mental health and substance abuse services | MH | SA | Y |  |  |  | X |  | X |  | Sep-8-09 |
| 4d | School based suicide prevention | MH | SA | Y |  |  | X |  |  |  |  | Oct-1-08 |
| 5a | Increase capacity for social and psychological assessments for juvenile justice youth | MH | SA | Y |  |  |  |  | X | X | X | Jan-1-09 |
|  |  |  |  |  |  |  |  |  |  | Assess Profess. | CDP/MH Liaison | Assessment Professional |
| 6a | Wraparound family, professional and natural support services for emotionally disturbed youth | MH |  | Y |  |  |  | X |  | X |  | Sep-1-09 |
| 7a | Reception centers for youth in crisis | MH | SA | Y |  |  |  | X |  | X |  | To be determined |
| 7b | Expanded crisis outreach and stabilization services for children and youth | MH |  | Y |  |  |  |  | X? | X? |  | Sep-1-09 |
| 8a | Expand family treatment court services and support to parents |  | SA | Y | A |  | X |  |  |  | X |  |
| 9a | Expand juvenile drug court treatment |  | SA | Y |  |  |  |  | X | X | X | Jan-1-09 |
| 10a | Crisis intervention training program | MH | SA | Y | A | OA | KSO |  |  |  |  | Jan-1-09 |
| 10b | Adult crisis diversion center, respite beds, and mobile behavioral health crisis team | MH | SA |  | A | OA |  | X |  | X |  | Nov-1-09 |
| 11a | Increase capacity for jail liaison program | MH |  |  | A | OA | X |  |  |  |  | Nov-1-08 |
| 11b | Increase services available for new or existing mental health court programs | MH |  |  | A | OA |  | X |  | X |  | Jun-1-09 |
| 12a | Increase jail re-entry program capacity | MH | SA |  | A | OA |  |  | X | X | X | Jan-1-09 |
|  |  |  |  |  |  |  |  |  |  | Pop #2 | Pop #1 | Pop #2 |
| 12b | Hospital re-entry respite beds | MH | SA |  | A | OA |  | X |  | X |  | Sep-1-09 |
| 12c | Increase capacity for Harborview’s Psychiatric Emergency Services to link individuals to community-based services upon discharge from Emergency Room* | MH | SA | Y | A | OA | To be determined |  | To be determined |
| 12d | Urinalysis supervision for Community Center for Alternative Programs clients |  | SA |  | A | OA |  | X |  | X |  | Feb-1-09 |
| 13a | Domestic violence and mental health services | MH |  | Y | A | OA | To be determined |  | Mar-1-09 |
| 13b | Domestic violence prevention | MH | SA |  | A | OA | X |  |  |  |  | Jan-1-09 |
| 14a | Sexual assault and mental health and chemical dependency services | MH | SA | Y | A | OA | X |  |  |  |  | Oct-1-09 |
| 15a | Expansion of Recovery Support Services |  | SA |  | A | OA | X |  |  |  | X |  |
| 16a | New housing units and rental subsidies | MH | SA |  | A | OA |  |  | X | X |  | Variable |
| 35 | Total | 26 | 27 | 20 | 24 | 24 | 14 | 12 | 7 | 19 | 11 | 28 |
| *Services not countywide (1c – Harborview and South King County, 12c – Harborview) |  |  |  |  |  |  |  |  |  |

Appendix D

Spending Plan

|  |  | 2008 Revised Budget Proposal |
| --- | --- | --- |
| Strategy Number and Description | Original 2008 Budget Proposal | Development & Start-Up | Ongoing Services | 2008 Total |
| 1a-1 | Increase access to community mental health treatment | $ 8,357,419 |  | $ 2,130,000 | $ 2,130,000 |
| 1a-2 | Increase access to community substance abuse treatment |  |  | 635,806 | 635,806 |
| 1b | Outreach and engagement to individuals leaving hospitals, jails, or crisis facilities | 181,740 |  |  | 0 |
| 1c | Emergency room substance abuse early intervention program | 265,500 |  | 120,000 | 120,000 |
| 1d | Mental health crisis next day appointments and stabilization services | 83,333 |  | 73,000 | 73,000 |
| 1e | Chemical dependency professional education and training | 205,225 |  | 160,000 | 160,000 |
| 1f | Peer support and parent partner family assistance | 150,000 | 75,000 |  | 75,000 |
| 1g | Prevention and early intervention mental health and substance abuse services for older adults | 166,677 | 150,000 |  | 150,000 |
| 1h | Expand availability of crisis intervention and linkage to on-going services for older adults | 117,250 | 87,500 |  | 87,500 |
| 2a | Caseload reduction for mental health (use $1 million MIDD to leverage additional $1 million federal) | 1,333,333 |  | 1,750,000 | 1,750,000 |
| 2b | Employment services for individuals with mental illness and chemical dependency | 500,217 | 350,000 |  | 350,000 |
| 3a | Supportive services for housing projects | 666,640 |  | 2,000,000 | 2,000,000 |
| 4a | Services to parents participating in substance abuse outpatient treatment programs | 166,429 |  |  | 0 |
| 4b | Prevention services to children of substance abusers | 300,000 |  |  | 0 |
| 4c | School district based mental health and substance abuse services | 411,450 |  |  | 0 |
| 4d | School based suicide prevention | 66,000 | 75,000 |  | 75,000 |
| 5a | Increase capacity for social and psychological assessments for juvenile justice youth | 119,147 | 60,000 |  | 60,000 |
| 6a | Wraparound family, professional and natural support services for emotionally disturbed youth | 1,563,928 | 175,000 |  | 175,000 |
| 7a | Reception centers for youth in crisis | 165,600 | 75,000 |  | 75,000 |
| 7b | Expanded crisis outreach and stabilization services for children and youth | 750,000 |  |  | 0 |
| 8a | Expand family treatment court services and support to parents | 521,045 |  | 522,000 | 522,000 |
| 9a | Expand juvenile drug court treatment | 33,763 | 250,000 |  | 250,000 |
| 10a | Crisis intervention training program | 846,878 | 50,000 |  | 50,000 |
| 10b | Adult crisis diversion center, respite beds, and mobile behavioral health crisis team | 1,515,965 | 10,350 |  | 10,350 |
| 11a | Increase capacity for jail liaison program | 60,000 | 20,000 |  | 20,000 |
| 11b | Increase services available for new or existing mental health court programs | 368,330 |  |  | 0 |
| 12a | Increase jail re-entry program capacity | 240,000 | 7,500 | 80,000 | 87,500 |
| 12b | Hospital re-entry respite beds | 186,450 | 20,000 |  | 20,000 |
| 12c | Increase capacity for Harborview’s Psychiatric Emergency Services to link individuals to community-based services upon discharge from Emergency Room | 150,000 |  |  | 0 |
| 12d | Urinalysis supervision for Community Center for Alternative Programs clients | 56,250 | 20,000 |  | 20,000 |
| 13a | Domestic violence and mental health services |  | 31,000 |  | 31,000 |
| 13b | Domestic violence prevention |  | 70,000 |  | 70,000 |
| 14a | Sexual assault and mental health and chemical dependency services |  | 110,000 |  | 110,000 |
| 15a | Drug Court: Expansion of Recovery Support Services |  |  | 107,000 | 107,000 |
|  | Revenue Stabilization Fund | 2,000,000 |  | 2,000,000 | 2,000,000 |
|  | Contingency Funds |  |  | 500,000 | 500,000 |
|  | Administration / Evaluation / Data Systems | 2,663,036 |  | 900,000 | 900,000 |
| 2008 Total Budget | $ 24,211,605 | $ 1,636,350 | $ 10,977,806 | $ 12,614,156 |
| 2008 Estimated Revenue | $ 28,096,730 |  |  | $ 38,618,000 |
| Balance to be used for 16a and New Strategy Reserve |  |  | 19,800,844 | 19,800,844 |
| 16a | New housing units and rental subsidies - See Note 1 |  |  | 18,000,844 | 18,000,844 |
|  | NEW STRATEGY RESERVE-SEE NOTE 3 |  |  | 2,500,000 | 2,500,000 |
| 17a | New Strategy: Crisis Intervention Team/Mental Health Partnership Pilot (24 month funding) - See Note 2 |  |  | 500,000 | 500,000 |
| 17b | New Strategy: Safe Housing and Treatment for Children in Prostitution Pilot (24 month funding) - See Note 2 |  |  | 960,000 | 960,000 |

Note 1: Only $11,597,449 of the $18,000,000 allocated to Housing can be spent in 2008 unless a supplemental appropriation is requested.

Note 2: Funding for new strategies is for 24 calendar months.

Note 3: For 2008, the new strategy reserve is funded by $1.8 million in new revenue, $700,000 in unprogrammed revenue.

Appendix E

Decision Model Determining the Need for

Requests for Proposals/Competitive Procurement

# Principles of Purchasing

King County will apply principles that promote effectiveness, accountability and social justice.

## Ethical Behavior and Conduct

The objectives of ethical behavior and conduct are to insure that in its procurement activities, the County will:

- Behave with impartiality, fairness, independence, openness, integrity and professionalism in its dealings with suppliers

- Advance the interests of the County in all transactions with suppliers.

## Open and Effective Competition

The objectives of open and effective competition are:

- To instill confidence in the County and the public about the integrity and cost effectiveness of public sector procurement

- To maximize the most economically beneficial outcome for the County

- To ensure that all suppliers wishing to conduct business with the County are given a reasonable opportunity to do so

- To ensure that bid documents and contracts reflect the requirements and desired outcome of the County and that all participants are subject to equivalent terms, conditions and requirements.

Open and Effective Competition means:

- Procurement procedures and processes are visible to the County, suppliers, and the public

- Suppliers have a real opportunity to do business with the County

- Competition is sought to provide value for money, to achieve the best possible return from County spend on goods and services.

When is a Competitive Process to Secure a Contract Required?

Purchases over $2,499 for a single purchase of goods or services and/or purchases of over $2,500 in a calendar year to a single vendor or provider require a contract.  When the County initiates a contracting process the default procurement stance is that a competitive process to identify the vendor/provider must occur.  A competitive bid process shall be utilized when:

- The County has new funding to purchase services(e.g. new grants, new levies, new allocations from funders)

- A new program/service is to be implemented

- There is a change in requirements or regulations related to services/programs currently under contract with the County requiring a substantial revision in the scope of services

- The funder of programs/services requires competitive procurement process for new funds and/or ongoing funds at a specified frequency.

The following categories of purchases are exempt from the requirement of a competitive bid process:

- Purchases that are covered by a blanket contract entered into by King County Purchasing

- Purchases of services where an there is an existing contract within the Division/Department that purchases the same scope of work:

  - The purchase adds capacity to the program (e.g. purchases more program slots, or bed days); or

  - The purchase expands the population to be served (without changing the scope of work);

- Purchases where there is only one source that can provide the scope of work (A Sole Source Waiver must be sought and authorized from King County Purchasing):

  - The County has been told by a funder to hire a particular (sub)contractor; or

  - There is only one expert/specialty organization in the region that can deliver the scope of work.

Methods Utilized for Competitive Bid Processes

The competitive bid processes below are solicited by the County.  The responses to these solicitations are evaluated against the County’s criteria/requirements for the service/program and awards are made for responses that best meet the County’s needs/specifications.

- Requests for Proposals – Prospective bidders complete a proposal to provide services that includes details about: a) their experience providing similar service; b)  details on how the agency meets required qualifications;  c) a proposal for how the needed/required services will be provided; and d) a detailed expenditure budget

- Requests for Qualifications/Applications – Prospective bidders complete a response detailing their qualifications to provide the needed/required services according to the County specifications and funding

- Letters of Intent – A response to a request for a letter of intent that describes the responder’s interest, qualifications,  and a description of their plan to provide services according to the County’s specifications and funding.

Special Purchasing Issues

Divisions/Departments have been delegated the authority to competitively procure and purchase services that are designed to address the needs of the County’s citizens (e.g. treatment, supportive services, prevention services, etc.).  King County Purchasing may be utilized for the purchase of services if the Division/Department wishes to.

Goods and Consultant Services purchased for King County Divisions/Departments can be competitively procured by the Divisions/Departments if the total expenditure for the consultation will be less than $25,000.  For consultation purchase/contracts that exceed $25,000 the competitive procurement process must be directed and run by King County Purchasing.

# Footnotes

Department of Social and Health Services - Research and Data Analysis Division - Methadone Treatment for Opiate Addiction Lowers Health Care Costs and Reduces Arrests and Convictions, June 2004 (Fact Sheet - PDF)

Department of Social and Health Services - Research and Data Analysis Division – Non Methadone Chemical Dependency Treatment for Opiate Addiction Reduces Health Care Costs, Arrests and Convictions, June 2004 (Fact Sheet - PDF)

Department of Social and Health Services - Research and Data Analysis Division, (May 2, 2007) Harborview Medical Center Substance Use Outcomes,

http://www1.dshs.wa.gov/pdf/ms/rda/research/4/60/HMC.2007.1.pdf

Abt Associates. (2007). Strengthening Professional Identity: Challenges of the Addictions Treatment Workforce, Rockville: Substance Abuse and Mental Health Services Administration (SAMHSA)/DHHS. http://www.samhsa.gov/Workforce/WorkforceReportFinal.pdf

National Association of State Alcohol and Drug Abuse Directors (NASADAD). (2003). Recommendations related to closing the treatment gap, NASADAD policy position paper, 2003. www.nasadad.org/resource.php?base_id=37.

Children Living with Substance-Abusing or Substance-Dependent Parents, The NHSDA Report,

June 2, 2003

DSHS/DASA, TARGET Treatment Analyzer Standard Reports for King County, 2007

National Association for Children of Alcoholics (NACoA) website, Children of Alcoholics:  Important Facts, August 1998 compilation, http://www.nacoa.net/impfacts.htm

Substance Abuse and Mental Health Services Administration (SAMHSA), National Clearinghouse for Alcohol and Drug Information (NCADI) website, You Can Help:  A Guide for Caring Adults Working with Young People Experiencing Addiction in the Family, NCADI Publication No. PHD878, http://csat.samhsa.gov/publications/youcanhelp.aspx

SAMHSA, Ibid.

NACoA, Celebrating Families!™ website, http://www.celebratingfamilies.net/

Caring for Kids, The Center for Health and Health Care in Schools, School of Public Health and Health Services, Graduate School of Education and Human Development, The George Washington University, Summer 2003

U.S. Public Health Service, Report of the Surgeon General’s Conference on Children’s Mental Health: A National Action Agenda. Washington, DC: Department of Health and Human Services, 2000

Substance Abuse and Mental Health Services Administration, 2002. Report to Congress on the prevention and treatment of co-occuring substance abuse disorders and mental disorders

Malignant Neglect: Substance Abuse and America’s Schools, National Center on Addition and Substance Abuse, Columbia University, September 2001

U.S. Department of Health and Human Services, Mental Health: A Report to the Surgeon General, 1999

President’s New Freedom Commission on Mental Health, Final Report to the President, 2003

Outcomes of Expanded Mental Health Programs, Center for School Mental Health Assistance, 2003

Deane, Martha; Steadman, Henry J; Borum, Randy; Veysey, Bonita; Morrissey, Joseph P. “Emerging Partnerships Between Mental Health and Law Enforcement.”  Psychiatric Services Vol. 50, No. 1 January 1999: pp.99-101

Reuland. Melissa and Cheney, Jason.  Enhancing Success of Police-Based Diversion Programs for People with Mental Illness.  Police Executive Research Forum. May 2005

Domestic Violence, Mental Health and Trauma, Carole Warshaw and Holly Barnes, Domestic Violence and Mental Health Policy Initiative, April, 2003.

- Drug Courts --Just the Beginning: Getting Other Areas of Public Policy in Sync. Caroline S. Cooper, Research Professor. Justice Programs Office, School of Public Affairs, American University, Washington D.C. 2003-2004.

BUREAU OF JUSTICE ASSISTANCE (BJA) DRUG COURT CLEARINGHOUSE:  FREQUENTLY ASKED QUESTIONS SERIES:

Information Relevant to Female Participants in Drug Courts:

Prepared By: BJA Drug Court Clearinghouse Project

Date: February 10, 2007.BJA

Learning Disabilities Association of Washington:  CHOICES Adult History and Overview July 7, 2007.

Understanding the Complexities of Offenders’ Special Learning Needs, Weisel, Laura, et. al from Winters, 1997; Mears and Aron, 2003).

King County Drug Court Evaluation, Final Report, M.M. Bell, Inc. February 27, 1998, p. 39.

Deane, Martha; Steadman, Henry J; Borum, Randy; Veysey, Bonita; Morrissey, Joseph P. “Emerging Partnerships Between Mental Health and Law Enforcement.”  Psychiatric Services Vol. 50, No. 1 January 1999: pp.99-101

Boyer, D., 2008, Who Pays the Price? Assessment of Youth Involvement in Prostitution in Seattle, http://www.ci.seattle.wa.us/humanservices/domesticviolence/Report_YouthInProstitution.pdf).

Commercial Exploitation of Children in Georgia.  The Barton Child Law and Policy Clinic of the Emory University School of Law.  July 23, 2008.

Commercial Exploitation of Children in Georgia.  The Barton Child Law and Policy Clinic of the Emory University School of Law.  July 23, 2008.

Boyer, D., 2008, Who Pays the Price? Assessment of Youth Involvement in Prostitution in Seattle, http://www.ci.seattle.wa.us/humanservices/domesticviolence/Report_YouthInProstitution.pdf).

Boyer, D., 2008, Who Pays the Price? Assessment of Youth Involvement in Prostitution in Seattle, http://www.ci.seattle.wa.us/humanservices/domesticviolence/Report_YouthInProstitution.pdf).

Boyer, D., 2008, Who Pays the Price? Assessment of Youth Involvement in Prostitution in Seattle, http://www.ci.seattle.wa.us/humanservices/domesticviolence/Report_YouthInProstitution.pdf).

Washington State Department of Social and Health Services, Research & Analysis Division. (2006). The Voices: 2006 Washington State Mental Health Resource & Needs Assessment Study. Report no. 3.31. Available at: http://www1.dshs.wa.gov/rda/research/3/31.shtm.

Washington State Department of Health. (2006). Substance Abuse Treatment Services for Youth. Report. Olympia, WA. Available at: http://www.doh.wa.gov/cfh/mch/mch_assessment/mchdatareport/2005_pdfs/ServiceChapters/sub_abuse_treat_yth.pdf.

Seattle King County Coalition for the Homeless, Youth and Young Adult Committee (2008). Plan to End Young Adult Homelessness in Seattle/King County. Prepared by Mark Putnam.

Training will cover, among other topics, trauma stewardship; de-escalation; GAIN-SS screening for mental illness and chemical dependency; motivational interviewing; recognizing post-traumatic stress disorder; dialectical behavioral therapy techniques; mental illness diagnoses and treatment.