# Description of Firewise Forests Initiative

Building on accomplishments of Fire Safe Forests initiated in 2006 through 2008 King County’s Forestry Program proposes expanding into a comprehensive Firewise Forests Initiative through:

- Convening and staffing a Firewise Advisory Committee

- Assessing feasibility of a chipper program and if feasible, helping to implement it

- Developing Community Wildfire Protection Plans (CWPP) for more communities

- Incorporating CCWP’s into the County’s regional Hazard Mitigation Plan

- Expanding educational effort – materials & website

The goal of the Initiative is to prevent the loss of lives, property and resources to wildfire while ensuring forest stewardship among landowners.

Project Description:

The Initiative will involve small forest landowners and forest residents in developing community wildfire prevention and implementation plans.  A King County forester will work directly with community residents through consultation sessions and visits to their forest properties.  The forester will also work with community members to develop forest stewardship plans for their individual properties, which for many will be the first step in implementing Firewise forest management practices on their land.  Studies have shown that a healthy forest with sufficient growing space for trees will be resilient, more drought tolerant and less susceptible to fire.

The Forestry Program will partner with educational institutions, non-profit organizations and/or community groups to provide written information and training sessions for forest landowners. Web-based fire protection planning resources will be developed and existing resources made available.  Community residents will be encouraged to share information with their neighbors.  Residents of forested areas will be also be encouraged  to consult with local fire departments to determine risk factors, such as ease of access to their home, appropriate home and street signing, that may need to be addressed in their plans.

In cooperation with the Rural Forest Commission, Washington Department of Natural Resources and other groups, the program will implement a chipper project to provide a means for property owners in Firewise communities to chip their wood debris.  This will promote wildfire protection by reducing fuels; it will provide an alternative to burning, thereby reducing smoke emissions; it will allow the waste wood to be put to a beneficial use; and it will provide an incentive for communities to embark on community wildfire protection planning.  This project would directly benefit carbon storage and reduce carbon emissions, supporting King County’s Climate Change Initiative.  The chipper project will start with a feasibility study in 2009, which will determine the best approach for providing the services (existing or new business enterprise, non-profit, or existing agency).  Depending on the results of the analysis, the Firewise Program will provide grant funding in subsequent years to support the implementation of the chipper project.

2009 Budget $118,505 ($45,000 in 2009 budget plus $73,505 of 2009 Title III funds):

$5,000 – Develop website (DNRP staff time) fire start map, risk analysis tools, risk assessments, clickable CWPP map (contract or staff time)

$24,000 – King County WLRD forestry program staff time

- Develop RFP for  and manage Firewise Chipper Project feasibility study

- Develop RFP for four CWPPs and manage

- Staff  Foothills Firewise Advisory Committee:

Fire Districts		Insurance Corporations	CERT

Fire Marshal		King County WLR		WDNR

PSCAA		Landowner Representation

$25,000 – Contract for a Firewise Chipper Program feasibility study which will include:

- An assessment of best business structure (NPO, existing, for profit)

- A review of appropriate equipment, best acquisition sources and cost ranges

- Program partners - contact them and get letters of support, commitments (KCD, WDNR, PSCAA, PSP, Pierce and Snohomish)

- Secure funding sources from partners and other grant sources

- Target communities - higher fire risk areas in King County, maps, basic information

- A model of how the program will be delivered

- Potential markets and end uses for chips indentified

- Benefits from the program: fire risk reduction, healthy forests, community engagement, carbon storage, students skills development and resume building

$10,000 – Chipper Program pilot program, depending on results of the feasibility study.

- Chipper services provided to communities with approved Community Wildfire Protection Plans (CWPPs) to support/incentivize healthy forest management

$40,000 – Contract - completion of four Community Wildfire Protection Plans (CWPPs)

- Four completed plans ready for state approval

$5,000 – DDES hours

DDES clearing inspectors will participate in the public planning process.  Participation in the public planning process may assist DDES to develop a programmatic permit covering forest management (e.g., thinning) related to fire safety plans.

$5,000 – Fire Districts staff hours

The local fire district[s] will assist with initial fire risk assessments, map and integrate CWPPs in their operational planning for participating communities.

The Initiative will establish a partnership among the County, local fire districts, the County’s fire marshal, Washington DNR and other agencies concerned with wild fire.

$4,505 – Outreach publications and mailings; printing and postage

The Initiative will provide resources such as videos, pamphlets, checklists or booklets to help landowners prepare their plan and implement elements of it: e.g., a planning check list, a “how to do a thinning” checklist, guidance on how to hire a forester, etc.

Estimated 2010 Budget $124,500:

Project will continue to support participation by forestry program staff, DDES fire marshal, and fires district personnel.  Work will include continuation of the advisory committee, a contract for several community fire plans, and implementation of the chipper project, directed by the feasibility study results.

Estimated 2011 Budget $40,500

Forestry staff will continue to manage the contract for community fire plans and implementation of the chipper project.